## Slide 1: Sharing on Project Lessons Learnt (PLL) conducted in PRPC for FY2016
Internal
Presentation by:
Reza Ikram A Rani
Profiling & Assurance (Project)

## Slide 2: Why do we need to conduct Project Lessons Learnt?
Internal
To gather any lessons learnt during the project that can be usefully applied to other projects
To capture the knowledge before the team disbands and secure the lessons learnt for the benefit of future project and future assessment
Improved knowledge to make better decision
BACKGROUND

## Slide 3: The PLL workshop shall be structured as to gain the most out of the participants. As a guide, the session should proceed and take heed of the following categories
Views about past experience are drawn from workshop participants, then grouped into the appropriate *categories which include the following;
        Engineering
        Procurement
        Construction
        Project Management
        Interface
        Contract
        Commissioning
        QA/QC
        HSSE
        Document Management
*The list is not exhaustive
Source:
PETRONAS Project Management System (PPMS 2009), Risk Management Manual
Internal
METHODOLOGY

## Slide 4: The causes or impacts of each issue is to be defined, and the issue will be ranked as high, medium or low based on the impact assessment / consequences
Lesson Description
Cause
Impact / Consequence
Action Taken / Recommendation
Impact Level
Internal
Source:
PETRONAS Project Management System (PPMS 2009), Risk Management Manual
METHODOLOGY

## Slide 5
Engineering & Procurement
Prior to SG1
PLL Workshop
End of Execution Phase
Construction
Commissioning
Prior to SG2
Prior to SG3
Refer PLL
Refer PLL
Refer PLL
PLL
Database
Prior to ITB
Pre Start-Up
Conceptual
Design
FEED /
Basic Design
25% Construction
50% Procurement
Post Engineering
15% Construction
PRA
SRA
CRA
PLL
QUANTITATIVE
QUALITATIVE
Pre-FID
20% to 30% of total execution progress
Construction
Mandatory
Optional
PIR
Source:
PETRONAS Project Management System (PPMS 2009), Risk Management Manual
This slide was approved during 10 June 2015 Project Risk Management Working Committee (PRMWC)
PIC Portfolio PRM Framework dictates the requirement of PLL which is identified at each phase of the project life cycle and at a predetermined frequency to capture lessons from project in progress up to the acceptance of the project.
FRONT-END LOADING (FEL)
EXECUTION
START-UP
OPERATION
FEL 2
Scope Selection
FEL 3
Scope Definition
FEL 1
Feasibility
PHASE
“Doing the Project Right”
“Doing the Right Project”
FRAMING
Gate 0
Gate 1
Gate 2
Gate 3
Gate 4
FID
Internal
FRAMEWORK

## Slide 6: 6 Project Lessons Learnt workshops were successfully conducted in FY2016…
Internal
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
PLL P18A & 18B
PLL RC P3
TIMELINE
PACKAGE 2
Refinery & Cracker
Engineering & Procurement
22 November 2016
PACKAGE 3
Refinery & Cracker
Engineering & Procurement
6 October 2016
EURO 5
Refinery & Cracker
Prior FID (FEL)
25 November 2016
PAMER
Close-Out
19 December 2016
PACKAGE
Close-Out
28 January 2016
20C2
PACKAGE
Close-Out
26 May 2016
PLL AWARENESS
Refinery & Cracker
8 September 2016
RGT-2
Gas & Power
Engineering
1 May 2016

## Slide 7: …where 132 Lessons Learnt were identified mostly covering these 5 categories
132
Project Lessons Learnt identified
41
Engineering
19
Project Management
13
Procurement
12
HSES
8
Document Management
Internal
6
Project Lessons Learnt activities
FRAMEWORK

## Slide 8: Engineering Lessons Learnt is recorded the highest in the PLL past year (FY2016)
41
Engineering
FY2016
Project Lessons Learnt
Delays in Change Order Approval
Unfamiliarity of PTS requirements and project specification by EPCC/Vendor
Late mobilization of iPMT to home office
Internal
Interdisciplinary design changes not properly escalated / communicated amongst EPCC/PMT
Lack of communication between PRPC Core Engineering, LICENSOR and FEED team
Failure to timely acquire plot plan
Common PLL identified in PRPC Projects
ENGINEERING

## Slide 9: Project Mgmt. Lessons Learnt is recorded the 2nd highest due to challenges dealing in integrated project
19
Project Mgmt.
FY2016
Project Lessons Learnt
Common PLL identified in PRPC Projects
Untimely mobilization of sufficient workforce to Home Office / Site
Challenges in doing project in fast track environment
Proper platform for grievance management for workers
Internal
PROJ. MGMT.

## Slide 10: Procurement & HSES are also amongst the most common Lessons Leant identified for PIC projects
13
Procurement
FY2016
Project Lessons Learnt
Internal
12
HSES
FY2016
Project Lessons Learnt
Delay in delivery of critical equipment & materials due to the enforcement of CIDB/COA
Unfamiliarity of PETRONAS requirements by EPCC/Vendor
High turnover of Safety Manager at EPCC level
Non-compliance with confined space and scaffolding activities
Common PLL identified in PRPC Projects
Common PLL identified in PRPC Projects
PROC. & HSES

## Slide 11: Lessons learnt for each phase of project implementation including the project closeout has been captured in a structured centralized database for any referencing by all project management team in PRPC
Active Risk Manager (ARM) system is developed for PRA and PLL management.
It is an online centralized database for real time sharing and learning to projects.
Internal
SYSTEM
Database

## Slide 12: Challenges
Internal
No proper platform for PLL to be documented
Disbandment of Project Team / Contractor prior PLL
Discontinuation of FEL team to Execution team
Improvement
Project team to conduct PLL before project close-out
Ensure continuity from FEL to Execution ; or
Ensure proper handover
Establish centralized PRPC database for PLL
Few challenges faced in conducting PLL in FY2016
CHALLENGES

## Slide 13: Project Lessons Learnt target to be conducted in Q1 FY2017
Internal
JAN 2017 | FEB 2017 | MAR 2017
FY2017 Q1
PACKAGE 5
Refinery & Cracker
Engineering & Procurement
PACKAGE 1
Refinery & Cracker
Engineering & Procurement
PACKAGE 4
Refinery & Cracker
Engineering & Procurement
Setapa / Ramunia
MOLF
Close-Out
C4 INA
Petchem
Prior FID (FEL)
Quarter 1

## Slide 14: Way forward
Further syndicate with GPD, PD&T to explore possibility of sharing PRPC PLL database for group-wide benefits.
  E.g. :
  Development of Share-point to be utilized by all PETRONAS project; or
  Establishment of centralized database at PETRONAS level.
PRPC project team to incorporate its respective PLL planned activities for FY2017 and subsequently share the plan with PRPC Risk Management
Internal
WAY FORWARD

## Slide 15: Thank you
Internal

## Slide 16: PLL Impact Level
Impact Level | Description
1 | Low priority action for improvement (Individual / Project Level)
2 | Medium priority action for improvement (Discipline / Functions / PMO Level)
3 | High priority action for improvement (Organizational Level)
Reference:PPMS_910-001_Project Risk Management Manual v1.0.doc
Internal

## Slide 17: Next Action (PLL Deliverables)
Internal
1st draft of the PLL findings (in excel) will be shared to PMT 2 days after the workshop for review (3 working days)
The reviewed PLL to be submitted to PRPC Risk Management team for final report
PRPC Risk Management to generate PLL Management Report (5 working days after receiving it from PMT)
PLL Management Report is to be approved by Project/Package Manager
Approved PLL Report will be kept in PRPC centralized database for future reference