## PLL Report - 2
PIC Project Lesson Learned
Owning Item | Package | Categories | ID | Lesson Description | Cause | Impact / Consequences | Action Taken / Recommendation | Action Title | Impact Level
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Planning | 5287 | (Good PLL): Construction manpower (direct workers) sufficiency were less affected by the low productivity and inconsistency of performance by local workers. | 1. Low productivity of local workers. | 1. Limited occurrence of manpower pinching/movement between RAPID packages or other projects within Malaysia |  | 14406 - Action Taken: iPMT highlighted to EPCC Contractor on the forecasted insufficient skilled workers in Malaysia. 14407 - Action Taken: EPCC Contractor was receptive to owners proposal to engage more Chinese contractor and manpower. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5445 | 1. No availability of EPCC/Rotating Field Engineers at site. 2. No clear cut separation in term of role for Rotating Superintendent/Rotating Field Engineer at site | 1. EPCC has mobilized all the Rotating Field engineer back to their Home office in Gurgaon. 2. EPCC has hired new mechanical erection (static & rotating) site engineer. However, the transition in term of info from the Design Rotating engineer back in home office to the site mechanical rotating erection engineer is lacking. | 1. Delayed in preparing/getting all the latest drawing/info on rotating equipment. Unaware of Latest ITP, approved rotating procedures and applicable PTS/project specs. 2. Delayed in deliverable such as Rotating Lubrication List, SPIR list, special tools and others. |  | 14550 - Action Taken: Stationed one existing field design engineer back in site office in assisting construction/erection team. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | HSSE | 5883 | 1. PDR statement is about the OFFLINE 100% INERGEN spare scope deleted but the requirement of ONLINE 100% spare INERGEN is compulsory. 2. Mismatch between PDR and BOMBA requirements | 1. Lack of engagement / discussion between MIE (EPCC appointed Local Permitting consultant) with EPCC Engineering office in Milan to get update on local authorities’ requirement. 2. The PDR deleted the scope which included BOMBAs requirements | 1. Cost and schedule impact. 2. Non- compliance to regulatory requirements |  | 15170 - Recommendation: Regular meeting to be conducted between Contractors Engineering Home office in Milan and local permitting consultant by weekly basis. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Project Management | 5868 | 1. Poor Subcontract Management by EPCC Contractor at site 2. Poor coordination in Subcontracting activities at Engineering office | 1. Contractor Focal person from subcontracting department not full time in Engineering office (located in home office) and poor IDC ( internal discipline check) by QAQC and others department. 2. Lack of project control in managing subcontractor at site. | 1. Project delay |  | 15151 - Recommendation: Dedicated Subcontracting personnel to be full time and as a key personnel in Project Org Chart. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Precommissioning/Commissioning | 5668 | 3D Vendor / LLI shall be incorporate in the main 3D model. | 1. Requirement of the 3D Model for the LLI was not be fulfilled as per requirement. | 1. The 3D session was carried out in general review without going into details. 2. The 3D model requirement shall be put in the LLI packages in clear and specific. |  | 15058 - Action Taken: CONTRACTOR shall develop as per 3D model requirement and incorporate into the model. 15059 - Recommendation: Dedicated SSP personnel for LLDPE package required. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Quality | 5872 | 60 % Engineering Audit findings - 12 out of 39 Findings still open during 90% Engineering Audit | 1. Poor QAQC management of EPCC Contractor and lack of intervention by EPCC Project Director and Project manager | 1. Schedule - some of findings required re- work |  | 15156 - Recommendation: A dedicated QAQC manager and QA Engineer to be stationed full time in Engineering office. Audit closure to be part of project milestone payment. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5948 | 60% and 90% 3D model review was conducted with incomplete 3D model | 1. EPCC not familiar with 3D model tools (1st time user) | 1. Most of the 3D model review comments not incorporated in timely |  | 15753 - Action Taken: Most of the comments closed during construction phase 15754 - Action Taken: EPCC engaged 3rd party specialist for 3D model 15755 - Recommendation: To consider 3rd party specialist for 3D modeling from tendering stage | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5207 | A lot internal design changes during fabrication stage that cause delay awaiting for approval | 1. Unclear PTS requirement and late discovery of technical issue vendor engineer inexperience with PTS & Project specs | 1. Additional VO 2. Delay in schedule |  | 14266 - To share lesson learn (design issue) from other project from time to time by engineering team. 14267 - To allow buffer time after PO issuance for any engineering issue to be resolved quickly. 14268 - Experience vendor engineer is required to anticipate future engineering drawing problems | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5985 | A lot of motor feeders (MCC) are not properly sized | 1. No motor datasheet for verification | 1. A lot of critical findings were captured during commissioning stage |  | 15815 - Action Taken: Restudy/rematch MCC to the correct sizing | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Award/Contract | 5887 | A lot of times CONTRACTOR upheld Licensor’s requirements / specifications that contradict OWNER’s requirements without first informing thus obtaining OWNER’s approval. | 1. CONTRACTOR failed to appreciate the technical requirements order of precedence. It also failed to observe the requirement for OWNER to be consulted in cases of discrepancies and that the general rule is the more stringent shall apply. Where regarding Engineering, an example of the level of priority is between Licensor’s and OWNER’s specifications. For one, the Contract provides for any discrepancies between Licensor’s requirements with any other technical requirements that CONTRACTOR needs to comply with, CONTRACTOR needs to consult the Licensor for a solution that does not deviate from OWNER’s requirements and OWNER’s approval shall be sought. But CONTRACTOR had failed to observe this process amongst other processes that it needs to adhere to in delivering its detail design. | 1. Schedule and cost |  | 15178 - Recommendation: It needs CONTRACTOR management (at Project level) action to ensure compliance awareness. 15179 - Recommendation: Contractor shall give trainings to all its key personnel on awareness of technical requirements and order of precedence of technical documents 15180 - Recommendation: Kick-off meeting | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5832 | AC / DC UPS Battery Autonomy Time | 1. RAPID Project Specifications (RAPID-FE1-TPX-ELE-DES-0001-0002_Rev.3, RAPID-FE1-TPX-ELE-SPN-0001-0005_Rev.0, RAPID-FE1-TPX-INC-DES-0001-0003_Rev.3) provides requirement for AC / DC UPS Battery Autonomy Time | 1. OWNER had made comments on CONTRACTOR’s documents and drawings to have longer AC / DC UPS Battery Autonomy Time than RAPID Project Specifications. |  | 15503 - Action Taken: CONTRACTOR had issued 3 (three) numbers of Technical Query (“TEQ”) as attached below. 15504 - Action Taken: OWNER instructed to have longer AC / DC UPS Battery Autonomy Time than RAPID Project Specifications. 15505 - Recommendation: Preventive Action.- In order to avoid conflict between OWNER & CONTRACTOR, Revision of the Project Specification to have OWNER’s requirement clearly is necessary.- PDR or New Memorandum for CONTRACTORs can be an alternative solution. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5736 | ACC Pit Design: Resizing of ACC basin / pit. | 1. The project specification - Process Philosophy only mentioned the first 15mm rain water WITHOUT including the liquid filled volume of ACC lines. | 1. The First Flush (FF) pit will be filled up with liquid in the ACC lines first and therefore dirty rain water will flow direct into the STW which cause environmental issue. |  | 15296 - Action Taken: The pit size was enlarged to include filled volume of ACC lines. 15297 - Recommendation: Specification to be updated. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5107 | Accessibility during operation & maintenance on vertical vessel e.g. manhole at the top instead of at the bottom | 1. PTS is not clearly specify the location of the manhole | 1. Potential safety issue during operation 2. Required to relocate the manhole (at fab shop) caused longer time for the fabrication |  | 14208 - Action taken: Relocate the location of the manhole 14209 - Recommendation: Revisit PTS requirement | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2094 | Actual productivity lower as compare to plan | Inaccurate estimate for dumping ground haulage distant. | Excavators under utilized | Mobilise additional resources e.g lorry | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5426 | Actuator sizing for EIV was done at 6 bar, which RAPID specs call for lower pressure (should be 4 bar). | 1. Incorrect reference of project documents 2. Inconsistency in requirements between FEED and project spec. | 1. EIV Air Buffer Vessel was sized at 6 bar (requirement is 4 bar) due to differential pressure that has to be maintained with the actuator 2. CONTRACTOR is now stuck with actuator sized at 4 bar, and PDR for affected 10 tags are not approved 3. Major delay to EIV inspection |  | 14520 - Action Taken: CONTRACTOR was requested to submit a PDR. Some tags were rejected (10 tags rejected and 135 tags approved) 14521 - Recommendation: EPCC to get clarifications upon any encounter of conflicting documents and EPCC should not make assumptions | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5686 | Additional breather valve for silo | 1. Polymer transportation or Vent can be lead pressure rising or vacuum in the silo. (HAZOP recommendation) | 1. New additional breather valve is installed for the silo. It is impact to cost and plot. |  | 15083 - Recommendation: To minimize design change from HAZOP, study BP and LL in the early stage or engineering. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5687 | Additional flow meter for service water | 1. OWNER requested to provide flow meter for service water line in the battery limit even though it is not mentioned in the project spec. | 1. Provided additional flow meter on service water line and issued change order to OWNER. |  | 15084 - Action Taken: The work scope and interface with other contractor has to be discuss and finalize in the bid stage or early stage of engineering to avoid late design change. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Construction | 6032 | Additional land had to be acquired after PCC contract was already awarded | 1. The lands (Bukit Pelali) was in the process of being alienated, and was not yet marked as private lots during the initial land acquisition process. 2. The lands (along Section 3 pipeline) was marked as State Land during the initial land acquisition process, but was actually under KEJORA. 3. The lands (Felda & Plot D & Plot E) around perimeter of Seluyut impoundment area were not identified earlier due to survey area. | 1. Out of sequence construction activities - construction activities had to be rearranged, resulting in a few remobiization and demobilization. 2. Additional land acquisition of private lots had to use Borang I approach, resulting in additional cost. 3. Delay in overall impounding of Seluyut Dam because the clearing of Plot D and E had to be completed first. |  | 15577 - Action Taken: Negotiation with contractor to rearrange the construction activities. 15578 - Action Taken: Borang I approach (for land acquisition of private lots). 15579 - Action Taken: Directly approach State agencies (Dato SS, Jabatan Hutan, UPENJ) for assistance to acquire Plot D & E soonest possible. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6089 | Addressing the authority requirement on marine work | 1. Most of the main activities later start such as dredging, marine piling, land piling and RC structures work. 2. Interfacing between contractor and auhtorities due to late approval, late submission of method statement and sometimes the equipment is not ready such pending inspection by related authorities. | 1. More time is required to complete the dredging work |  | 15567 - Recommendation: CONTRACTOR must always alert to submit all necessary documents, drawings and method statement in advance to avoid any delay before work start. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Interface | 6073 | Adhoc water demand / request by Lebam reservoir to support RAPID and community. | 1. Insufficient water supply by state government. 2. Drought season. | 1. Expedite extra piping from PAMER to the reservoir – VO. 2. PAMER cannot perform the hydro test as per planned. 3. Schedule delay. |  | 15661 - Action Taken: Reschedule hydro test. 15662 - Action Taken: Start using permanent supply and stop emergency supply to carry out the hydro test. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Procurement | 5404 | Aggressive planning by Contractor on sub orders placement after placing order | 1. Some vendor will go to multiple sub-vendors. | 1. Delay in delivery of vendor package. 2. Delay in getting VDI. |  | 14455 - Action Taken: Advised Contractor during weekly meeting to list out in details on post PO progress for critical equipment and items with potential delay due to late receive on materials or delay in start of fabrication activity. 14456 - Action Taken: Mitigation and Monitoring thru weekly expediting meeting for materials receive status and fabrication progress to ensure delivery schedule as per plan. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Interface | 6265 | Agreed scope during planning stage not captured by execution team | 1. Scope not properly defined. 2. Incorrect project management process. | 1. Schedule impact. |  | 16392 - Action Taken: Owner engaged CD interface and coordinate work with EPCC. 16393 - Recommendation: Keep formal correspondence for reference and monitoring. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5495 | All piping GADs/ ISOs are held up which in turn delay in civil pipe supports/ platform drawings till the time P IDs are approved. | 1. Schedule has been prepared considering the same aspect. | 1. PIDs approval impacting other discipline deliverables. |  | 14626 - Action Taken: If such a condition exists in any project then request for deviation for the same should be made to client at the beginning of the project itself so that Piping and Civil could continue to issue their drawings. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5930 | All VCR has to be solved before awarding the PO or prior to FAT. | 1. No proper management to track and expedite the resolution of VCR. 2. Vendor delay the submission due to vendor no commitment to follow project spec especially Electrical and Instrumentation. By doing this, vendor is hoping that due to tight schedule, the VCR will be waived. | 1. A lot of VCRs has not been issued by the vendor resulting all the of them has not been approved prior to FAT. Hence the FAT has been conducted with lots of pending VCR submission which has to be solved at site. |  | 15715 - Action Taken: A focal person is assigned to track the status. 15716 - Action Taken: To ensure that site people knows that the equipment is not fully accepted yet even after the FAT, the Inspection Release Note has to be attached with all pending VCR. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5932 | All vendor deliverables shall be getting Code 3 approval before the delivery of the equipment at site. | 1. Lack of commitment from vendor side to finalize the document plus lack of expediting from contractor side. | 1. A lot of documents has not reaching Code 3 Approval even after delivery of the equipment at site (happened to all rotating equipment) |  | 15719 - Action Taken: Few meeting were conducted with non-performance vendor to highlight delay of the document. Target date is given for vendor to commit. 15720 - Recommendation: Contractor should send their rep to office of all non-performance vendor to monitor and expedite the submission of the document. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5552 | Anchor bolt at foundation was not cleaned immediately after concrete pouring done. | 1. CONTRACTOR did not comply with Method of Statement and concrete pouring procedure. | 1. Anchor bolt was not cleaned after concrete pouring and the remain concrete was cured on the anchor bolt. It is time consuming to remove the hardened concrete and has the possibility of damaging the anchor bolt thread during removing of hardened concrete. |  | 14765 - Action Taken: CBMI to clean the hardened concrete before handover to other discipline for installation of structure. 14766 - Recommendation: Anchor bolt protection shall be available before concrete placing. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Quality | 6008 | Anti-Termite treatment application not as per PTS | 1. PTS not being properly read | 1. The ground floor slab being cast without anti-termite treatment to the ground |  | 15855 - Action Taken: Anti-termite treatment being injected by drilling the ground slab 15856 - Recommendation: EPCC supervision team must be competent | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5607 | Any deviation from MVL shall require Pre-Qualification exercise. | 1. In MVL, certain OEMs have origin as International while others have specified location. Pre-Qualification exercise is required for those with specific location as origin when OEM indicated different origin. | 1. More time is required to response to CONTRACTORs Recommendation to Award since approval is required to be obtained for the change in origin. |  | 14892 - Action Taken: Requested CONTRACTOR to provide relevant documents to explain about the change of origin and submitted memo to seek Managements approval to accept the change in origin. 14893 - Recommendation: MVL to be managed by specific department e.g. GSCM to ensure that information in MVL is updated and all projects to source the MVL from such department only. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5447 | AOC/COC/ACC Pumps(Low Shear requirement) | 1. In ITB, FEED data specified centrifugal pump as the pump type while there is a note for low sheer type to avoid emulsion. 2. Based on vendor recommendation as well PTS 31.29.02.11 - Pump Type Selection Procedures, Positive Displacement pump - Progressive Cavity vertical type (is the preferred pump type for the intended service. 3. CONTRACTOR has overlooked the requirement to have low shear pumps in order to avoid emulsion, causing the delay in issuance of Technical Query for further clarification | 1. Delayed in PO issuance and Pump delivery at site. 2. Additional man-hours spent for re-clarification/document review process. 3. Issuance of additional change proposal (cost adder). |  | 14553 - Recommendation: The requirement shall clearly be highlighted in the ITB/ Contract, not under Notes section of the data sheet. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Procurement | 5865 | Application and Approval | 1. E-Permit: data Transferred by the MTO into the e-permit is inconsistent with the supporting documents 2. Documentation: Incomplete and / or incorrect supporting documents 3. Physical Verification: Failure during the physical verification due to container seals broken, invisible marking, damage tagging, mixed material inconsistent with supporting document. 4. Tariff Code: Incorrect selection of tariff code 5. Mill Test Certificate: Inability to provide original Mill Test Certificate 6. TPIB Form: Incomplete TPIB form | 1. Cost and schedule impact. |  | 15143 - Recommendation: MTO/EPCC focal person to check the draft e-Permit prior for submission 15144 - Recommendation: MTO/EPCC focal person to review supporting documents prior to uploading into e-Permits & submission of hardcopy to CIDBs desk verification officer 15145 - Recommendation: Ensure seals are intact, conduct verification at site, and ensure tagging intact, declared material consistent with submitted supporting documents. 15146 - Recommendation: Select appropriate tariff code in accordance to the approved PRPC tax exemption list 15147 - Recommendation: In the absence of original mill test certificate to issue certified through copy certificate together with authenticity letter with back to back declaration letter from EPCC authenticate by relevant Project Directors 15148 - Recommendation: One TPIB for one manufacturer and for fabricated steel structure, fabricator is equivalent to manufacturer. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Project Management | 5517 | Appointment of FEED CONTRACTOR (TECHNIP), LICENSOR (AXENS PL) and INTEGRATOR (AXENS P²) which are very familiar with the context of the RAPID project | 1. They have been involved in the past phases of the original RAPID, namely in Conceptual Study, License package & FEED phase. 2. RAPID project specifications were already familiar to the project team | 1. Very committed and competent project management team of PRPC. 2. Fast and efficient decision making of PRPC. 3. Presence of representative of FEED contractor in LICENSOR office during PDP development 4. Early sharing of Process document to FEED contractor. |  | 14670 - Action taken: Contracting LICENSOR as the integrator and leader during IPS and FEED contractor as sub-contractor. In the past, the main lead was always the FEED contractor. 14671 - Recommendation: Since the team is quite familiar with the RAPID context, it is recommended to appoint manpower/personnel with appropriate knowledge & past experience to the right fucntion/discipline to increase the effectiveness of the IPS realisation. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Procurement | 6195 | Approved Vendor List registration. | 1. Some of the Approved Vendor List is not registered under YEI. | 1. Unnecessary waste of time to register under YEI. |  | 16233 - Recommendation: Ensure required PETRONAS approved vendors is registered under EPCC prior to EPCC award. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5713 | Architecture: OSB configuration changes in mid of execution. | 1. Manning philosophy definition by OR team came later after execution started. 2. AMT team and operation manning increased in number led to changes in OSB design. | 1. OSB layout had to undergo several changes due to changes in Operations manning requirement. |  | 15237 - Action Taken: Offset few changes such as minimized lab and storage area against the increased in AMT room, operation room and changing room. 15238 - Action Taken: Changes was agreed to be absorbed by CONTRACTOR although floor area has increased with additional external workshop. 15239 - Recommendation: Operation readiness manning philosophy has to be cascaded to PMT at the beginning of execution stage. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Award/Contract | 6251 | Argument on detail scope during execution (i.e. change order - TRS) | 1. No detail scope (FEL3 deliverables) 2. Proposal accepted as contract document | 1. Unclear local requirement 2. PMT to cover extra workload |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5935 | As per EPCC CONTRACTORs proposal, engineering work was to be performed by M/S: SMHB Sdn. Bhd., an Engineering Subcontractor to EPCC CONTRACTOR. | 1. Everything done on this Project by EPCC CONTRACTORs Instrument Team was first time activity for the individual. Hence, the quality of work was very poor, which caused lot of rework, delay in engineering and resulted in increase of review time cycle. | 1. Due to some reasons, EPCC CONTRACTOR had decided unilaterally to perform the Instrument Engineering on their own without involving SMHB Sdn. Bhd., engineers, though they did not have experienced and sufficient enough infrastructure to perform Instrument Basic and Detailed Engineering. |  | 15724 - Action Taken: Informed it to the Engineering Management and also many Instrument Meetings resulted in educating Instrument Engineers on the basics of Instrumentation Engineering and associated requirements. 15725 - Recommendation: When the EPCC CONTRACTOR proposal was to use a third party engineering contractor to perform the engineering, third party should have been allowed to do the job instead of EPCC CONTRACTOR interfering in the middle | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5894 | At the beginning of the project the number of employees involved for Secretary and Document Control activities are a few respect of the pick. So all the TF register that name (references) and not send the deliverables/request to the new arrivals. |  |  |  | 15189 - Suggestion for Improvement: To create at the beginning of the project a common email address readable from all the person in charge | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5634 | Auditors from PMC / Core Engineering who involved in UPT document reviews shall be from independent personal. | 1. To avoid conflict of interest. 2. Shortage of auditors. | 1. Conflict of interest. |  | 14957 - Action Taken: Internal audit by the project team prior to the actual audit. 14958 - Recommendation: To follow audit procedure. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Engineering | 6285 | Authorities imposed penalty on STP | 1. Authority approval not obtain before start of construction works. | 1. Delayed the operation process 2. Schedule delay 3. Risk of penalty impose by authority. |  | 16431 - Action Taken: Work closely with authorities to close out the issue 16432 - Recommendation: To engage consultant that have STP background and experience. 16433 - Recommendation: To have dedicated focal person to follow up with authority. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5786 | Average PDR turnaround time of 35 days in 2016. | 1. Core Engineering signature requirements were too lengthy. 2. In addition to the long time needed to agree on the technical solution, sometimes there were delays due to obtaining formal approval which could require up to 10 signatures. | 1. Prolonged response time to contractor. |  | 15421 - Action Taken: The project team took a proactive approach by sharing subjects that required PDR approval in advance with PTAs so that the lead time after PDR issuance by Contractor could be reduced. 15422 - Recommendation: Signatory requirements should be streamlined and reduced where not relevant. 15423 - Recommendation: A linkup to PDDM system for E-signatures should be adopted so that the mode of approval could be simplified (i.e.) without requiring printer / scanner which could be unavailable when they are travelling. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5553 | Backfilling and compaction work was not completed upon ground beam casting. | 1. It was reported by CONTRACTOR that there is a miscommunication between CONTRACTOR and SUB-CONTRACTOR resulting proper sequence of work was not followed. | 1. CONTRACTOR had constructed the ground beam without performing backfilling and compaction. 2. It has resulted gap under the ground beam whereby the area is restricted for proper backfilling and compaction. |  | 14767 - Action Taken: Issued NCR to CONTRACTOR to record and mitigate. 14768 - Recommendation: Establish the sequence of work during construction of building. Expedite the backfilling and compaction activities. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5104 | Ball valve hard facing material did not follow PMRC requirement. <Conflict of PTS> | 1. CCSM considered instrument on-off valves shall follow instrument project specifications. In PTS, it mentioned the hard facing material shall be recommended by vendor. But vendor proposed material is different with PMRC. | 1. Potential schedule and cost impact |  | 14201 - Action Taken: Owner / PMC reviewed the service for each instrument on-off valves and partial accepted the material proposed by vendor. For the rest of the valves, the hard facing material shall follow PMRC requirement. 14202 - Recommendation: For instrument on-off valves, the material and testing shall also consider the requirement from PMRC. 14203 - Recommendation: The related design shall be cross checked by other disciplines to ensure all required specifications are followed. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5504 | Baseline Thickness Measurement Location | 1. Insufficient guidelines provided in the ITB - Sec C - Part II - 4.6 Material Corrosion Insulation | 1. Dispute in the requirements. |  | 14642 - Recommendation: To provide clear requirement | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5266 | Baseplate Grouting: Difficulty in grouting activities for pumps with not vent hole as we have to ensure that the forms are properly installed for the seal grout. | 1. PTS 31.29.02.30 requires that there are not grout fill or vent hole. | 1. Difficulty in grouting and ensuring that the grout is properly vented. |  | 14373 - Action Taken: Recommend to allow deviation to PTS 31.29.02.30. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Interface | 5113 | BENCHMARK COORDINATES: 1. Shifting the Refinery coordinates during construction. 2. The installed benchmark has moved from original position. | 1. Delay in HAZOP in other packages, that affecting the package layout that will affect the overall dimension of the Refinery plot. 2. Benchmarck not install as per standard. Also, uncontrolled external factors (vehicle, machineries) that might cause the benchmark to moved. | 1. Potential cost impact 2. Will affect the IP coordinates between packages. Also the connection of any piping, structures, etc if they have been installed before the change of coordinates. |  | 14220 - Recommendation: Finalized the Refinery dimension and coordinates before contract award, or at least before construction stage starts. 14221 - Recommendation: Re-locating the Common benchmark. Install as per standard. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5817 | Best Practice: 3D Model Fix - Use 3D model as information interface to communicate among people concerned. |  | 1. Designers can review model status by applying Color Set file under Review S/W. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5834 | Best Practice: Applying Multi-bore orifice plate rather than Conventional orifice which requires straight run. |  | 1. As per RAPID-FE1-TPX-INC-DES-0001-0006, para.10.2 Flow Instruments, “When straight length requirement is not possible, V-Cone, multi-bore orifice plate flow-meters (Conditioning orifice plate) or pitot tubes shall be considered.” CONTRACTOR applied Multi-bore orifice plate in order to avoid reflecting straight run pipe. |  | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Award/Contract | 5803 | Best Practice: Award of local Authority approvals and site permitting contract in time to start site works. |  | 1. Smoother the project execution. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5708 | Best Practice: Based on experience from 30% model review, the session could take a lot of time and not timely effective. |  | 1. Improvement in 60% and 90% model review. This was achieved by breaking the session into piping / process, electrical and instrument separately. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5692 | Best Practice: Catalyst holding drum as a piping pot. | 1. Catalyst holding drum is manufacturing by stationary vendor, but it is verified to piping item like piping pot. | 1. Because it is verified to piping item, it will not be applied DOSH. This is discussed and confirmed with OWNER. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6331 | Best Practice: Civil: Improve design pipe rack foundation | 1. Minimize rock excavation | 1. Minimize schedule impact by minizing foundation depth. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6333 | Best Practice: Civil: Relocate SI holes. Expediate SI works | 1. All SI holes is at P3 office and canteen area. | 1. Schedule impact 2. Late handover (P3 to P28B). |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6332 | Best Practice: Civil: To support construction driven schedule | 1. Issuance of IFC drawing ahead. 2. Strong support and full commitment from CTCI (civil discipline). | 1. Meet the construction schedule. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5777 | BEST PRACTICE: Cohesiveness between PMT and EPCC engineers. | 1. Good Practice on collaborative problem solving with PMT / EPCC engineers working together to find acceptable technical solutions to problems. | 1. Resolves multiple technical issues through rigorous communication to avoid schedule impact. |  | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Undefined | 6312 | Best Practice: Contractor having good cash flow | 1. Contractor is an established company with good financial standing | 1. Able to provide additional manpower more than planned |  | 16487 - Recommendation: To consider company with good financial record | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Project Management | 6304 | Best Practice: Contractor Management Support | 1. Contractor Management always proving support to the project, always have the Do FIRST attitude. | 1. Reslove contractual issues, to avoid holding back to construction |  | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5691 | Best Practice: Discussion for movable platform during model review. | 1. During 90% model review, shared / discussed with OWNER the location and list that cannot provide permanent access. | 1. 3D model review is good tool/time to share / understand situation with OWNER. Movable platform will be provided as a ready-made goods. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5695 | Best Practice: Early start of main P/R piling and U/G work. | 1. SC tried to start piling and U/G work earlier than base schedule as a mitigation plan for rainy season. So, pile load test was proceeded simultaneously when soil investigation was proceeded. It can be lead to finalize pile design earlier. | 1. Baseline Schedule was Aug. 2016 for main P/R piling but actual is July 2016. (2 months ahead). |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6351 | Best Practice: Electrical: Better spec for cable by include anti Rodent protection | 1. Lessons learnt from other packages. | 1. Avoid cable damage by rodent |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6349 | Best Practice: Electrical: Originally Lighting JB termination using teed cable joint. P28B using terminal block for improvement. | 1. Lessons learnt from P1. | 1. Proper termination. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6350 | Best Practice: Electrical: Use higher voltage rating for electrical process heater to reduce cable ampacity | 1. Due to constraint work space. | 1. Cost reduction. 2. Reduce no of termination. 3. Reduce no of cable use. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5753 | Best Practice: EPCC Contractor successfully adopted the wireless technology for implementation in EOEG. |  | 1. EPCC managed to gather technical input and justification to convince Licensor for wireless implementation to monitoring signals. 2. Reduction in cost and expedite installation at site. |  | 15340 - Action Taken: Wireless technology implemented at EO EG plant for monitoring signals. 15341 - Recommendation: Wireless technology implementation shall be promoted group wide in view of cost and installation efficiency. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5818 | Best Practice: Equipment vendors’ actual platform 3D model incorporated in SC 3D model to enhance the engineering quality |  | 1. We can easily check interference or clearance between SC 3D model and vendor platform design. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5792 | Best Practice: Establish communication lines with Owner Team / Site teams. |  | 1. Smoother the project execution. |  | 15438 - Recommendation: Effective Coordination to be established with rules Email discipline. 15439 - Recommendation: Face to face discussions are recommended for every opportunity. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Award/Contract | 5799 | Best Practice: Establish document management system day 1 ( contracts filing and maintenance methods). |  | 1. Smoother the project execution. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Award/Contract | 5801 | Best Practice: Establish early mobilization of subcontractors in order to carefully plan the work and join in constructability reviews. |  | 1. Smoother the project execution. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5791 | Best Practice: Establish relationship with Contractors team and establish Owners needs and expectations. |  | 1. Smoother the project execution. |  | 15437 - Recommendation: Practice PCB with Contractors and Subcontractors | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Award/Contract | 5800 | Best Practice: Establish subcontracting plan and execution strategy for early approvals by including it in the 120 day look ahead schedule. |  | 1. Smoother the project execution. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Award/Contract | 5804 | Best Practice: Evaluate earliest possible Subcontract awards. |  | 1. Smoother the project execution. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6190 | BEST PRACTICE: Excellent collaboration between PETRONAS and YKM to develop advance system solutions (P-TASK) | 1. Major gaps from P14. | 1. Implementation of new IP for PETRONAS. 2. Avoid possible schedule and cost impact from P14. |  | 16226 - Action Taken: Full commitment and support from higher management from PETRONAS and YKM. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5694 | Best Practice: Flowmeter – Dual sensor type. | 1. In the FEED, 2 flow meters are applied for DCS and ESD. | 1. Change the type of flow meter from flow meters to 1 dual sensor type flow meter to minimize straight run on the line. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5659 | Best Practice: Full commitment / adhoc support from CONTRACTOR in dealing with incomplete deliverables / managing issues. | 1. Full commitment and support from CONTRACTORs management in dealing with contract requirement. | 1. CONTRACTOR had mobilized additional numbers of project control from their Home office team to support the completion of Level III Schedule. 2. Managed to complete pending deliverables to avoid further delay. |  | 15032 - Recommendation: To maintain continuous support from CONTRACTORs HO team to ensure the deliverables and contract requirement is fulfilled. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Award/Contract | 6302 | Best Practice: Good Project Manager in handling contractual issue. Willing to discuss and resolved many issues | 1. Pro-active and willing to discuss to get issue resolved | 1. Resolve many issues |  | 16469 - Action Taken: Proactive | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5828 | Best Practice: Grating Positioner without Welding |  | 1. To minimize the site-welding, HILTI standard product will be used for grating positioner. 2. In accordance with RAPID-FE1-TPX-CVS-ST-0001-0004 sheet: 20/23 GRATING TYPE 1, “4 stud welded or actuated fastened positioners” shall be used for grating positioning. 3. M8 S-BT type had been suggested and approved for grating positioning. This type has the advantage as like; i) Not required gun powder and easy installation whereas in case of utilizing gun powder type only authorized person can do this work. ii) Sealing washer is used to make sure no exposure for drilled hole from moisture or debris iii) Easy maintenance due to local Vendor available. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6340 | Best Practice: Instrument: Reference from P1 project on the best approach and methods to be applied in P28B (e.g. SPD requirement, type of the ON/OFF valve, material for cable tray bolt & nuts, MAC, etc.) | 1. Lessons learnt from P1. | 1. Improve the quality. 2. Avoid potential delay. 3. Have more control on schedule. 4. Full compliance to project spec. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6176 | BEST PRACTICE: Interactive Planning Session | 1. To align All Disciplines and Client on Overall Project Planning throughout EPCC timeline | 1. Unforeseen in-between activities (delay in Review / Analysis/ Vendor Data/etc) may offset overall baseline planning |  | 16193 - Action Taken: Organizing workshops / schedule meeting / update: i) with Engineering disciplines, ii) with Client | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Project Management | 6247 | Best Practice: LEAN PMT Structure | 1. Proprietary standard plant design. 2. Pre-design review conducted before award (value engineering). | 1. No schedule delay. 2. No cost impact. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Document Management | 6320 | Best Practice: Letter: Good recording and follow up | 1. Pro-active DC, follow up to ensure there is no back up between OWNER - Contractor | 1. Less back log |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Procurement | 6233 | Best Practice: Long lead items delivered 2 months ahead | 1. Good and proper planning. 2. Existing framework agreement between EPCC and vendors. | 1. Ahead of schedule for LLI. |  | 16347 - Action Taken: Sent Owner reps to check and expedite the progress. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5760 | Best Practice: MAC execution was as planned both at integrator level i.e. SD-4 and Petchem UPT level, with Petchem EPCC Contractors. |  | 1. Scope demarcation is identified thoroughly with no scope misalignment, with specialized group identified to manage MAC interfacing and overall execution. |  | 15356 - Action Taken: Engineering identified specialized personnel for MAC overall deliverables, led by I&C PTA causing smooth execution of MAC contracts. 15357 - Recommendation: MAC implementation could be extended for future projects extending beyond RAPID complex i.e. Interconnecting PICs. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6334 | Best Practice: Mechanical Rotating: Optimize pump type from BB5 to BB2 four number of pumps | 1. More accurate and stable (as per advised by vendor). | 1. Less cost. 2. Less fabrication schedule. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6335 | Best Practice: Mechanical Rotating: Speed up the approval for deviation of project spec based on P1 pre-approved technical documents | 1. Lessons learnt from P1 project. 2. Using same spec from P1. | 1. Minimize the decision making. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5826 | Best Practice: Minimize Reinforced Concrete Structures – Schedule has been improved. |  | 1. There are 6 nos. RC(Reinforced Concrete) structures in FEED 2. RC structures needed long-term erection period compare to steel structures even though it have cost benefit. 3. RC structures reduced 4 nos. from 6. 4. In accordance with circumstances the material of structure to be selected |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5685 | Best Practice: Minimum elevation of Heat Exchanger installation | 1. In the FEED P&ID, minimum elevation of heat exchanger is specified 1m from condensate line to secure static pressure of steam condensate. But some case of heat exchanger is not matched with requirement. | 1. Clarified with hydraulic calculation that there is no problem even though elevation is lower than 1m and received the confirmation from licensor. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Procurement | 6229 | Best Practice: Modular package strategy | 1. Standard plant design. 2. Recognized vendor / fabricator. | 1. Secure procurement / delivery duration. 2. Less quality issue during construction. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5823 | Best Practice: Modular type cable tray support in cable cellar room |  | 1. To reduce installation time without welding increase productivity |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Engineering | 6241 | Best practice: No major design changes after detailed engineering | 1. Proprietary standard plant design. 2. Pre-design review conducted before award (value engineering). 3. EPCC is part of JVco partner. | 1. No schedule delay. 2. No cost impact. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5551 | Best Practice: Obtained approval from DOSH for Load Test for Tower Crane upon joint inspection. | 1. Load Test for Tower Crane for main pipe rack was approved upon inspection by DOSH. | 1. Internal audit has been performed to ensure all DOSH requirements are met before the inspection. 2. DOSH approval was obtained immediately. |  | 14763 - Action Taken: Effective coordination was done to ensure smooth progress with DOSH. 14764 - Recommendation: Early engagement with local authorities. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5787 | Best Practice: Only contractor was implementing a numbered E-mail system. | 1. Not clearly defined in the project correspondent procedure. | 1. Sometimes important information is required to be shared with Contractor but might be not relevant to be routed via official letter. |  | 15424 - Action Taken: Devised a numbered email system which is screened by PM/EM/PE before issuance and this enables effective sharing of information and directions with Contractor and at the same time improving record keeping / logging of important email 15425 - Recommendation: To introduce Numbered E-mail systems clearly in project procedure and implement from start of the project. 15426 - Recommendation: Numbered Emails must be issued systematically with proper screening and control. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5696 | Best Practice: Optimization / Standardization of U/G foundation depth. | 1. For the mitigation of rainy season, tried to optimize / standard U/G foundation depth. | 1. It can be minimize to decline productivity of U/G excavation work. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5759 | Best Practice: Owner discipline engineers are recruited to involve in IPMT setup for EPCC execution covering multiple disciplines. |  | 1. Project lesson learnt and Group direction or initiative is captured during EPCC execution. |  | 15354 - Action Taken: Owner discipline engineers are heavily involved throughout all project phases i.e. Engineering, Procurement, Construction and Commissioning activities. 15355 - Recommendation: Owner discipline engineers hired to be screened with prioritization for personnel with extensive EPCC project management experience. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6343 | Best Practice: Piping: Enhanced / improved pipe support design followed project requirement | 1. Lessons learnt from P1. | 1. Eliminated piping issue during construction phase. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6347 | Best Practice: Piping: Pre-model review among PMT and CMI for 60% and 90% |  | 1. Reduce the finding during official review. 2. Expediate engineering schedule. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6346 | Best Practice: Piping: Pre-review documents / engineering deliverables before issued officially |  | 1. Shorter review cycle for documents approval. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6342 | Best Practice: Piping: Ride on P1 PDR & TEQ | 1. Lessons learnt from P1. | 1. Can expediate engineering schedule. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6345 | Best Practice: Piping: SIMOP and Interface meeting managed to identify construction constraint earlier. | 1. Identified during constructibility study. | 1. Avoid construction constraint. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5836 | Best Practice: PKG Document management for Loop Folder |  | 1. Loop folder shall be made for Loop Test. PKG Documents are missing from time to time. Document management is necessary by reflecting them in VPIS at the beginning stage of project to prevent. 2. Document missing during loop test. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6328 | Best practice: Process Safety: Engineering study conducted concurrently (e.g. ELSOR & RCM, etc.) | 1. To achive the target schedule of engineering completion by end of July 2018. | 1. Reduce the duration. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6327 | Best Practice: Process: Issued P&ID IFC ahead of schedule | 1. Re-draw vendor P&ID upfront prior receiving final version | 1. Ahead of schedule by 1 month. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5663 | Best Practice: Project schedule with enough float to manage / minimize risks during construction phase. | 1. CONTRACTOR prepared Target schedule with 1.2 month float which enabled contractor early commencement of site works. | 1. Early commencement of site works i.e. piping, civil & structure & etc. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5835 | Best Practice: Reducing quantity of Cable/Tray/MCT/Gland by application of Wireless Transmitters for non-critical monitoring loop. |  | 1. As per RAPID-FE1-TPX-INC-DES-0001-0006, para.9.14 Wireless Instruments, “Wireless field instruments should be used for non-critical monitoring loops only, subject to Licensor approval, where applicable. This shall be based on wireless HART technology. Wireless HART shall support both star and Mesh topologies.” 2. Non critical monitoring loop are defined as below: 3. Loops which are not used as pre-alarm to an ESD. 4. Loops which are not used as key indication for process operation. 5. Loops which do not require an update better than 8 Seconds. 6. Loops which are not used for computation in DCS (flow compensation, etc.) or other systems (OMS, BCS, APC, Mass balance calculations, etc.) |  | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5749 | Best Practice: Requirement of corrosion coupon and probe. |  | 1. CDBM review by 3rd party has been conducted earlier resulting additional corrosion coupon and probe captured at early stage. 2. No rework on isometric. |  | 15330 - Recommendation: CDBM has to be established at early stage i.e. before 60% 3D model review. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5813 | Best Practice: Separate Chilled Water Tank (3220-T-601/602) |  | 1. ITB requirement (3220-T-601); - Divide two compartments for chilled water tank #1,#2 by separation baffle. - Dividing wall shall be insulated to minimize heat transfer between the two compartments. (Compartment#1 : O/T 15°C, Compartment#2 : O/T 25°C) 2. Current design - Separate two tanks of 3220-T-601 and 3220-T-602 3. The reason to change - Tank size cannot be fixed before verifying insulation material, thickness, heat transfer value. It could result in delayed P/O and plot plan. - Insulation with separation baffle is not proper design under the construction point of view. Additional support structure should be attached on separation baffle to hold liquid loading and proper concrete foundation under the baffle is required. |  | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5825 | Best Practice: Sequential erection on Main Pipe rack |  | 1. Pipe rack has been spliced vertically into 2 part lower and upper. And each structure is handled as one structure. 2. SC executed 8 segments by dividing horizontally & vertically. 3. It’s helpful to manage sequential fabrication and erection. 4. Enable early work front for piping work. 5. Early start the design and easy follow-up |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5697 | Best Practice: Simplified concept of pipe rack to improve constructability. | 1. Standardized bottom elevation of foundation to improve efficiency of U/G construction. 2. Minimize the type of foundation 3. Minimize the size of steel to prevent to procure small amount and to provide flexibility for design change. | 1. Improved constructability of U/G foundation, steel fabrication and erection. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Award/Contract | 5802 | Best Practice: Site Security Contract to be awarded in time for TCF operation. |  | 1. Smoother the project execution. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5793 | Best Practice: Site Temporary facilities. |  | 1. Smoother the project execution. |  | 15440 - Recommendation: Start as early as possible in the schedule. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5820 | Best Practice: Soil Dry-Density Below Foundation |  | 1. Shallow Foundation 2. 95% Compaction Generally Applied (Normal Practice) 3. 95% Compaction for Cohesive Soil under Rainy Condition is Very Hard to Achieve 4. Soil Replacement (Form natural Soil to Crushed Stone) will be Applied for Soil below Shallow FDN in Some Area |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6336 | Best Practice: Static: Pre-checking vendor calculation for fiber elongation of the cold forming part (e.g. Vessel head). | 1. Lessons learnt from P1 project. 2. Checking done before fabrication. | 1. No rework. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Award/Contract | 5798 | Best Practice: Summarize (Obligations) contract deliverable for Owner and Contractor and completion dates as per the Condition of contract. |  | 1. Smoother the project execution. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5637 | Best Practice: Technical Assurance Audit instituted for RAPID project. |  | 1. Value added to the quality of project deliverables. |  | 14963 - Recommendation: To continue to implement technical audit by SMEs with relevant experience. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Award/Contract | 6253 | Best Practice: Thorough check (by line item) on the contract clause / requirement by iPMT | 1. Project Manager has direct access to EPCC. | 1. No major issue on contract. 2. No additional cost. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5838 | Best Practice: Transportation Steel skid for Steel Structure |  | 1. Easy stuffing & unloading to / from container by using Transportation steel skid for Steel-Structure. |  | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5681 | Best Practice: Transportation Steel skid for Steel Structure. |  | 1. Easy stuffing & unloading to / from container by using Transportation steel skid for Steel-Structure. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5824 | Best Practice: Use corrugated conduit(ELP) in paved area |  | 1. Use the Corrugated conduit (ELP) instead of PVC rigid conduit for achieve constructability in paved area. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5827 | Best Practice: Use Pin brazing(X-BT) at steel structure |  | 1. Use the pin brazing material for earthing plate instead of welding at steel structure in order to secure constructability without welding. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5822 | Best Practice: Using ball bearing support – replacement for spring support of heavy equipment |  | 1. Primary product cooler (3220-E-102) has huge horizontal displacement. (Approx. 60mm) 2. CONTRACTOR solved this by spring hanger support but CLIENT concerned about using spring support for heavy equipment. 3. Equipment reactions shall be calculated considering the piping’s thermal expansion, other external forces acting on the piping (weight, friction, wind, etc.) and the movement to which the piping is subjected by connected equipment. The effect of friction is based on the friction factor i) Steel to steel: 0.3 ii) stainless steel to PTFE: 0.1 iii) Ball bearing support: 0.01 4. CONTRACTOR using multi ball bearing support which is movable in any direction ±75mm |  | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5778 | BEST PRACTICE: Value engineering even at EPC late stage. | 1. Develop a consolidated tracking list, maintained by both EPC and PMT. | 1. Effective monitoring of value engineering items. |  | 15398 - Recommendation: Much more effort should have been applied to FEED stage VEP in collaboration with Operations Team and Licensor. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5794 | Best Practice: Workers accommodation. |  | 1. Smoother the project execution. |  | 15441 - Recommendation: Consider using prefab modular building system which was very successful. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Project Management | 6356 | Best Practice: Strong support, commitment and collaboration from EPCC and PMT | 1. PETRONAS cultural belief | 1. Smooth project progress. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5761 | Bidder noncompliance to bidding document format as given by OWNER. | 1. BIDDER is using their own format in preparing certain key information even though ITB format has been clearly provided. | 1. Difficulty in assessing or comparing same information between BIDDER’s proposal. |  | 15358 - Recommendation: Emphasis on the importance of compliance to ITB prescribed formats and potential disqualification upon noncompliance. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5754 | Blast resilient requirement for analyser house. | 1. The blast resilient requirement is not specified in Project Specification, hence, deemed not required. | 1. Late engineering design freeze for analyzer package. 2. Late PO award and equipment delivery. |  | 15342 - Action Taken: Deviation approval is obtained from Core Engineering with involvement from GTA. 15343 - Action Taken: EPCC Contractor applied for deviation considering non-occupancy (limited hours per day) of the analyzer house building. 15344 - Recommendation: Requirement for blast resilient for analyzer house shall be established in FEED specification (if required). | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5816 | Blast Wall requirement for oxygen mixing nozzle | 1. Requirement for blast wall of oxygen mixing nozzle is specified in ITB but detail design basis (size, wall thickness, clearance) not defined in detail. 2. A few inquiries have been asked for LICENSOR’s clarification several times, but no clear information has not provided. 3. Licensor’s comments during 60% review were received and implemented to the Plot Plan and submitted to Client. 4. Design changed again as per new comments (change of entrance) | 1. Uncertain requirement for blast wall of oxygen mixing nozzle. 2. Clients of each discipline have different understanding about blast wall concept and purpose. |  | 15481 - Action Taken: Civil engineering has submitted construction drawings of it, and design modifications are unavoidable. 15482 - Recommendation: Preventive Action. 15483 - Recommendation: Specific requirement shall be described in ITB for blast wall design. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5829 | BOMBA Requirement | 1. Expect rework on panel location and cabling for FACP during final stage due to BOMBA comments. | 1. Pre-Consideration in drawing as refer to previous project L&L and communication with BOMBA earlier. |  | 15489 - Action Taken: FACP was located at outside entrance of building. Isolator switch for power will be install nearby door. 15490 - Recommendation: Preventive Action. Need to change drawing | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5440 | Bullet thickness - Minimum 17.5 bar as per Malaysian Std. MS 830. | 1. Due to cost saving initiative, it was agreed to reduced bullet design pressure from 19 bar to 16.5 bar (due to cost saving). This will reduce bullet thickness, which will eventually return the saving to OWNER. However, it was later noticed that under MS 830, the minimum design pressure for LPG bullets shall be 17.5 bar | 1. Will be recorded as Change Proposal since the vendor procure the materials. 2. Wasting of time & cost since there is a lot of meeting & discussion to be held. |  | 14542 - Recommendation: Design engineer shall be made aware of MS 830. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5106 | Bus duct layout clash with the beam of transformer room that it may affect the progress of the site installation. | 1. The manufacturer bus duct layout and the modified bus duct routing not be updated to 3D model at once. | 1. The installation schedule will be impacted by rectification work. 2. Fourteen lines out of all eighteen lines are affected. |  | 14206 - Recommendation: The plan and profile/elevation drawings issued by Civil shall be used as information to Vendor rather than redrawn by EE vice versa to avoid misleading. 14207 - Recommendation: Internal communication between VDR and 3D layout engineers must be well coordinated and implemented. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6025 | Cable pulled to have been labelled properly with the correct cable tags. | 1. Due to that, wrong termination of cables in the wrong junction boxes occurred. | 1. Cable pulled wasn’t labeled properly with the correct cable tags. |  | 15888 - Action Taken: The cables had to be tracked back by performing continuity test for tracing 15889 - Recommendation: The cables has to be labeled accordingly while pulling is ongoing. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5833 | Cable tray support within 3m for bending points | 1. Cable tray support for tray bending points is not sufficient. | 1. Tray support considered within 1m from joint point between fitting and straight cable tray. |  | 15506 - Action Taken: Install the additional support within 3m for tray bending points. 15507 - Recommendation: Preventive Action. Installation method for tray bending points to be checked during 3D modeling. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5255 | Cable tray supports clash with electrical cable tray. | 1. No coordination between electrical and instrument team | 1. Relocate electrical cable tray to other location. Remove and reinstall supports. |  | 14355 - Action Taken: To have Instrument and electrical coordination before start of cable tray in new area | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Quality | 6060 | Cable trench leaking at compressor house. | 1. Poor workmanship. | 1. Water seep through concrete and could damage cables and other equipment. |  | 15640 - Action Taken: Rework / Repair. 15641 - Action Taken: Seal leaking area. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | HSSE | 5646 | CBMI (Subcon for civil work) violated and breached Legal and PTS requirement with regards to the Scaffolder Competency. | 1. CBMI reluctant to comply with Legal and PTS requirement as they think their China Competent Scaffolder can do better than Local Malaysian Competent Scaffolder. 2. CONTRACTOR Site Management did not take a concrete action to mitigate the MAJOR Noncompliance although the SC PM already give an instruction for them to resolve the issue due to budget constrain. 3. Technical skill for CBMI Chinese Scaffolder (with China origin Competency Certificate) is arguable due to a lot of Nonconformance report issued by PRPC Scaffolding Specialist to their scaffolding design specification as well as P6a HSE Walkabout findings. 4. As a recovery measure, Scaffolding Inspector (L3) to take proactive action by conducting discussion with the Scaffolding Supervisor (L2) and come out with sketching plan prior the erection work conducted by Scaffolder (L1) and PTW approval. | 1. Non-compliance to various Scaffolding requirements, increased the risk of Working at Height and scaffolding work. |  | 14989 - Action Taken: Highlight the issue: i. CONTRACTOR HSE Committee ii. UPT P6A HSE Committee iii. Site Weekly Progress Meeting. iv. PMT VC Weekly Meeting. v. SD3 Weekly VC Meeting (KL-Seoul-Pengerang). 14990 - Action Taken: Stop Work Order for scaffolding activity as an operational control until both CBMI & CONTRACTOR resolve the issue and followed with consequence management if they still failed to comply within timeframe given. 14991 - Recommendation: iPMT to ensure the CONTRACTOR selection of main contractor is subject to the standard requirement stipulated in ITB. 14992 - Recommendation: CONTRACTOR to take a necessary consequence management and ZeRo Tolerance to the major HSE violation among their subcon. 14993 - Recommendation: Recommend CONTRACTOR / CBMI to hire Local Competent Scaffolder as per ratio and concurrently sending the China competent scaffolder to DOSH approved Basic Scaffolder training and undergo RAPID VOC to be accepted as erector inside RAPID. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Procurement | 5918 | Cement lined mild steel pipe shall be free from rust | 1. Poor quality of mild steel pipe delivered by the supplier | 1. Rust appear below painted surface |  | 15682 - Action Taken: The pipes has been blasted & repainted 15683 - Recommendation: Proper material inspection at factory prior to delivery 15684 - Recommendation: Factory inspection | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5614 | Certain pipes are not delivered with pipe caps. | 1. Pipes are covered with a cut canvass and tape around pipe both ends. | 1. Strong wind at site torn the cut canvas covering pipe both ends and pipe interior exposed to dust and water. |  | 14910 - Action Taken: Advise CONTRACTOR to provide suitable pipe caps according to its size. 14911 - Recommendation: Packaging Method should be clarified clearly that pipe mills must provide pipe caps and ensuring that pipes are already covered with pipe caps prior shipment. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Project Management | 5515 | Challenges in coordination/communication between PMT and Contractor | 1. Different time-zone between PMT office and contractor office (8-9 Hours) 2. Language barrier 3. Cultural differences | 1. Poor quality of some project deliverables due to lack of communication 2. Late submission of some project documents |  | 14667 - Recommendation: To appoint intermediateor | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5781 | Change control across interfaces. | 1. The Interface Management Tool (IMT) does not have a function for scope changes / adjustments. 2. No formal communication system available to formalize design developments and changes that have interdirectorate impact (e.g) with SD4 | 1. In a few instances there are scope gaps at the interface with utilities and off-plots package. There is an interface management system, but it ignores the need to scope adjustment in some instances. 2. Lack of such communication systems / mode of communication resulted in implementation of several issues being delayed because UPTs from each SD could not proceed without formal notification at the management level. |  | 15404 - Action Taken: Worked closely with SD3 and SD4 Interface Management and Engineering departments to devise a procedure to issue inter-directorate Memos to formalize interface related design developments / changes. 15405 - Recommendation: The Interface Management Tool (IMT) should include a feature that enables users to flag and manage IFQs that result in scope changes / adjustments. 15406 - Recommendation: Introduce and specify such modes of inter-directorate communication systems at the beginning of the project, especially for large complex developments like RAPID. 15407 - Recommendation: Linkup to PDDM system for inter UPT review and comment of critical interface documents. 15408 - Recommendation: For future, consider using digital memo system as propagated by PETRONAS management. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5688 | Change explosion protection area for K-660A/B | 1. Regarding PCS Powder Conveying Compressor, Electrical Area Classification has been changed. | 1. The type of compressor motor has been change from Ex/n to Ex/d and it will lead to delay equipment delay. To minimize impact, adjusted installation / construction sequence. |  | 15085 - Action Taken: Design studies has to proceed as soon as possible to minimize design change regardless contractual schedule. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Precommissioning/Commissioning | 5669 | Change in Operator Shelter Building (OSB) design. | 1. Operator Shelter Building (OSB) increased in total number of occupancy in results to design changes. 2. The request of OSB design change was evaluated and take in consideration of the additional number of the occupancy. 3. Late request from OWNER in regards to increase of the additional occupancy in OSB. | 1. Design change will lead to change order. |  | 15060 - Action Taken: The proposal was acceptable by management with some minor deviation changes without cost and schedule impacts. 15061 - Action Taken: The proposal was presented to TRC and endorsed and approved in time. 15062 - Action Taken: The proposal was shared and confirm from all stake holders. 15063 - Recommendation: The request or proposal shall be finalized before ITB issuance or during FEED. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5625 | Change Notice Submission without strong basis. | 1. CONTRACTOR continue Change Notice unnecessarily. | 1. CONTRACTORs position to pursue due to pressure from mgmt. |  | 14934 - Action Taken: On-going discussion between OWNER and CONTRACTOR. 14935 - Recommendation: Discuss with OWNER before issuance of Change Notice. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5244 | Change of lifting plan at very last minute due to site condition | 1. Resources i.e. crane, spreader bar, or wire sling arrangement change last minute due to unavailability of resources | 1. Lifting of equipment deferred due to stop work on safety issue. |  | 14337 - Action Taken: Confirm crane and lifting jigs and in good condition and sufficient at least one day to lifting | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5197 | Change order workflow: Confusion whether to process with changes prior to any COC sitting, even if the changes are technically required. | 1. Magnitude of cost impacts which can vary depending on changes. | 1. Leads to late decision making. 2. Impact on design to other UPTs due to change deviation (interface). |  | 14249 - Respective Project Mgmt. Team at EPCC office to be given certain authority (LOA) to immediately decide within certain guideline without the need to go through Core Team depending on the rating of the risks. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5682 | Change the quantity of detector for OSB | 1. In the ITB requirement, H2 detector has to provide in the mini lab. Since there is no equipment to make H2, SC tried to delete H2 detector in mini lab. 2. But OWNER stretched the meaning of detector, OWNER requested to SC to provide H2 and EO detector for OSB. | 1. The quantity of detector is changed from 1 to 12. SC issued change notice and OWNER confirmed. |  | 15080 - Action Taken: If change has been occurred, have to analyze impacts for the change and share / discuss with OWNER. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2081 | Changes in drawings/ details due to interface with other packages. | - No proper coordination with other packages (fiber optic, SAJ, TM and TNB) | - Delay in completion of certain aspect of work/ construction. - Additional detail such as ductbank installation and slab protection for utilities. | - Proper coordination/ planning between all relevant parties to capture all details prior execution of work. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2072 | Changes in Final Doc procedure(QA/QC) | -Introduction of new department for turnover process which required new final doc procedure | -Delay in submission of project final documentation -Delay of Provisional Acceptance/ Final Acceptance issuance by owner | -PMC has guided and provided Finalized Master Index to Package Contractor -Setup dedicated team to expedite document submission - For future project, minimum procedure amendment shall be allowed during the project implementation. Sytematically periodically review for procedure shall be introduce to reduce interruption/ redo work. - PMC/ turnover dept. will need to standardize for all packages, the final documentation format inclusive number of hardcopy/ softcopy to be submitted by package contractor. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Project Management | 5411 | Changes of PEPI key personnel e.g. Engineering Manager, Project Director. | 1. Due to PEPI internal arrangement. | 1. Disruption to the project momentum and requirement of learning curve. |  | 14474 - Action Taken: Closed communication to bring up the Engineering Manager up to speed. 14475 - Action Taken: To get experienced Project Director. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Document Management | 5420 | Channel of communication from directorate (HSSE, Core Engineering, Quality, and Site Management) to Contractor. | 1. Some memo / Job bulletin / etc. sent directly to Contractor or some are missed out to be sent to Contractor. Sometime PMC also not aware of the memo / Job bulletin / etc. Example: - FSDP issued to Contractor without notification to UPT. - Job Bulletin RAPID-P0024-PMC-ENG-JB-0001-0005 (Performance Standards - Review and Validation by Engineering) was released, but not received by Contractor / UPT. | 1. Misunderstanding on the issue. 2. Delay execution of any required action. |  | 14499 - Action Taken: Need to issue list of PDR / Job Bulletin / Memo which are issued to Contractors for tracking. So that everybody aware what is missing. 14500 - Recommendation: To improve communication by compliance to RAPID PMT communication procedure. 14501 - Recommendation: To give access of P-EDMS to construction and site management directorate. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5961 | Check sheet C functional test should be carried out according to commissioning workflow | 1. Late issuance of Request for Inspection (RFI) by contractor which may cause error in verifying closure of Check Sheet A, B and Punch list A, and difficulty to engage Operation to witness functional test. | 1. Incompliance of commissioning pre-requisite in the workflow prior to conducting functional test condition |  | 15785 - Action Taken: Workflow revised for better clarity 15786 - Action Taken: Assigned focal person for each discipline for smooth implementation of functional test 15787 - Recommendation: Commissioning workflow can be standardized and specified in ITB for future projects | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5772 | Chilled water debacle. | 1. Scope definition in FEED not certain. | 1. A lot effort and resources to change the design to reincorporate the Chilled Water system. |  | 15386 - Action Taken: Having Chilled Water system as an OWNERs Option in case the need for it arose. 15387 - Recommendation: To conduct adequate feasibility studies and incorporate such essential scope at FEED stage. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5971 | Chlorine emergency kit not in initial spare list and the emergency procedure not been trained to RWTP personnel | 1. Chlorine emergency kit and procedure not available | 1. Might be fatality due to insufficient training |  | 15801 - Action Taken: Sent RWTP personnel for training 2) Buy chlorine emergency kit | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5627 | CIDB - COA imposed new requirement. | 1. CIDB have lift the waiver given to PETRONAS earlier. 2. Full enforcement by CIDB / COA once waiver have been revoked. | 1. Potential schedule and cost impact by CONTRACTOR. |  | 14942 - Action Taken: Frequent meeting with CIDB, CONTRACTOR and OWNER. 14943 - Recommendation: CONTRACTOR to comply to any new impose of regulation requirement by regulatory. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Procurement | 5900 | CIDB MANAGEMENT IMPROVEMENT: The work flow of COA application and related documents preparation is not going very well. |  |  |  | 15198 - Applied Solution: Assign a specific position to check these documents at each stage and monitor the whole application status. 15199 - Suggestion for Improvement: Its recommended to pay high attention to the preparation of documents applied for COA (including TPIB) and assign a specific position to check these documents at each stage. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Procurement | 5408 | CIDB requirement for COA. | 1. CIDB requirement came late after award of contract. 2. Waiver was withdrawn and OWNER agree to comply. 3. EPCC was not clear on the new requirements. | 1. Delay in delivery of construction material. 2. Schedule and cost impact to EPCC. |  | 14464 - Action Taken: Various workshop by PRPC permitting team. 14465 - Action Taken: Engagement between CIDB and EPCC on the new requirements. 14466 - Recommendation: For this value of project, we should ask for a blanket waiver. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5562 | Civil Structural: Best Practice: Proper documentation of completed piling installation and pile test records. |  | 1. Piling records, Material Approval Request, Method Statement, ITP, Pile Test Report, Pile layout and detail drawings are properly recorded. During inspection few piles were selected. |  | 14789 - Recommendation: To ensure all documents to be approved by authorized personnel before the test pile activities. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5560 | Civil Structural: CONTRACTOR was not apply the Non shrink concrete for pile in tension. | 1. The requirement was not mentioned in the ITB. | 1. Late decision from engineering team might impact the piling works progress at site. |  | 14784 - Action Taken: Organized teleconference with all parties to finalize and conclude the issue. 14785 - Action Taken: Lengthy discussion take places to finalize the application of non-shrink concrete for pile in tension as the Central Engineering and PTA has different view / opinion. 14786 - Recommendation: To spell out technical requirement in the ITB. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5558 | Civil Structural: Criteria for structural deflection was not complied as per stipulated in Civil Design Basis. | 1. CONTRACTOR did not followed structural deflection limit and was inconsistent with Civil Design Basis and did not specify the reference of the recommended limit. | 1. Potential rework. 2. Potential issue on quality. |  | 14778 - Action Taken: Commented on the structure deflection limit and asked CONTRACTOR to follow the requirement in Civil Design Basis / PTS. 14779 - Recommendation: UPT to check on Civil Design Basis / PTS before commenting. 14780 - Recommendation: Criteria for structural deflection shall be complied as per stipulated in Civil Design Basis. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5557 | Civil Structural: Down drag load was not included in pile foundation design for pile penetration in loose fill material and soft compressible soil. | 1. The requirement was not mentioned in the ITB. 2. Down drag force was not included in pile foundation design. | 1. CONTRACTOR didn’t consider down drag effect in pile capacity calculation. 2. Potential change order. |  | 14775 - Action Taken: Resolution with the CONTRACTOR on technical requirement for pile foundation considering down drag load. 14776 - Recommendation: To spell out technical requirement in Design basis. 14777 - Recommendation: Down drag load shall be included in pile foundation design for pile penetration in loose fill material and soft compressible soil. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5559 | Civil Structural: Low quality deliverables with errors on critical design parameter i.e. application of loading data to structural is expected by the OWNER. | 1. Inadequate checking and data verification by CONTRACTOR before submission for OWNERs review. | 1. Structure and foundation (i.e. STR 1006/V-909) was returned with code 2 (returned with comments) as the comment has not been incorporated and could not be issued for Construction, hence, consuming more review cycle. 2. Too many revisions of deliverables due to inadequate checking and data verification by CONTRACTOR before submission for OWNERs review. |  | 14781 - Action Taken: Informed CONTRACTOR through Engineering Manager to properly go through the deliverables before submitting in PEDMS. 14782 - Recommendation: CONTRACTOR to produce high quality design document as per project expectation. 14783 - Recommendation: CONTRACTOR Lead Engineer to play their role by check in details their document before submitting for clients check. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5555 | Civil Structural: Pile head for tension pile was not designed to resist tension force. | 1. Unclear requirement in Project Specification and PTS for pile head treatment for tension spun pile. | 1. Dispute views on pile head treatment for tension pile between OWNER and CONTRACTOR. |  | 14771 - Action Taken: Highlighted to core engineering team for CONTRACTOR to design adequate adhesion resistance of pile cap and spun pile to tension force accordingly. 14772 - Recommendation: To spell out technical requirement for tension pile clearly in PTS / Project spec / FEED basis. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5561 | Civil Structural: Specific FDT / Compaction test requirement for backfilling work of Reinforced Concrete foundation area was not applied by CONTRACTOR. | 1. There is no specific requirement for backfilling work of RC foundation / trenching stipulated in Design Basis whereby the stipulated requirement is appropriate for general site preparation or road work construction. | 1. Inadequate numbers of FDT / compaction test to validate the 95% MDD for compacted backfill material. |  | 14787 - Action Taken: Discussed with CONTRACTOR to provide adequate FDT / Compaction test and mark up the location in Excavation Layout. 14788 - Recommendation: To include specific clause in ITB related documents for specific backfill material for foundation work and pipe trenching in order to ensure adequate numbers of test to be carried out. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5564 | Civil Structural: Structure-Steel was not packed in single batch delivery as per area by area in complete quantity and not mixed with others. | 1. Structure-steel vendor working in tonnage milestone and not putting effort to work / complete area-by-area as required by site readiness. | 1. Some of received structure-steel material cant be installed due to insufficient / incomplete set as steel members. |  | 14792 - Action Taken: Requested CONTRACTOR to inform vendor to work and priorities according to the site demand. 14793 - Recommendation: To ensure milestone being made for this fabrication area-by-area and all list of steel members to deliver is being checked as per agreed list. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5556 | Civil Structural: The weir crest level was not designed as 107.10 during detail design. | 1. Incomplete information received by CONTRACTOR from PDR 005 issued by CORE team as attachment with regards to weir crest level is missing during transmittal. | 1. CONTRACTOR designed the weir crest level below 107.10 which could cause backflow from OUI drainage system. |  | 14773 - Action Taken: Face to face meeting between CONTRACTORC and OUI subject matter expert in engineering office to find the resolution. 14774 - Recommendation: Proper checking on the receiving transmittal document. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5563 | Civil Structural: Underground services was not reflected in foundation layout. | 1. Underground service layout is not in deliverable list. | 1. Construction team doesn’t have underground service layout drawing for inspection purpose. |  | 14790 - Action Taken: Requested underground service layout from CONTRACTOR. 14791 - Recommendation: To include underground service layout in the Master Deliverables Register (MDR). | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5010 | Civil: Damage of pile top level | 1. Aggressive excavator movement damaged top of pile during excavation activity. | 1. Pile top were damaged during excavation. Pile top level had to be reduced resulting in reduced level for bottom of foundation. |  | 13955 - Excavation works to be accompanied by a watcher to look out for any potential damage to pile during excavation | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5007 | Civil: Honeycombing of concrete column | 1. Segregation of concrete due to high drop elevation combined with congestion due to rebar. 2. Insufficient length of concrete poker, where bottom of cast was not reachable. | 1. Honeycomb of concrete columns leading to repair and rework of concrete column 2. Impact on schedule |  | 13949 - Retraining of supervisors 13950 - Pre-concrete inspection check of job tools and readiness. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5008 | Civil: Insufficient support for concrete formwork. | 1. Wooden support formwork for concrete were anchored to soft soil. Anchoring length was also small. | 1. Movement of formwork during concrete pour resulting in geometrical distortion of casted foundation |  | 13951 - On soft clay soil, to utilized improved formwork anchoring method. (i.e., improvise to use scaffold tubular to achieve deeper anchoring into soil and stiffer formwork support.) | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5711 | Civil: Late changes of ACC network engineering. | 1. Central Engineering informed changes in ACC basin weir crest Level for overall RAPID packages. However the attachment appended together with the MEMO was sent later and was not received by CONTRACTOR. 2. Missing information in project memorandum with regards to ACC network design which was provided later. | 1. Rework on Hydraulic calculation of ACC network. |  | 15232 - Action Taken: Series of VC took place but ultimately a Face to Face meeting between EPCC-CoreEng-OUIJV was conducted. A resolution was achieved through give and take. On P11 account, few changes in internal ACC network size to accommodate the change. 15233 - Recommendation: Originator or central engineering to follow up on high impact changes issued through JB or MEMO. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5006 | Civil: Paving settlement | 1. Sequence of construction where paving was done prior to completion of deep pipe trench. 2. Overloading of paving due to crane movement | 1. Paving settled beyond allowable tolerance leading to rework of paving. |  | 13947 - Internal coordination to prioritize works. 13948 - Steel mats to be required for any heavy crane movement above paving. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5009 | Civil: Settlement of pump foundations | 1. Sequence of works where nearby pipe support foundation excavation was undertaken after pump was positioned. | 1. Soil erosion below pump foundation leading to settlement. |  | 13952 - Action Taken: Prioritize sequence of work especially near settlement sensitive foundations and equipment. 13953 - Recommendation: Pump foundation to be on pile for future. 13954 - Recommendation: Composite drawings to include duct bank, utilities and underground networks etc. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5005 | Civil: Soil erosion during excavation to expose duct bank | 1. Duct bank length specified in drawing does not concede 45 degree soil slope above the duct bank. | 1. Soil erosion below cables crossing above duct bank leading to hanging cables |  | 13946 - IDC and Constructability check for Duct bank and Cable Route (E&I and CVS) | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6178 | Client engagement on a working level to be kept in check | 1. Client interaction on a working level is extended as a professional courtesy. This may sometimes encourage client to encroach beyond their initial involvement, impacting overrun in engineering activities. | 1. Discipline engineer should be familiar with contractual scope of work as stipulated in project contract. Further iteration that may be considered additional should be avoided. |  | 16196 - Action Taken: PMT should ensure that Discipline Leads make their engineers familiar with the SOW & raise questions as required. Contractual presentation should be given to Leads & they should ensure that this is disseminated 16197 - Recommendation: Preliminary induction to be conducted 16198 - Recommendation: Engineers to understand SOW in the ITB | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Engineering | 5512 | Close integration of the PDP’s, together with the FEED package through Integrated Process System (IPS) | 1. Lack of communication between PRPC team, LICENSOR and FEED team 2. Redundancy and duplication of document review/comments toward different parties 3. Lack of integration between parties | 1. Engineering activities could be started during the curse of the PDP development. 2. Allowed full integration of PRPC, LICENSOR and FEED organization 3. Saving time in the overall schedule, as compared to the usual scheme of PDP first and Engineering disciplines afterwards. 4. Allowed PRPC to minimize the manpower required for document review/comment 5. Centeralize the source of review/coment and avoid duplication of the comments toward different parties 6. Close involvment of the LICENSOR, even after the PDP issue, to accompany the FEED activities. |  | 14661 - Action Taken: Established IPS at early stage of project initiation to expedite process 14662 - Action Taken: Ensure closed integration between OWNER (PRPC), FEED CONTRACTOR (TECHNIP), LICENSOR (AXENS PL) and INTEGRATOR (AXENS P²) via IPS project | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Engineering | 6284 | CMF: Design has to be changed due to suit the latest authorities requirement | 1. Late Change Input on building data at late stage of project. | 1. Work at site unable to proceed delay in works. |  | 16429 - Action Taken: Design coordination with the relevant authorities (CKAPS - agency under MOH) 16430 - Recommendation: To engage consultant that have prior CKAPS background and experience. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Procurement | 5118 | COA (common) |  |  |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5612 | COA application was not approved as per API 5L guidelines. | 1. Different interpretation by local authorities on the guideline. 2. Different understanding between region and headquarters CIDB office on guidelines interpretation. | 1. CIDB insisted that the marking of API monogram on API 5L pipes are required although the marking were supposed to be on voluntarily basis by the mills based on API 5L guidelines. |  | 14904 - Action Taken: Issue appeal letter to CIDB with explanation based on own understanding on API 5L guidelines. 14905 - Recommendation: To ensure that all procedures to be clearly understood and clarified with government authorities. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5715 | Coating Qualification Test: Qualification test for 3LPE coating. | 1. CONTRACTOR missed out the requirement to conduct 200-days thermal ageing test to qualify the coating material. End up additional 200-days delivery impact to the UG piping. | 1. To comply with project specification, additional 200-days thermal ageing test need to be performed. This will surely impact on overall project schedule. |  | 15242 - Action Taken: PDR was raised and was approved by PTA to use existing certificates by the similar coating manufacturer supplied to other RAPID package. 15243 - Recommendation: Even though this is a CONTRACTOR obligation to carefully read and understand each requirements of project specification, however some critical requirements which can impact overall project cost and schedule need to be highlighted | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5489 | Codification of Surveillance Report not available. | 1. Codification for Site Surveillance Report is not available. | 1. Document numbering system not established. |  | 14619 - Recommendation: To incorporate in future project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5490 | Codification of Technical Query not available. | 1. Codification for Site Technical Query is not available. | 1. Document numbering system not established. |  | 14620 - Action Taken: To separate between Technical Engineering Query (TEQ) and Site Technical Query. 14621 - Recommendation: To use FTQ for Field Technical Query. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5737 | Colour Coding: Lack of information of colour coding for roofing and wall cladding. | 1. PTS does not covered colour coding for all the items comprehensively. | 1. Steel shelter for one of the RAPID package using different colour for both metal roof and wall cladding. |  | 15298 - Action Taken: Project Memorandum is issued to standardize the colour coding which to be followed by all packages. 15299 - Recommendation: Relevant project specification shall be issued during ITB to cover the missing items from PTS. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5100 | Colour tone variation e.g. handrails, structural paintings, etc | 1. Different vendors awarded 2. Late involvement/intervention by PETRONAS Brand team | 1. Variation of colors 2. Quality issue 3. Rework |  | 14192 - Action Taken: Escalated the issue to RC engineering 14193 - Action Taken: Requested RC engineering to core engineering team for a official memo (exception for purchased items) 14194 - Recommendation: Sample to be provided to vendor 14195 - Recommendation: Stringent quality control for sub-contractors | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Procurement | 5120 | Colour tone variation e.g. handrails, structural paintings, etc | 1. Different vendors awarded | 1. Variation of colors 2. Quality issue 3. Rework |  | 14238 - Recommendation: Sample to be provided to vendor 14239 - Recommendation: Stringent quality control for sub-contractors | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5830 | Combination of UPS and Battery Room in FAR | 1. OWNER requested that UPS Room and Battery Room would be separate in FAR building. | 1. Change AC UPS battery type from vented type to VRLA (Valve Regulated Lead Acid) called maintenance free type through OWNER’s option 2. According to project specification, separate Battery Room is not required for VRLA type battery. 3. CONTRACTOR combined UPS Room and Battery Room in FAR. |  | 15491 - Action Taken: CONTRACTOR checked revision of design as per OWNER’s requirement. 15492 - Action Taken: The revision of design had some problems such as extension of FAR building. 15493 - Action Taken: OWNER and CONTRACTOR discussed this matter and OWNER accepted combination of UPS and Battery Room in FAR through TEQ. 15494 - Recommendation: Preventive Action. Need detail discussion with OWNER and CONTRACTOR | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5949 | Common understanding of project standard/specification to be used. | 1. Unclear understanding on whether PTS or water industry standards is to be used | 1. In early stages of the projects, Engineers were not aware of the requirement and insisted on all PTS must be followed. a) delays in approving deliverables. b) External teams were still insisted on referring to PTS whenever reviewing docs and auditing. |  | 15756 - Action Taken: PMC Management has approved concessions given to certain tasks. 15757 - Action Taken: Issued raised in monthly meeting and minute for actions and cascading to all the relevant engineers. 15758 - Recommendation: To clearly stated the requirement in the ITB and understood by all parties. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Project Management | 6051 | Communication plan. | 1. To ensure better communication amongst various partner; PETRONAS HQ, PETRONAS Site, PMC HQ, PMC site, KAP HQ, KAP site. | 1. Better communication. 2. Authority level of approval smoother project management. |  | 15623 - Action Taken: To continue and enhance; what, how, when and who. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | HSSE | 6058 | Community engagement. | 1. Create public awareness. | 1. Reputation of PETRONAS in CSR. |  | 15637 - Action Taken: Event to invite community and government officers. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | HSSE | 6004 | Competent Process Safety personnel with oil and gas project experience to be selected. | 1. Wrong selection of process safety engineer 2. Lack of knowledge/experience | 1. The engineering design work done are not up to oil and gas industrial standard. 2. Some safety workshops like ENVID n FSAR werent be conducted following proper procedures, hence causing rework 3. Contractor doesnt understand the requirements and procedure of closeout, causing a lot of comments and rework on close out actions 4. During safety workshop/ audit, contractor didnt properly defend their designs hence causing a lot of action items being raised during workshop. However, at the end of the day, contractor is unable to close those action items. This creates lots of unnecessary issues and effort to close these action items |  | 15847 - Action Taken: More efforts need to be made to confirm the work complied to oil and gas codes and standards 15848 - Recommendation: Process Safety with oil and gas project experience, shall be a factor of consideration during Technical Bid Evaluation. For the bidders with insufficient of oil and gas project experience, clarification shall be made | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Document Management | 5290 | Compilation of Final Documentation | 1. Contractor unable to finalize the compilation content and arrangement for final documentation | 1. Will affect whole Rapid. Different contractor different arrangement / format |  | 14410 - Action Taken: To have standardize procedure throughout Rapid for final documentation | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | HSSE | 6003 | Complete ITB documents shall be provided to Contractor during bidding stage. | 1. Incomplete ITB documents provided to LLWT as selective ITB documents only. | 1. This creates problems in standardization of design, as part of RAPID complex. |  | 15845 - Action Taken: Some of the project specific requirement were waived as they are not listed in the ITB documents. 15846 - Recommendation: Special project requirement must be highlighted to Contractor during bidding stage | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Precommissioning/Commissioning | 5672 | Completion review of Valve Critical Assessment (VCA) prior to 60% 3D Model Review. | 1. The VCA review was presented during 60% 3D Model review. | 1. Unable to identify and confirm the valve critical classification during the model review in results of disagreement the valve accessibility requirement. |  | 15068 - Action Taken: To remind CONTRACTOR to ensure all sessions required to be completed accordingly per schedule. 15069 - Action Taken: To carry out the VCA session for identifying the critical classification and incorporate into 60% 3D Model review. 15070 - Recommendation: Focal person shall identify the sessions which need to be conducted as per schedule. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5788 | Complex Change Order approval process. | 1. Intricate queries by Change Order Committee (COC) members. 2. Involvement of new parties in the process (e.g. PD&T Cost Estimators). | 1. Change Order Papers were recycled several times with the Change Order Committee (COC) because there were unexpected comments / queries by members which required the team to go back and make extra preparation after a sitting. 2. PD&T Cost Estimators are required to endorse the check estimate and can lead to opposing positions with the project team during the COC Sitting if not aligned beforehand. 3. These sort of setbacks delayed CO approval process significantly. |  | 15427 - Action Taken: Proactively engaged in the following discussions with stakeholders before actual COC Sittings to avoid repetitive sittings. 15428 - Recommendation: Hold pre-briefing sessions with COC Chairman to gauge expectations. 15429 - Recommendation: Review cost estimate basis and details with PD&T cost Estimators several weeks before COC Sitting to reach alignment and acceptable check estimate range. 15430 - Recommendation: Review Delegation of Authority to streamline process. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Construction | 6298 | Complex sequence of works | 1. Involve multi-disciplinary trades | 1. Rework. 2. Redesign 3. Schedule delay |  | 16460 - Action Taken: Design coordinator based at site. 16461 - Recommendation: To ensure design coordinator post present in the org chart from beginning of the project. 16462 - Recommendation: To ensure the requirement to have design coordinator spell out in the ITB. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6090 | Complexity of marine work sequence | 1. Congested area - Very tight construction corridor with high numbers of marine plants 2. Too regular marine plant movement 3. Uncertainty of the sea bed and tide conditions | 1. Slow marine work progress |  | 15568 - Action Taken: Program planning performed by experienced construction manager with the assistance of the planner | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | HSSE | 6057 | Compliance with safety regulation. | 1. Non-compliance with confined space and scaffolding. | 1. Improve HSE procedures. 2. Improve HSE compliance Incidents. |  | 15632 - Action Taken: Experiment conducted as determined O2 level in. 15633 - Action Taken: Training of workers at site. 15634 - Action Taken: Use instrument to measure data. 15635 - Action Taken: HSE committee - penalty for noncompliance. 15636 - Action Taken: Penalty imposed to contractor, sub-contractor and workers. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5094 | Compressor testing procedures contained lots of technical comments from PMC causing delay in procedure approval. | 1. Contractor reviewed and approved the procedures as per their previous project experiences. 2. Late vendor respond to PMCs comments 3. Non-compliance to PTS requirements | 1. Delay in procedure final approval by PMC. 2. Compressor testing schedule impacted, hence delivery of the equipment also impacted. |  | 14174 - Action Taken: Tele-conferencing between OWNER (PMC, UPT and core team), EPCC and vendor 14175 - Recommendation: Critical equipment testing procedure shall be submitted earlier ( 2 months in advance before testing schedule) for reviewed by Owner. 14176 - Recommendation: The review of the documents shall be conducted amongst vendor, EPCC and OWNER | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5544 | Concrete curing was not done as per procedure and method statement. | 1. Inadequate supervision from CONTRACTOR. | 1. Concrete curing terminated after 2 days. |  | 14743 - Action Taken: Instructed CONTRACTOR to continue curing in accordance to procedure and method statement. 14744 - Recommendation: CONTRACTOR to monitor closely concreting work. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Construction | 6033 | Concrete supplier unable to supply concrete as per demand. | 1. Seluyut dam and Sedili intake required high demand at same time (overlapping orders). | 1. Slow construction progress. 2. Schedule delay. |  | 15580 - Action Taken: Find alternative supplier. 15581 - Action Taken: Work long shift. 15582 - Recommendation: To have backup / alternative supplier to cater project demand. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5946 | Confusion on engineering standard to be adopted by EPCC, PTS vs water industry standard | 1. No clarity in the ITB | 1. Engineering work process delay affected procurement activities |  | 15747 - Action Taken: Concession given to the EPCC on case by case basis 15748 - Recommendation: Review on specification based on project specific requirement 15749 - Recommendation: Clarity on ITB for future project 15750 - Recommendation: Competent personnel in reviewing the ITB requirement/process | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Project Management | 5989 | Confusion on JV single line reporting | 1. CONTRACTORs C& S and M&E team were not reporting to same leaders. | 1. CONTRACTORs M&E and C&S team are reporting to different managements. PMC has to communicate with two different parties and mediate them if conflict arises. |  | 15819 - Action Taken: Involvement of EPCC higher management to resolve 15820 - Action Taken: PMC to play roles as middle man 15821 - Recommendation: Contractors to ensure they report to one single site management even though they are from two or more JV partners. 15822 - Recommendation: ITB to emphasize on single line reporting for JV partners | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Document Management | 5421 | Confusion on the scope of HSE design and HSE in overall. | 1. Some document not properly distributed to the correct RP as all the documents are under same discipline (i.e. HSE). Example: - Working at height, Project HSE plan, etc. should be sent to HSE team under directorate, not HSE design / Process Safety. | 1. Delay in reviewing and approval of site HSSE related document. |  | 14502 - Action Taken: Need to have clear demarcation on the scope & responsibility between these two. 14503 - Action Taken: PDDM need to aware on these. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2097 | Congested working area | 3 contractors working within the same area (P20C3-1, P18) | Disruption in workflow | Regular interfacing / coordination meeting between contractors | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5814 | Considering wind or earthquake load at rotating equipment nozzle evaluation | 1. All nozzle loads on connected rotating equipment shall be calculated in maximum operating conditions as per ITB. 2. Also the equipment nozzle loads resulting from wind or earthquake in addition with thermal + weight + pressure will be checked as per ITB. International practice (code (NEMA SM23), manual (Peng, Kellogg), vendor opinion, etc.) require that wind of earthquake loads to be considered in pressure vessel and not in rotating equipment. | 1. ITB criteria is not clear Discrepancy between Owner requirement and International practice |  | 15474 - Action Taken: Additional support such as snubber, spring and routing change is considered to comply with Owner requirement. 15475 - Recommendation: Preventive Action. 15476 - Recommendation: Specific instruction | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5782 | Consolidated QRA study by OWNER before ITB issuance. | 1. Lack of any overall QRA study, which is needed to establish building blast resistance to pressure waves and contours that might be imposed on EOEG from outside units. | 1. Unclear definition of QRA safety requirements during EPCC phase. |  | 15409 - Recommendation: Owner should conduct a consolidated QRA Study to solidify scope definition prior to EPCC contract award. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5773 | Construction execution plan - Pre Assembled Unit (PAU) strategy never assessed even though massive available capacity to build offshore, MOLF and heavy haul road are required for 2000+ tonne equipment, and skilled labour not available for stick-building. | 1. Lack of construction strategy as part of FEED. | 1. Heavy reliance on site based work. |  | 15388 - Recommendation: Investigate feasibility of PAU and implement where possible to reduce heavy reliance on direct labour at site and eliminating sensitive issue of foreign labour quotas / work permits. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B2-MOLF RAMUNIA | IO-P20B2-MOLF RAMUNIA | Planning | 6101 | Construction manpower and equipment load chart was not well planned in term of document presentation at the early stage of the project | 1. Contractor does not familiar with OWNER requirement. Normal conventional contract does not implement detail manpower & equipment monitoring system like PETRONAS | 1. Work Progress and completion of work |  | 15536 - Action Taken: Owner assisted Contractor in developing the template and resources load chart 15537 - Recommendation: Recommend Contractor to engage a qualified planner 15538 - Recommendation: Recommend Contractors Project Manager / Construction Manager to have relevant experience in similar project | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5554 | Construction planning & scheduling was not established by CONTRACTOR and made available for site team reference. | 1. Improper planning and coordination was observed during construction where involves integrated discipline works at the same location. i.e. Main pipe rack (UG piping, CP installation, backfilling & STL-STR installation). | 1. Proper construction planning & resources arrangement were not in place, can create dis-harmony and delay to the project. |  | 14769 - Action Taken: Requested CONTRACTOR to provides such information since Oct16, with verbally follow up, emails and also minuted in Construction WPM, but still unable to obtain the requested information for reference and site monitoring. 14770 - Recommendation: Need competent site planner to coordinate within discipline PIC and established officially / mutually agreed schedule that every discipline / Sub-contractor to meet agreed time line. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B2-MOLF RAMUNIA | IO-P20B2-MOLF RAMUNIA | Planning | 6100 | Construction timeline was unclear and work sequence was not well defined at the early stage | 1. Contractor does not have an in-house planner. 2. The construction planning performed by third party was not experience in construction work | 1. Slow schedule development |  | 15532 - Action Taken: Owner assisted Contractor in refinement of the work schedule 15533 - Action Taken: Owner close monitoring and tracking of the work progress 15534 - Recommendation: Recommend Contractors Project Manager / Construction Manager to work out construction methodology and planning 15535 - Recommendation: Recommend for Contractor to have own experienced planner | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5624 | Continuation of PDR issuance from Core Engineering may impact engineering change design and schedule. | 1. Late changes in engineering design from core engineering and UIO. 2. The last date PDRs submission was not clearly indicated and PDR issuance continue even few months after LOA. | 1. Potential change order. 2. Potential schedule impact. |  | 14932 - Action Taken: Regular meeting were conducted between core, UPTs and UIO. 14933 - Recommendation: Introduce last date submission. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Precommissioning/Commissioning | 5666 | Continuous communication between CONTRACTOR and OWNER during engineering which contribute to earlier submission of deliverables by CONTRACTOR. | 1. Regular discussion and clarification before official issuance for every deliverables, e.g. PreComm & Commissioning Plan, Roles and Responsible Matrix. 2. Mutual understanding and cooperation. Any feedback and comment been highlighted on the document by offline. | 1. Ahead of schedule. 2. Changes can be made prior to issue officially the document thru PDEMS. |  | 15052 - Action Taken: Continuous communication between CONTRACTOR and OWNER during engineering. 15053 - Recommendation: Clear and detailed explanation to each party on their scope of work. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | HSSE | 5275 | Continuous findings with regard to opening and hole in the building despite the issuance of reminders and alerts. | 1. Sub-contractors failed to cascade down the info to their respective personnel and vendors. | 1. Several Unsafe Conditions associated with opening and hole in the building being captured as well as one (1) First Aid Case occurred. |  | 14389 - Action Taken: To ensure proper planning on the switch gear and panel installation. 14390 - Action Taken: To open up effected hole only instead of opening up the whole stretch during the installation. 14391 - Action Taken: To cover all holes using hard plywood or metal form work. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Award/Contract | 5654 | CONTRACTOR did not fulfil all the Insurance requirement in the CONTRACT at the required period. | 1. Partial submission of insurance deliverables by CONTRACTOR. | 1. Incomplete submission of CONTRACTORs and Subcontractors insurance deliverables. |  | 15020 - Action Taken: Reminding CONTRACTOR, Head Office and Group Insurance. 15021 - Recommendation: Engagements with various stakeholders on insurances deliverables. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Award/Contract | 5658 | CONTRACTOR did not understand the principles of insurance in construction project. | 1. CONTRACTOR requested part of OWNERs CAR & CGL insurance cover not being issued with complaints of perils coming to CONTRACTORs way. 2. CONTRACTOR lack of understanding on liability and insurance aspect of the CONTRACT are too glaring. | 1. Lead to ill intention and wastage of effort in communication. |  | 15029 - Action Taken: Educate CONTRACTOR. 15030 - Action Taken: Expedite Group Insurance to hasten issuance of remaining CAR and CGL not due to CONTRACTORs goading, but to safeguard OWNERs interests. 15031 - Recommendation: Earlier planning by GROUP INSURANCE to issue insurance cover for the Project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6029 | Contractor didn’t lock the delivery date with the marine pile manufacturer | 1. Contractor missed out booking the piles casting programme with the manufacturer | 1. Contractor end up with their own additional cost to meet the work programme |  | 15539 - Action Taken: Owner forced the Contractor to engage alternate supplier 15540 - Action Taken: Owner and Contractor closely monitoring and tracking the marine piles delivery schedule | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | HSSE | 5640 | CONTRACTOR failed to execute their HSSE execution plan. | 1. Improper planning of activities, manpower, and sequence by CONTRACTOR. | 1. Delay to some construction work as Owner need to review HSSE documents and plans prior approving the work. |  | 14970 - Action Taken: Communicate through memo and enforced at site the requirement to submit paperwork in advance to allow time for OWNERs review and comment. 14971 - Recommendation: CONTRACTOR to have proper planning for future activity. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | HSSE | 5638 | CONTRACTOR failed to submit all HSE Procedures in P-EDMS and approved by OWNER before project execution. | 1. Late submission of certain HSE procedures. | 1. Impacted HSE compliance and awareness among site workers (OWNER & CONTRACTOR) as procedure were not yet available to them. |  | 14964 - Action Taken: OWNER urged CONTRACTOR to submit the procedures through meetings and email. 14965 - Action Taken: OWNER manually reviewed and commented the procedures (for those that doesnt have P-EDMS access). 14966 - Recommendation: Submission of procedures should be in timely manner. 14967 - Recommendation: Company computer and P-EDMS software should be made ready for new staff. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Award/Contract | 6300 | CONTRACTOR is not familiar with PETRONAS requirement | 1. First project with PETRONAS | 1. Schedule delay |  | 16465 - Action Taken: Provided guidance 16466 - Recommendation: OWNER to provide seminar to all new local contractor | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6081 | Contractor lack in managing engineering | 1. Contractor does not have experience in doing engineering 2. Contractor did not have experience manpower to manage the engineering design work | 1. Design quality and work progress |  | 15548 - Action Taken: Owner intervened by assist in managing the 3rd party deliverables 15549 - Recommendation: Recommend to scrutinize contractor engineering manpower and experience | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | HSSE | 5642 | CONTRACTOR lack of control their workers and SUBCONTRACTORS (language, work attitude and knowledge). | 1. CONTRACTOR did not screen workers during hiring. 2. CONTRACTOR doesn’t have a competent training manager. | 1. Potential HSSE incident. |  | 14976 - Action Taken: OWNER required CONTRACTOR to provide trainings for their workers and SUBCONTRACTORs. 14977 - Recommendation: CONTRACTOR to have proper screening process before hiring workers. 14978 - Recommendation: CONTRACTOR to hire competent training manager. 14979 - Recommendation: OWNER to ensure the HSSE system are implemented. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B2-MOLF RAMUNIA | IO-P20B2-MOLF RAMUNIA | Engineering | 6096 | Contractor lack of experience in EPCC contract; particularly in engineering management | 1. CONTRACTOR engineering was led by the Project Manager 2. Lack of experience in managing engineering consultant 3. Most of the engineering matters were dictated by the Engineering consultant | 1. Slow progress in Engineering and Design Work |  | 15520 - Action Taken: Owner engineering assisted in managing in engineering deliverables 15521 - Recommendation: Recommend Contractor to have experienced engineering personnel to manage the engineering deliverables | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5855 | Contractor misinterpret concept of the flare header and sub flare header. Contractor follow the slope requirement of flare header but not for sub header because it is not specified in PTS. | 1. PSVs for purification unit not designed for slope to sub header 2. Discrepancies in PTS requirements with Contractors 3. Unfamiliarity with PTS requirements by vendors 4. Stringent PTS requirements | 1. Redesigned the PSV location as per PTS requirement caused delays in design analysis |  | 15127 - Recommendation: To include the flare sub header requirement in PTS 15128 - Recommendation: Specific Model Review to be conducted based on PTS requirement at early stage of FEED to identify gaps 15129 - Action Taken: Redesigned the PSV location as per PTS requirement. 15130 - Action Taken: Intervention by PETRONAS GTA (process) | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Quality | 5797 | Contractor not comply to the document issuance process. | 1. Many document were simply issued to OWNER without going through a proper checking. 2. Lack of guidance and checking by senior engineers at SC. | 1. Too many errors were found on multiple documents i.e. typo error, formatting, clerical errors etc.). 2. OWNER were acting as quality checking. |  | 15449 - Action Taken: Feedback were given to SC Process Team and currently, the documents were issued to OWNER only by Lead / Senior Process Team. 15450 - Action Taken: SC accept the feedback and improve the documents quality. 15451 - Recommendation: Quality checking practice. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6083 | Contractor too dependent on the subcontractors | 1. Contractor intended to sub all the works to 3rd party inclusive project management | 1. Contractor cannot control the work, 2. Very slow work progress |  | 15552 - Action Taken: Contractor terminated the 3rd party / subcontractors. 15553 - Action Taken: Contractor set up their own project management team to manage the project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5547 | CONTRACTOR used corroded scaffold. | 1. There was a delay in mobilizing new steel tubular for scaffolding by CONTRACTOR. 2. CONTRACTOR used existing corroded scaffolding as working platform to continue construction activity. | 1. Potential HSSE incidents. 2. Noncompliance to ZeTo Rules. |  | 14750 - Action Taken: Instructed stop work. 14751 - Action Taken: Requested CONTRACTOR to expedite mobilization of new scaffolding material as per project requirement. 14752 - Recommendation: The off spec material shall be banned from entering site to avoid HSE issues. 14753 - Recommendation: The mobilization of scaffolding material should have been done earlier. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Award/Contract | 6062 | Contractors cash flow issue. | 1. Milestones payment too rigid. 2. Rearrangement of work activities. 3. Priorities of construction. | 1. Changes of payment milestone cause additional workload of PMT. |  | 15643 - Action Taken: Payment milestone to be flexible sensitive to potential rearrangement work / activities. 15644 - Action Taken: Retention sum to be introduced also advance payment. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5260 | Contractors Engineering division did not update drawing reviewed and commented by IPMT Engineering which resulted in non-updated drawing used for construction | 1. Contractor did not comply to document turnaround time | 1. Site rectification work required thus delaying schedule and additional cost incurred |  | 14361 - Action Taken: Contractor to be more responsible and adhere to the document turnaround time and respond to comments promptly. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B2-MOLF RAMUNIA | IO-P20B2-MOLF RAMUNIA | Construction | 6095 | Contractors own initiative to mobilize additional marine plants at no additional cost to Owner | 1. To meet the timeline | 1. Project delivered as per schedule |  | 15519 - Action Taken: Timely monitored the progress and placing intervention whenever necessary | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Award/Contract | 6303 | Contractual Issue | 1. Some scope of work is unclear | 1. Dispute arised |  | 16470 - Action Taken: Negotiated to find a common ground. 16471 - Recommendation: Scope of work for EPCC near to clear | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Document Management | 5291 | Control Log Status for VDB and MDR | 1. Contractor are not aware of the requirement | 1. Will affect whole Rapid. Different contractor different arrangement / format |  | 14411 - Action Taken: Contractor to comply | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5751 | Core Engineering support for UPTs. | 1. Core Engineering has limited manpower which are occupied e.g. MAC and Refinery duties. | 1. Engineering input and resolution from Core Engineering is slow, exceeding the contractual response time with EPCC Contractor. |  | 15336 - Action Taken: Core Engineering acquires additional manpower, and identify focal person for all Petchem units. 15337 - Recommendation: To have a dedicated coordinator at Core Engineering level. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5250 | Corrosion at recycle gas compressor turbine body and shaft | 1. Lack of preservation | 1. Depending on corrosion location, require cleaning and touch up painting. If shaft corroded at burnished area, the shaft has to be taken out, rebuilt, machine, and polish |  | 14344 - Action Taken: Make sure good packing and preservation before mobilizing from factory. 14345 - Action Taken: Thorough checking of equipment and packaging during receiving at site 14346 - Action Taken: Make sure compliance of preservation program | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5483 | Corrosion Deliverables not identified at early stage | 1. CONTRACTOR lack of experience causing corrosion deliverables are delayed. There is no Corrosion Engineer / Specialist in CONTRACTORs team. CONTRACTOR denies the P-RBI under its scope makes thing worse. | 1. Potential delay in corrosion deliverables and impacted other discipline deliverables. |  | 14610 - Recommendation: Early identification of the requirement. 14611 - Recommendation: To have Corrosion Engineer / Specialist in CONTRACTORs team. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Procurement | 6193 | Costing budgeted for Instrument Air Dryer Package is a way too low compare to the actual cost quoted by the suppliers. (park) | 1. Wrong cost estimation has been used during the bidding stage. | 1. Cost over-run for Instrument Air Dryer Package which is affecting the overall project budget. |  | 16230 - Action Taken: Conducted several evaluation of suppliers in terms of technical compliance and with lowest commercial offer. 16231 - Action Taken: Selected the suppliers with lowest offer and negotiated further on the overall costing to substantially reduce the negative cost impact to project. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Undefined | 6309 | Critical path was not established properly | 1. Lacked of details in engineering activities | 1. Logic could not be linked correctly between engineering activities and construction activities 2. Difficulty to calculate EOT from the schedule slippage |  | 16481 - Action Taken: Focused put on extracting critical path 16482 - Recommendation: Same detail level must be established in engineering and construction | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2067 | Critical sand supply with big volume and challenging time frame | 1. Sand pumping not suitable 2. No jetty along shoreline 3. Poor procedure and logistic arrangement | -Delay in ground treatment work -Create local discontent -Delay in in progress and cost | Direct discharge of sand from Penebuk jetty (Private jetty) -use agregate as an alternative. | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Document Management | 5423 | Current DCC database platform is not standardize between OWNER and EPCC. | 1. Mumbai office using FTP, EPCC using Petrocept while UPT is using POL and P-EDMS. | 1. Review and approval cycle takes longer time. 2. Misalignment on the latest update of documents status. |  | 14507 - Action Taken: To have regular meeting between both OWNER and EPCC DCC to streamline the update. 14508 - Recommendation: To have a standardize system for DC. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5223 | Daily report is not accurate | 1. Lack of site verification | 1. Impact on the target planning and progress claim |  | 14300 - Action Taken: Highlight to planner to verify on the target and progress claimed | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5763 | Damaged to equipment at vendor shop i.e. EO reactor baffles. | 1. There was an unexpected accident at vendor shop which resulted in damage of 4 finished tube support baffles (with around 40,000 holes). 2. Vendor didnt arrange fabrication shop properly. 3. Counter weight of lifting equipment fell on the baffle. | 1. Original schedule impact was estimated at 10 weeks. |  | 15361 - Action Taken: Safety and fab process audit was perform to ensure no further mishap will happen. 15362 - Action Taken: Safety refresher was performed by vendor as well. 15363 - Action Taken: Actual schedule impact reduced to 4 weeks after mitigation actions. 15364 - Recommendation: Remind and ensure EPCC contractor to review process and shop layout plan before fabrication. 15365 - Recommendation: Resident inspector should be more vigilant to ensure all the finished components are properly protected from possible external damage. 15366 - Recommendation: For criticality 1 and 2 equipment, add loss prevention review should be added to scope of PIM. For criticality 1, shop audit to be considered. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5432 | DCS 100% SPD requirement for spare cores from field | 1. ESD and FGS FDS clearly specify this requirement. DCS does not clearly specify. | 1. Lengthy discussion / man-hours wasted for discussions to resolve this matter 2. Other packages are also affected and discussion is still on-going |  | 14524 - Action Taken: To correct FDS and clearly mention the requirement 14525 - Action Taken: CONTRACTOR agreed to provide after achieving mutual agreement | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5469 | Dedicated line from AOC Collection Basin to Light Slop Oil Tank | 1. Relevant drawing or line schedule is not available. Tank P&ID does not show the line. It is only shown on typical P&ID. | 1. Potential change order. |  | 14589 - Recommendation: Ensure that Light Slop Oil Line from AOC Network to Light Slop Oil Tank, 5190-T-001 is available | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5098 | Defect during steam turbine casing casting process i.e. porosity | 1. Difficulty in casting process Note: Steam Turbine casing was manufactured by Man Diesel Turbo (MDT) has been identified with major casting defects | 1. Schedule Impact. Since this is the first incident happening in PMC, Rotating team has no direction on dealing with such issue and have not obtained proper support from relevant disciplines or parties. 2. The review activity has been delayed as there was no proper procedure and history to deal with such issue. |  | 14185 - Action Taken: PMC Rotating has cascaded this issue to PMC Core Team Rotating. 14186 - Action Taken: Rectification process e.g weld buildup were performed 14187 - Recommendation: Rotating team to involve and cascade the information to related parties ASAP should such incident ever happen again. 14188 - Recommendation: Rotating team to prepare brief report as soon as receiving the complete set of document from the CONTRACTOR. 14189 - Recommendation: To strengthen the review on casting method and technique | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Interface | 5870 | Delay close out action in Interface Management Tools (IMT) | 1. No dedicated Interface Engineer to supervise the interface issues. EPCC Contractor only assigned Interface Manager cum Permitting Manager in managing interface matters and permitting works. 2. Complication in RAPID interfacing | 1. Schedule impact |  | 15153 - Recommendation: For Mega Project that required a lot of interfacing works, a dedicated Interface Engineer shall be part of Project Key Personnel Requirement inside the CONTRACT | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5388 | Delay in closure of 3D model review comments. | 1. Lack of Engineering resources. 2. Locality of engineering resources. | 1. Delay in issuance of revised Engineering deliverables e.g. Underground layouts, Piping Isometrics. |  | 14429 - Action Taken: To ensure timely closure of model review and timely issuance of engineering deliverables. 14430 - Recommendation: The proposal of different location for Engineering between OWNER and contractor should not be agreed. 14431 - Recommendation: Alternatively OWNER should ensure contractor to provide adequate manpower. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Procurement | 5270 | Delay in delivery of equipment /materials due to factory capacity over-load, tight cash flow and lack of leadership/management skills. | 1. Excessively high commitment as a result of many Purchase Orders received resulting to aggressive schedule with limited float. 2. Poor cash flow management by Contractor during execution phase. 3. Lack of leadership training and/or Contractor staff attitude issues. | 1. Delay in installation & heavy lifting plan impacting subsequent construction activities. |  | 14379 - Action Taken: Owner stepped up to mitigate the delay by closely monitoring all fabrication activities through weekly management meeting and assignment of resident engineers/inspectors at fabrication shop. 14380 - Action Taken: Contractor must have proper plan to ensure sufficient resources (skilled manpower, manufacturing slot & financial capacity) before undertaking any mega project such as RAPID. 14381 - Action Taken: Contract Owner must strengthen bid evaluation criteria in terms of technical (quality, work load) and commercial (financial) with extra attention for mega project. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Document Management | 5419 | Delay in document / drawings transmission. | 1. Lack of sufficient resources in Document control. | 1. Critical documents were missed out or technical comments could not be closed out in time. |  | 14496 - Action Taken: Sufficient manpower to be provided for document control. 14497 - Action Taken: Regular Internal audits. 14498 - Action Taken: Extended working hours. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5268 | Delay in fabrication and delivery of bus duct to site even though PO has been awarded at earlier stage | 1. Due to different practice, CONTRACTOR requires actual site measurement to be done at site, after both transformer and switchgear to be installed. Engineering drawings for bus duct fabrication shall only be produced thereafter. 2. Lack of monitoring and mitigation plan by CONTRACTOR. | 1. Exposed CONTRACTOR to a bigger risk (with limited buffer schedule) of unable to energize the substation as per construction timeline i.e. if vendor cannot deliver timely, parts damage, construction issue etc. |  | 14375 - Action Taken: Engage CONTRACTOR to come out with detailed action and mitigation plan 14376 - Action Taken: Consistent monitoring by OWNER at important hold points | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Interface | 6071 | Delay in getting approval from JKR. | 1. JKR takes time to check the design. | 1. Late start of construction work. 2. Schedule delay. |  | 15657 - Action Taken: Contractor issued BG to JKR (JKR came to inspect first before contractor release the BG). 15658 - Action Taken: Closely monitor and follow up with JKR. 15659 - Recommendation: To have dedicated personnel to handle all the public relation engagement with local authorities. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Procurement | 6044 | Delay in getting land (site possession) after the PCC contract was awarded. | 1. Late FID on RAPID project, causing delay to land acquisition process (i.e. delay by Management to commit to acquiring the land). 2. Fast track project - the land acquisition process could not cope up with project requirements. 3. Head Of Agreement not finalized on time - the Management was not willing to commit to acquiring the land before the HOA was finalized. | 1. Overall Schedule delay (4 months). 2. Limited pipe staging area by contractor - pipe production had started but theres no place at site to send the pipes. 3. Line pipe production, which had been planned earlier, had to be slowed down. 4. Shorter overall project duration in order to meet the completion date (at the time, RWTPs first water requirement had remained the same). |  | 15608 - Action Taken: Negotiated with the contractor to secure Temporary staging area for pipes (1800 mm). 15609 - Action Taken: Negotiated with the pipe manufacturer to slower down the production (1.3mm) 15610 - Recommendation: Land acquisition must be made ready before award. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Construction | 6034 | Delay in getting TNB permanent power supply. | 1. TNB delay in responding to PAMER request for dedicated power supply to PAMER. | 1. Delay in getting permanent power supply. 2. Delay in testing & commissioning. 3. Unstable power supply (temporary supply). |  | 15583 - Action Taken: Managed to get temporary power from TNB but it is unstable and minimal protection. 15584 - Action Taken: Contractor used their own genset for installation and functional test. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5387 | Delay in isometric drawing resulting in finalization P.O of Piping MTO. | 1. Lack of Engineering resources. 2. Locality of engineering resources. | 1. Delay in Piping Prefab works leading to delay in piping installation. |  | 14428 - Action Taken: Priority areas identification in advance to ensure timely placement of P.O. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5386 | Delay in issuance of Engineering deliverables. | 1. Lack of Engineering resources. | 1. Impact to finalization of underground layout drawings. |  | 14427 - Recommendation: To ensure timely closure of technical comments and consequently timely issuance of engineering deliverables. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6188 | Delay in Issuance of smart plant database (SPI,SPPID,SPEL) files | 1. Late PO issuance and late receiving patch file from core team for Smartplant | 1. Possible schedule impact for completion of work |  | 16223 - Action Taken: Expedite PO issuance for Smartplant and patch file from core team 16224 - Recommendation: Timely transfer of files from core team and issuance of PO. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Procurement | 5506 | Delay in issuance/establishment of LC with the awarded vendors. | 1. Poor financial standing of the EPCC contractor. 2. Finance is handle by EPCC Central team in India, which not aware of the urgency at SITE | 1. Delivery of equipment and material was delayed and impacted progress (pumps, pipes, LLI etc.) |  | 14645 - Action Taken: Management meeting was held to intervene and to highlight the impact and urgency at SITE. 14646 - Action Taken: Establishment of LC by Cost Control team (monitored and expedited) 14647 - Recommendation: Stringent requirement during bidding especially on financial background. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6084 | Delay in marine site possession | 1. Late resolution of sea land title | 1. 5 months delay in commencement of construction activities |  | 15554 - Action Taken: PETRONAS management intervened by meeting the Stake holder i.e. Johor Royal 15555 - Action Taken: Awareness of Johor state and stake holder requirement for marine development | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Procurement | 5272 | Delay in obtaining CIDB Certificate of Approval (COA) approvals for selected imported goods | 1. Lack of awareness by Owner/Contractor/Appointed Agent for the new CIDB COA process 2. High volume of COA application received by CIDB with lack of resources | 1. Late custom clearance to meet construction demand 2. Exposed to port storage charges 3. Material shortage at site impacting subsequent activities |  | 14384 - Action Taken: Owner stepped up to mitigate the delay by closely monitoring all COA application through dedicated War Room and assignment of personnel at CIDB office 14385 - Action Taken: Permitting Team to come up with strategic action plan specifically for high volume COA applications | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Procurement | 5507 | Delay in placement of PO / top up PO for Valves, Cables, Structural Material and Pipes. | 1. Delay in identifying the total required quantity by the EPCC Engineering team. | 1. Delivery impacted the work front for construction progress. |  | 14648 - Recommendation: Competency of EPCC engineering team need to be assessed. 14649 - Recommendation: Detail engineering to be done to identify the actual required quantity for major material. 14650 - Recommendation: Payment milestone must be tied up with critical equipment / material based on quantity. 14651 - Recommendation: Milestone payment definition must be in detailed. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5256 | Delay in procurement of Cable tray support material. | 1. Material description not provided in the drawings properly. Late issue of PO | 1. Delay in cable tray Support fabrication and installation. |  | 14356 - Action Taken: Revised drawing to indicate material description. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Procurement | 5271 | Delay in Purchase Order issuance due to engineering | 1. Late finalization of additional engineering/design works | 1. Delay in delivery to meet construction demand 2. Material shortage at site impacting subsequent activities |  | 14382 - Action Taken: Engineering team to have detailed checklist prior to engineering closure 14383 - Action Taken: Procurement team to follow up with engineering team on finalization of MTO and tech. evaluation | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Engineering | 5510 | Delay in revision of Process Datasheet by Licensor and thus affected Mechanical Datasheet by FEED contractor. | 1. PDP and FEED are developed concurrently and at different location. i.e FEED at KL office except process and fired heater, PDP at Axens office France. 2. Any changes on the PDP has affected mechanical equipment design | 1. Several changes on mechanical datasheet |  | 14658 - Action Taken: Frequent review cycle 14659 - Recommendation: To centralize all the engineering works at one location. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Procurement | 6323 | Delay in shipping and clearance | 1. Poor logistic coordination by specialist subcon | 1. Schedule delay |  | 16505 - Action Taken: OWNER requested main contractor to closely monitor the delivery. 16506 - Recommendation: To ensure LLI items properly reflected in the list | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2092 | Delay in site mobilisation and work commencement | Incompliannce of contracts requirement (insurance etc) | Late mobilisation of resources and Proj. team | - PMC to guide and facilitate i.e provide samples/ guidelines to package contractor. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Procurement | 5505 | Delay in the delivery of Structural steel and Pipe material | 1. New Requirement of COA by CIDB prior to Port Clearance. 2. Inexperience team from EPCC on the subject matter. | 1. Impact in the work front for construction progress. |  | 14643 - Action Taken: Continuous workshop and engagement by PMC and PRPC team with EPCC and CIDB to streamline the approval process and expedite the Port Clearance. 14644 - Recommendation: Continuous workshop and engagement by PMC and PRPC team with EPCC and CIDB to streamline the approval process and expedite the Port Clearance. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5252 | Delay in work progress for cable ladder and cable tray installation due to late material delivery to site. | 1. Material delivered to site not based on the site requirement. 2. Approved for Construction (AFC) drawing not specify the detail route for lighting installation. 3. Additional MR issued by Engineering. | 1. Work pending (ie. indoor cable pulling, lighting installation etc.) due to shortage of materials. 2. Late PO issuance by subcontractor for lighting installation. 3. RFI cannot be issued without 100% completion thus hindering the cable pulling work progress. |  | 14351 - Action Taken: Co-operate with Procurement to expedite the delivery for the materials to site. 14352 - Action Taken: Engineering to have detail drawing for lighting installation. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Quality | 6277 | Delay on closing NCR / SSR | 1. Slow respond by engineering and construction on EPCC to deviate engineering specification using concession request. | 1. Delay on test pack completion and punch list category A. |  | 16410 - Action Taken: Expedited during weekly construction meeting and monthly QAQC meeting. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Quality | 6278 | Delay on finalizing MC document format | 1. EPCC has their own typical template and requirement. | 1. Delay on MC dossier. 2. Delay on PSSR completion. |  | 16411 - Action Taken: Realignment the minimum RAPID and PGSSB requirements towards MC. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Quality | 6276 | Delay on the CMS database update for test pack completion | 1. Insufficient training for CMS. 2. CMS system not user friendly. 3. Incompetent operator. | 1. Delay on MC documents. 2. Delay on pressure test execution. |  | 16408 - Action Taken: Additional manpower. 16409 - Action Taken: EPCC supervised the subcontractor closely. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Procurement | 6191 | Delay on the issuance of PO to suppliers against the target schedule. | 1. Late issuance of engineering specification and TBEs. | 1. Possible delay on the delivery of items to Yokogawa workshop. |  | 16227 - Action Taken: Expedite the suppliers to improve the lead time by adding resources/manpower to meet the expected delivery. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Construction | 6295 | Delayed arriving of material for building work | 1. Oversea material procurement | 1. Construction delay |  | 16454 - Action Taken: Material by Air Freight 16455 - Recommendation: To utilize local fabricator as far as possible. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6179 | Delayed information from sub vendors on critical activities | 1. Late TBE finalization and PO issuance | 1. Extension of engineering schedule 2. Few engineering deliverables were being delayed due to lack / incomplete Vendor or sub-vendor information |  | 16199 - Action Taken: Vendor Data finalised as per schedule - within appropriate timeframe 16200 - Action Taken: Frequent session meetings (WAR room) with vendors 16201 - Action Taken: Prioritize TBE and expedite PO issuance 16202 - Recommendation: Award PO issuance timely | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | HSSE | 5639 | Delayed notification of incident from CONTRACTOR to OWNER. | 1. Unclear Incident Notification and Reporting procedure shared to subcontractor by CONTRACTOR. | 1. Poor and slow action taken by responsible parties as information received was delayed. |  | 14968 - Action Taken: Shared, made known, and enforced CONTRACTOR and subcontractors on OWNERs Incident Notification & Reporting flow. 14969 - Recommendation: OWNER should enforce the usage of PRPC Incident Notification & Reporting Procedures from the beginning of project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6183 | Delayed of P&ID issuance has delayed other discipline tasks | 1. Lack of manpower | 1. As only ONE (1) Sr. Process Engineer involve to overseer, design and as focal point for any meeting with PRPC, ample time to complete clean version of P&ID is not always available. Dependent to other Jr. Engineers may make way to resolve, however further check is still required from lead process engineer. |  | 16212 - Action Taken: To have more Sr. Process Engineers to cover Process Engineering works. 16213 - Action Taken: From time-to-time, every discipline need to communicate with PRO team on any update which may impact their discipline design works to speed up the deliverables submission 16214 - Action Taken: To speed up the preparation works, other disciplines has offered the help to assist on drafting works. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Engineering | 5531 | Delayed PAAF approval | 1. Slow approval by PRPC | 1. Unnecessary additional work to FEED team. 2. Rework due to inaccurate input data. 3. Access to RAPID standard was only permitted after PAAF approved. |  | 14697 - Action Taken: Expediate to RC Management 14698 - Recommendation: To timely approve PAAF as per approved FEED organisation chart. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Project Management | 5535 | Deleted inputs from ITB was not communicated and discussed | 1. Time limitation on additional OWNERs option | 1. Lack of options for cost saving to OWNER |  | 14705 - Recommendation: OWNERs option to be identified earlier. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5610 | Delivery period in the TBE is not reflected in the LOI / PO. | 1. CONTRACTOR negotiated / finalized delivery period after approval of TBE. 2. CONTRACTOR still seeking some technical and commercial clarification after Award Recommendation (AR) approved. Thus, some PO were issued few weeks after AR approved which led to delivery date to be later than expected. | 1. Some deliveries do not meet the target or L3 schedule delivery date. |  | 14898 - Action Taken: Requested CONTRACTOR to indicate the delivery period in Award Recommendation to check whether final delivery period meet the L3 schedule. 14899 - Action Taken: Concern raised for delivery date foreseen to be beyond L3 schedule during Kick-Off Meeting (KOM). 14900 - Recommendation: Delivery period to be part of CONTRACTOR Technical Evaluation and delivery period and estimated delivery date to be clearly indicated in the Award Recommendation. 14901 - Recommendation: CONTRACTOR to indicate expected date of delivery instead of delivery period only during submission of Award Recommendation. The expected date of delivery to include duration required by Contractor to finalize the PO. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5211 | Design changes interdisciplinary not properly escalated / communicated (among EPCC or EPCC-PMC / Owner) | 1. No proper communication procedure interdisciplinary 2. Changes from other discipline was realized last minute in later stage of design and not well communicated resulting design changes. | 1.Additional VO 2.Delay in schedule |  | 14273 - Communication between PMC - SEG and SEG - vendor need to be clearly recorded 14274 - To develop communication procedure to escalate the info to all relevant personnel to assist in design changes | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Quality | 6007 | Design coordination | 1. No M&E design coordination prior to wall construction | 1. Hacking of wall for M&E services |  | 15853 - Action Taken: The wall has to be hacked for M&E services opening 15854 - Recommendation: Proper design coordination among M&E & architecture. M&E design coordinator to be appointed | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Document Management | 5522 | Design documents from consultant received by PMT too late due to poor system | 1. Unreliable P-EDMS System caused late review 2. Lack of communication procedure | 1. Delay of Document review 2. Late submission of some project documents |  | 14678 - Action Taken: Do offline review with consultant before update it into P-EDMS 14679 - Recommendation: Once the document submitted into P-EDMS, consultant to alert/prompt PMT via email (cc) 14680 - Recommendation: Enhancement of the system to speed up the system retrieving and receiving | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5689 | Design error of vendor for K-230 | 1. Vendor didnt consider high suction pressure for overhung type single stage centrifugal compressor. | 1. Vendor suggested thrust balancing design with hydro jacking device for high suction pressure and OWNER confirmed. |  | 15086 - Action Taken: High suction pressure has to consider for overhung type single stage centrifugal compressor and contractor has to check to implementation on the design to vendor. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Construction | 5897 | Development Order and Building Plan submission to Authority Extrusion and Other Concrete Buildings. To prepare the DO and BP application our Local Consultant requested to provide documentation covering the whole project area. |  |  |  | 15194 - Applied Solution: Project team has provided an acceleration to complete said documents for DO and BP in time to obtain relevant Construction permits in due time according to the project schedule. 15195 - Suggestion for Improvement: We have investigated with Authority the possibility to split the DO and BP application for sub areas/building in order to proceed requiring construction permits well before the completion of documentation for all project. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6175 | Deviation from requirement in ITB. | 1. HER for Package P32 was not conducted as per ITB requirement. This is one of the findings observed from the recent Audit conducted for P32 Contractor. 2. Engineering studies which have been specified in ITB not performed. During the initial stage of project, agreement was taken from the Owner not to conduct the studies but required documentation was not completed. | 1. No significant consequence. Agreement not to conduct this study has been done during FEED via email but no PDR was raised. 2. Some PMC Core team members were not aware of this development as written agreement was not taken. |  | 16190 - Action Taken: A PDR was raised to address this deviation. 16191 - Action Taken: Follow proper project procedures to take required approvals from Owner to avoid any non compliance. 16192 - Recommendation: Thorough checks before issuance of ITB | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Procurement | 5405 | Deviations at TBE for bidders manufacturing location, name change and acquisition by company not listed with reference to MVL. | 1. EPCC finding cost saving by utilizing manufacturing location which has lower cost. | 1. Potential quality issue. 2. Impact on delivery. |  | 14457 - Action Taken: Contractor to be proactive in issuance of deviations with complete documents for Owner / PMC review approval to avoid delay in TBE approval and reduce returning of TBEs with code 2. 14458 - Action Taken: Guided with checklist and engage thru emails and meetings to ensure compliance and expedite TBE approval process. 14459 - Recommendation: To have arrangement similar with GFA. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5202 | Difference in Units covered under EPCC Package versus Operating Area; For e.g., SGP is part of UPT-3, but in Area 1 Operation together with CDU, SGP and FOS. CDU and FOS are part of UPT-2. | 1. May have been driven by different in objectives during the award of EPCC package. | 1. Challenges in coordination and alignment between Project Team and Operation (for docs review) - for e.g. in EPCC 2, CDU is in Operation 1A, while ARDS is in Operation 2A. |  | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Precommissioning/Commissioning | 6068 | Different requirements between O&G and Water Industries. | 1. The requirement was not included in ITB. | 1. Delay in commissioning. 2. VO to PCC contact. |  | 15654 - Action Taken: To incorporate the requirements in the ITB. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5396 | Different seismic standards from various disciplines were stated in project specifications. | 1. No integration during development of project specs. | 1. Confusion in detailed design causing delay in drawing issuance. |  | 14443 - Recommendation: The design guidelines for attaining seismic coefficient for design of other disciplines should be standardized to avoid confusion. 14444 - Recommendation: Specifications related to other disciplines in terms of seismic design should make reference to SHA report by owner. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Construction | 6036 | Different standard practices / requirements between Water industry and Oil & Gas industry. | 1. Difference in discipline / industry. 2. Both contractor and consultant were from water industry and were not familiar with PETRONAS / O&G industry practices, while PETRONAS team was expecting the contractor to comply with its normal standard practices. 3. ITB was originally developed following normal water industry requirements. | 1. Construction activities were undertaken in non-compliance to PETRONAS standards particularly relating to HSSE requirements. 2. Some of these requirement resulted in VOs. 3. Schedule delay. 4. Testing delay (NOT CLEAR WHAT THIS MEAN?) 5. Operational Readiness Assessment (ORA) was conducted using PETRONAS standards as reference. 6. Delay to closure of Operation Readiness Assessments findings. |  | 15587 - Action Taken: Provided training on DOSH basic requirements. 15588 - Action Taken: Engaged competent safety personnel to supervise safety related matters. 15589 - Recommendation: The requirements to fully comply with PETRONAS’ standard requirements to be clearly spelt out in the ITB. 15590 - Recommendation: Obtained exemptions from PTS. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5085 | Different understanding in scope interpretation lead to lack of closure of pending items by Contractor | 1. Incomplete and lack of details in FEED document leading to misinterpretation of project requirement 2. Different contractors practice or experience from different project 3. Unfamiliarity of the PTS requirements 4. PTS clause contradiction and unclear requirement with Project specifications | 1. Design proceeded not to the required project specification 2. Late rework that leads to impact to schedule 3. Potential cost impact 4. Potential Non-Conformance (NCR) |  | 14152 - Action Taken: Intervention by the Core Engineering team in KL 14153 - Recommendation: To provide clear and precise instruction to Contractor in order to close the item. 14154 - Recommendation: Review session with contractors in the early project stage for main/critical Design requirement 14155 - Recommendation: To revisit PTS requirements | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Project Management | 5537 | Difficulties / challenges during technical bid evaluation | 1. Difficulties in files sharing within TBE room 2. Difficulties in data access (ITB, technical clarification, data exchange) 3. Limited no of laptops | 1. Delayed in evaluation |  | 14707 - Action Taken: Increased no of laptops 14708 - Recommendation: Local network workstation inside TBE room | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Award/Contract | 6252 | Difficulty in managing contractor from different culture | 1. Change Notice / Change Proposal not detail (scoping and cost breakdown) 2. Different way of managing project (e.g Change notice / proposal not meeting owner expectation) | 1. Delay in approval 2. Delay in execution |  | 16371 - Recommendation: Contract with EPCC need to be robust to minimize scope change / VO etc. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Interface | 5292 | Difficulty in managing interface issues coordination i.e. Contractor to Sub contractor | 1. All sub-contractors not giving good cooperation among each other. 2. Late design change | 1. Delay in paving and cable trench completion |  | 14412 - Action Taken: Daily interface meeting between all discipline | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5680 | Difficulty of finding coating vendor | 1. Coating system qualification requires long term test; - Coating resistivity (100 days) - Thermal ageing (200 days). => As there is no coating category & vendors in MVL, it was hard to find vendors with the long term test certificate. 2. Hard to apply the 3LPE coating system to Fitting; - 3LPE system requires specialized automatic equipment for the cleaning & coating, which is used for a straight run pipe. - This process is not suitable for complex shapes of fittings such as elbows, tees, etc. | 1. Coating vendor who has been qualified in other RAPID Package has been selected for pipes. 2. Instead of 3LPE coating, Liquid Epoxy Coating has been applied for fitting. |  | 15078 - Recommendation: OWNER to provide a list of approved coating applicators who are qualified with long term test, are able to 3LPE for fitting. 15079 - Recommendation: This will reduce the time of vendor selection in the early stage. Dr gtAlso, help for the tight underground construction schedule. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5677 | Direct inquiry to OEM for PSI category equipment | 1. Cable was PSI category item during proposal stage, but it has been changed to direct inquiry item after award project. | 1. As per CONTRACTOR’s analysis, the price of OEM is 1.15 Mil USD higher than PSI. In the case of application of Gaon cable, the price of OEM is 0.63 Mil USD higher than PSI. 2. OWNER confirmed to use alternative approach to sourcing of the mandatory category items (managed by Prime Sourcing International Sdn. Bhd. (PSI)) as previously advised by OWNER has no impact either negative or positive on the CONTRACT PRICE now or in the future. |  | 15075 - Action Taken: If change has been occurred, have to analyze impacts for the change and share / discuss with OWNER. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5400 | Discrepancies between IPF findings and specs requirements e.g. partial stroke test for on/off valve. | 1. The IPF was carried out after the TBE has been finalized. | 1. Changes to the valve resulting in potential delay to project. |  | 14448 - Recommendation: To ensure any workshops/studies that involve potential changes to design to be undertaken before procurement of the material. 14449 - Recommendation: For any mandatory studies that must be done after material procurement, to remind the contractor during the study itself to do it as earliest as possible to minimize the impact. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5394 | Discrepancies between project specs and PTS - Piping class. | 1. Project specification between piping class and PTS 31.38.01.10 has discrepancies. Toxic service shall have its own piping class and Class A fugitive emission test shall be enforced for very toxic service. | 1. Does not complying to Class A fugitive emission test. |  | 14440 - Action Taken: Proper justification made for class B with the technical background. 14441 - Recommendation: Check for discrepancies during FEED. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Award/Contract | 5805 | Document agree process for Milestone Payment deliverables. |  | 1. Smoother the project execution. |  | 15452 - Recommendation: Prescribe evidence documents and procedure for payment milestone validation in the ITB. 15453 - Recommendation: Project Team to be allowed to improve Payment Milestone description for clarity. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Award/Contract | 5807 | Document agree process for payment and invoicing. |  | 1. Smoother the project execution. |  | 15455 - Recommendation: There is should be a process flow plan for invoicing and payment in the ITB. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Award/Contract | 5806 | Document agree process for Progress reporting. |  | 1. Smoother the project execution. |  | 15454 - Recommendation: Construction progress monitoring and reporting requirements should be more thoroughly defined in the ITB. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5622 | Document Distribution Matrix (DDM) was done manually. | 1. Delayed of CONTRACTORs Master Document Register. | 1. Missing the right assigned person for reviewer and consolidate. |  | 14928 - Action Taken: Expedite CONTRACTOR to re-submit MDR with OWNER comment. 14929 - Recommendation: Auto-DDM should be established for better document distribution. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Precommissioning/Commissioning | 5671 | Document to review: PFD / P&ID/ MSD shall be reviewed in staggered manners. | 1. The document was submitted in week lapse for review in results to shortage of time to review all document within 10 working days. | 1. The review of document was done in within the period for more than 200 document. 2. CONTRACTOR submitted the document based on the milestone target rather waiting for completion review by the Licensor. |  | 15066 - Action Taken: The team planned and scheduled the review by assigned specific area for each team member. 15067 - Recommendation: Staggered submission of the document will allow the time to be reviewed in details and proper manners. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Document Management | 6199 | Document work flow classification. | 1. Document classification not as per procedure | 1. Unnecessary document re- issuance for document class O. 2. Late finalization of document. |  | 16249 - Action Taken: EPCC to adhere to the agreed procedure 16250 - Action Taken: To ensure availability of QA / QC focal person. (Owner and EPCC) | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Interface | 5112 | DRAIN: Common area is flooded during raining season, since it is located in the middle of OTHER PACKAGES | 1. Temporary drainage is well further to the west side 2. West side temporary drainage to the North has been blocked by P14. 3. Permanent drainage is to the East (P3) and South (P14), which is not yet completed and build by OTHER PACKAGES. | 1. Impact to the daily work of Common area |  | 14217 - Action Taken: Pump out the flooded area 14218 - Recommendation: Suggest that the temporary drainage flow to be design same Permanent Flow. 14219 - Recommendation: The drainage shall be done by outside refinery packages, and shall be completed first for every package to use. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5819 | Drainage System for Transformer Area | 1. Drainage Concepts for TR System does not correspond. Each CTR’s design were different. Then, OWNER sent Project Memorandum. | 1. Project Memorandum were shared after design fix of Transformer Drainage System. |  | 15484 - Action Taken: To fix drainage concept for Transformer System: RAPID-FE1-TPX-CVS-DES-0001-0010; RAPID-FE1-TPX-ELE-DES-0001-0004 15485 - Recommendation: Preventive Action. 15486 - Recommendation: After review of Drainage System for Transformer, Modification of Specifications to Match Each Other is required. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5876 | Due to stringent requirements by CIDB, the COA approval process may take longer time (30-40 working days) | 1. No exemptions for PETRONAS Project/RAPID | 1. Delay in delivery of equipment/materials |  | 15161 - Recommendation: Higher level engagement with CIDB representatives in lobbying for COA exemption 15162 - Recommendation: Collaborated with Group Procurement on the COA for PETRONAS | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Construction | 6031 | During construction, site possession / land acquisition still ongoing. | 1. Late FID on RAPID project, causing delay to land acquisition process (i.e. delay by Management to commit to acquiring the land). 2. Fast track project - the land acquisition process could not cope up with project requirements. 3. Head Of Agreement not finalized on time - the Management was not willing to commit to acquiring the land before the HOA was finalized. | 1. 4 months delay in construction. 2. Construction cannot commence full swing. 3. Double handling of pipes - ready pipes delivered to site but could not be strung at site. 4. Main supplier pipe stop production because of limited space of storage at site. 5. Disruption in overall construction and manpower mobilization plan. |  | 15574 - Action Taken: Mock up at government land. 15575 - Action Taken: Main contractor mobilized in house team only and hold all sub-contractors. 15576 - Recommendation: Land acquisition must be ready before award. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5227 | During FEED and design stage the engineer need to consider constructability | 1. During design stage priority was given to install compressor | 1. Poor access during construction |  | 14305 - Recommendation: To consider crane access during design stage | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5857 | During FEED, the ACC PIT was designed as per Licensors Philosophy where 1 common line was used to route ACC water and Process water (150ppm<COD<1000ppm) to ETP unit 63000. EPCC Contractor just follow the FFED design. | 1. ACC Pit was not designed as per RAPID Project Specification for effluent management system 2. Discrepancies between PETCHEM industry practice and PTS | 1. Another line (80 mm line approx. 300 meter long to battery limit) to be added to send first flush with COD less than 150 ppm to ETP Unit 6320). |  | 15133 - Recommendation: To ensure that the waste water management follows the philosophy as specified in RAPID project specification. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5251 | Earthing cable damaged due to excavation and underground works. | 1. No dedicated supervisor to monitor and coordinate the excavation activity | 1. Disconnected earthing grid thus inefficient lightning protection to the plant. 2. Unnecessary rework which required additional man-hours and cost impact. |  | 14347 - Action Taken: Minimizing the quantity earthing cable damage by implementing the interdisciplinary coordination work. Work to execute after Civil and UG piping work completion. 14348 - Action Taken: To have dedicated supervisor 14349 - Action Taken: To have spare cables and jointing material. 14350 - Action Taken: During earthing grid system design, to avoid underground piping and foundation. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5821 | Elec./Inst. Tray support Design | 1. In EOEG plant there are multi-layered cable trays to support cables of Elec./Inst. And main route to be above ground | 1. Because of EMC requirements the requirement of space between trays is big than other project. 2. Eventually the height of structure to support trays are very high.(approx. 3m) |  | 15487 - Action Taken: Open-end type for support is considered for easy cable pulling work and maintenance 15488 - Recommendation: Preventive Action. Need to consider workability | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5928 | Electrical room access door shall be designed to open outward towards escape route, instead of open inward | 1. Electrical room egress shall be designed to allow quick and efficient evacuation during emergency. So the door shall be designed to open outward from inside the room rather than open inward. | 1. Access door at the Electrical room is designed for inward opening from internal. |  | 15712 - Action Taken: Contractor to re-design the door to comply. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5074 | Electrical: 1. Cable Gladding technical issue: Cable Gland size M50, M50S and M63 armor clamping ring does not grip with the cable armor. 2. shortage of cable gland especially cable gland for Air Fin Cooler Motor | 1. Lack of technical information regarding on cable gladding prior purchase the cable gland 2. Late PO issuance | 1. Poor electrical contact between the cable armor and the cable gland to ensure robust, and comply Ex Equipment requirement. 2. Delay in solo run Air Fin Cooler Motor. |  | 14094 - Action Taken: To check with cable gland vendor ensure the correct size of cable gland. 14095 - Action Taken: To expedite the delivery of cable gland. 14096 - Recommendation: To check the detail technical information regarding on cable gland and do mock up prior purchasing the cable gland. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5730 | Electrical: Additional requirement from P-ELSOR findings. | 1. P-ELSOR finding are not in the RAPID project specification. There are 37 out of 134 finding is not in the project specification. | 1. Difficulties to close the P-ELSOR finding with contractor and it is required several discussion to convince them in order to avoid change order from contractor. |  | 15281 - Action Taken: Arranged regular meeting with contractor in order to close the issues with support from PTA. 15282 - Recommendation: The input from other packages for P-ELSOR finding shall be shared to UPT in advance before detailed engineering in order to avoid any possibility of change order from contractor. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5733 | Electrical: Battery autonomy times for UPS. | 1. Discrepancy between 2 Project specifications: • According to RAPID-FE1-TPX-ELE-DES-0001-0002_Rev.3, Para 7.9.4, autonomy time of AC/DC UPS for HV / LV is 30 minutes. • As for RAPID-FE1-TPX-ELE-SPN-0001-0005 _Rev.0, Para [8.111] indicates tripping service of HV switchgear shall be minimum 8 hours. | 1. Late design freeze. 2. Late PO issuance. |  | 15288 - Action Taken: TEQ has been issued to Core Engineering to response on this matters. Core Engineering has responded that for HV, 8hrs battery autonomy shall be implemented. 15289 - Recommendation: Discrepancy between 2 project specifications shall be avoided. Some clause need to be aligned. 15290 - Recommendation: Battery autonomy times for UPS shall be standardized in the Project specs (RAPID-FE1-TPX-ELE-DES-0001-0002- Electrical Design Basis and Philosophy) shall be updated and clearly mentioned | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5594 | Electrical: Combine test for motor and starter should be clearly specified in the ITB. | 1. Unclear statement in the PTS and project specs for the combine test for motor and starter. | 1. Delay in procurement of starter and potential impact on motor delivery. |  | 14862 - Action Taken: Immediate instruction to Contractor to issue PDR / Deviation and to get quick approval from owner. A conditional approval was given to proceed with procurement. 14863 - Recommendation: Requirement for combined test motor shall be clearly specified in Project Specification. This will resolve the issue in case of motor starter requires a separate purchase from the driven motor. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5593 | Electrical: Comments, if any, related to items which are not explicitly defined in project specs were made in 2nd or 3rd revision (not in 1st revision) | 1. There are some new fresh (major) comments in new document revision. | 1. Some important comments were unintentionally missed out in the first revision. Contractor have to take longer time to re-issue new revision to incorporate new fresh comment for further approval. |  | 14860 - Action Taken: Consolidator has reminded all reviewers to ensure no major comments to be left out in first revision. Reviewers were reminded that the new fresh comments in each new revision might not be entertained. 14861 - Recommendation: Reviewers are recommended to have a checklist of the most likely error (major comment) in any documents based on other previous similar document in other packages. This will help to reduce possibility of missing out important comments. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5592 | Electrical: Contractor / Vendor were not ready for FAT for KM-675. | 1. Contractor unable to supply the coupling to the vendor timely. 2. Poor coordination by contractor. | 1. The FAT testing for 2.6MW Recycle Gas Compressor 3200-KM-675 was not fully done according to testing procedures. |  | 14858 - Action Taken: Contractor was instructed to send notification together with checklist for ensuring readiness of FAT. 14859 - Recommendation: The checklist on the internal shop test and readiness for FAT shall be provided and verified by all parties prior to issuance of FAT notification. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5589 | Electrical: Contractor did not fully incorporate all the comments in some of the documents. | 1. Misinterpretation of OWNERs comments. 2. Overlooked OWNERs comments. | 1. More review cycles are required resulting in unnecessary schedule delay. |  | 14852 - Action Taken: Conducted regular discussion meeting (weekly) as an avenue to update the electrical team progress, highlight issues / concerns and discussion on Owners comment on PEDMS deliverable. 14853 - Recommendation: To instruct contractor to be proactive to ask for clarification on any unclear comments made in PEDMS. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5595 | Electrical: Correct type of motor was not selected for Zone 2 Hazardous area classification. | 1. CONTRACTOR did not validate the FEED Datasheet for Motor. 2. Hazardous Area classification workshop was done after order was placed for the particular motor. 3. Conflicting requirements in project specs and PTS. | 1. Motor ordered with wrong specs. 2. Delay in motor delivery due to change of specs. 3. Potential cost impact. |  | 14864 - Action Taken: Immediate instruction to CONTRACTOR to recheck and confirm with process experts on the minimum amount and possibility of hydrocarbon presence in the driven line. 14865 - Recommendation: Hazardous area classification study and review session shall be done at earlier stage of Detail Design to confirm all hazardous related matters can be confirmed before equipment is purchased. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5072 | Electrical: Delay in lighting installation & wiring and late handover | 1. EPCC only provide Lighting layout Drawing as per project specification but drawing such as lighting cable schedule, or reticulation cable is not available for easy lighting installation and inspection. | 1. Delay in completion and handover of lighting installation |  | 14091 - Action Taken: EPCC to provide reticulation drawing based on input from construction team 14092 - Recommendation: Next project, EPCC to provide reticulation drawing for easy installation and inspection | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5732 | Electrical: Discrepancy of battery room requirement for building. | 1. Discrepancy between 2 documents: • Electrical Project Specs requires separate battery room only for battery with capacity exceeding 20,000VAh. • PTS 34.17.10.30 (Civil) requires separate battery room. | 1. Late building design freeze. |  | 15285 - Action Taken: UPT Electrical Engineer had a discussion with SECL and made a decision to have a combined AC UPS and battery room for FAR with an approval from Engineering Manager, Project Manager and Engineering Manager from RAPID Core Engineering. 15286 - Recommendation: Discrepancy with 2 documents shall be aligned with PDR. 15287 - Recommendation: Battery type for substation / FAR shall be determined clearly, and requirement of separate battery room shall be clearly mentioned. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5731 | Electrical: Execution of HAC workshop. | 1. Samsung was not aware on ITB requirement for HAC workshop. | 1. HAC workshop was conducted close to 90% engineering stage. It is quite late especially if there is major changes on Hazardous area classification. 2. Reissuance of several equipment PO due to reclassification of hazardous area. |  | 15283 - Action Taken: HAC workshop has been conducted successfully with the cooperation from all parties including all disciplines from OWNER, Samsung and Facilitator and all findings has been closed. 15284 - Recommendation: HAC workshop to be conducted at 30% Engineering stage. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5728 | Electrical: FAT testing for 13MW Recycle Gas Compressor Motor 3220-KM-201. | 1. Contractor did not understand / familiar with IEC standard. | 1. Failure of FAT testing. 2. Late equipment delivery. |  | 15276 - Action Taken: Immediately instruct contractor to test the motor based on IEC standard and performed the modification in the motor to meet the IEC specification. 15277 - Recommendation: The ITP and factory routine test shall be provided in advance. 15278 - Recommendation: Before the readiness of FAT it shall be verified by all parties prior to issuance of FAT notification. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5735 | Electrical: Implementation of Electrical Network Monitoring and Control System (ENMCS). | 1. Project Memorandum issued for implementation of Electrical Network Monitoring and Control System (ENMCS) during execution. | 1. Created a lot of misunderstanding to CONTRACTOR and few TEQ need to be issued to clarify. |  | 15293 - Action Taken: Few session of discussion with CONTRACTOR was held and below TEQ was issued by CONTRACTOR: i) RAPID-P0011-SCS-ELE-TEQ-3220-0029_0Q. ii) RAPID-P0011-SCS-ELE-TEQ-3220-0030_0Q & 1Q.iii) RAPID-P0011-SCS-ELE-TEQ-0021_0Q 15294 - Action Taken: PMC has released Project Memorandum RAPID-P0024-PMC-PMG-MEM-0073 dated 09 December 2015. 15295 - Recommendation: FEED drawing shall be revised to incorporate all the new design changes / additional requirements. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5591 | Electrical: Introducing time limit for reviewer has helped document review cycle. | 1. The DDM (Document Distribution List) was still in progress (with frequent changes) at initial stage of Engineering. This had confused some of the reviewers on their requirement to review. | 1. Overdue in document review. 2. Some reviewers did not aware the requirement to be part of reviewers. |  | 14855 - Action Taken: Reminder emails were frequently sent to related reviewers. 14856 - Action Taken: Introducing time limit with auto-termination scheme in PEDMS to keep the review window as schedule. 14857 - Recommendation: To finalize DDM and document controller shall ensure that the documents has been assigned to the exact reviewer. Each reviewer shall be responsible and take initiative to complete their task. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5070 | Electrical: Lack of support from Switchgear Vendor and shortage of material | 1. Poor planning from vendor to deliver complete material as per packing list | 1. Delay to complete switchgear installation work. |  | 14087 - Action Taken: Engage vendor to provide a full support and expedite the delivery of shortage material 14088 - Recommendation: Engage vendor to provide a full support and have a proper planning on material based on packing list. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5071 | Electrical: Not enough manpower to pull power cable | 1. Poor manpower planning | 1. Delay in completion of power cable installation |  | 14089 - Action Taken: To prioritize trench by trench 14090 - Recommendation: To add more manpower and to have a proper manpower planning. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5073 | Electrical: Poor preservation of power cable | 1. Lack of awareness on preservation | 1. Power cable may have low IR value and damage power cable. |  | 14093 - To make sure all power cable will be sealed end to end | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5069 | Electrical: Power Cable and Earthling cable damaged due to excavation and underground works. Very poor work coordination | 1. Work executed based on the available work front and not follow proper planning. | 1. Disconnected earthling grid thus inefficient lightning protection to the plant. 2. Unnecessary rework which required additional man-hours and cost impact. 3. Power cable damaged may cause severe impact on schedule and cost. |  | 14085 - Action Taken: To prevent power cable and earthling cable damage by implementing the interdisciplinary coordination work. Work to execute after Civil and UG piping work completion. 14086 - Recommendation: To prevent power cable and earthling cable damage by implementing the interdisciplinary coordination work. Work to execute after Civil and UG piping work completion. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5734 | Electrical: Source of ENMCS power supply. | 1. In project specification, there is no clear requirement for ENMCS control supply from DC UPS. 2. During P-ELSOR workshop, GTA highlighted this to CONTRACTOR that ENMCS power supply shall be from DC UPS. | 1. Late engineering design freeze. |  | 15291 - Action Taken: Samsung has make design changes. 15292 - Recommendation: Project specification shall specify clearly. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5729 | Electrical: Unclear TEQ response. | 1. Response provided from Core Team is unclear and without any solution. | 1. Prolong TEQ resolution. 2. Delay in deliverables. |  | 15279 - Action Taken: Discussion had been made together with contractor in order to resolve the issues and reconfirmed with core engineering to get approval from them. 15280 - Recommendation: Gather the information from project specification pts clause / phrase and practice with other packages together with support from core engineering before providing the information to contractor. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5727 | Electrical: Wrong interpretation from the comment in PEDMS. | 1. Lack communication between Owner and contractor. | 1. Repeating the same mistake from contractor. |  | 15273 - Action Taken: Plan / arrange regular meeting with contractor on weekly basis to discuss on unclear understanding of the comment in Pedms. 15274 - Recommendation: Consolidator and Lead Engineer should engage in face to face discussions with Contractor to clarify any ambiguous comments or areas. 15275 - Recommendation: To ask contractor proactively discuss with owner if they unclear on the comment in Pedms in order to avoid the same mistake happen. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6352 | Electrical: ITB not clearly define for brownfield interface definition (e.g. interface issue with P3) | 1. Different phase of project (i.e. construction & commissioning). | 1. Potential Schedule impact. 2. Potential cost impact. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2068 | Encounter unexpected subsurface condition (rock) | -lack of information on rock profile | -delay in schedule due to rock blasting activity | -carry out more extensive Soil Investigation (SI) | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Engineering | 6242 | Engineering design mismatch (e.g. civil & mechanical equipment) | 1. Lack of interdiscipline checking on engineering drawing. | 1. Schedule impact to EPCC. 2. Cost impact to EPCC. 3. Rework. |  | 16359 - Action Taken: Rework. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5264 | Engineering design was not completely implemented throughout the fabrication, inspection and installation. | 1. Contractor and PMC inspectors not well versed with Project Specification/ PTS and requirement 2. Found out late and give way to meet project schedule. 3. Lack of quality checker from EPCC prior submission to iPMT. 4. Different competency level of contractor’s engineers. | 1. Technical compliance on Project Specification and PTS 2. Issue was not transparent to PMC/ Owner and not properly recorded. 3. Maintenance issue during operation |  | 14368 - Action Taken: Vendor/ EPCC / PMC Owner to bring forward any queries and to be resolved transparent and quickly. 14369 - Action Taken: Any deviation to PTS & Project specs is properly recorded. 14370 - Action Taken: Communication between PMC - SEG and SEG - vendor need to be clearly recorded 14371 - Action Taken: To develop communication procedure to escalate the info to all relevant personnel to assist in design changes | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2069 | Engineering for Plot plan still at early stage while construction work has been ongoing | -Plot plan not firmed up during construction stage | -Additional work or rework of executed work. -abortive work -Change order and VO | -Early confirmation of design plot plan is required -Replan of construction activity to suit requirement. -To have overall design coordinator (assurance). | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6186 | Engineering overall plot plan shall be shared with sub- vendors to ensure there is no operability and maintainability issues for their package based on the overall plot plan. | 1. In the absence of overall plot plan, sub- vendors are not able to express the constraints on their package as a result of overall plot plan. | 1. When constraints are highlighted during vendor Hazop or Hazid studies, it is difficult to make changes in overall plot plan as engineering / construction is in the advanced stage. |  | 16221 - Action Taken: Project documents shall be shared with the Sub Vendors at the initial stage itself and feedback taken to ensure there is no bottleneck on the vendor packages. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5462 | Engineering Studies & Services (PGTSSB) | 1. Smartcen is not required | 1. Cost dispute with EPCC |  | 14581 - Recommendation: To include Smartcen only if there is a custody meter under CONTRACTORs scope. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5461 | Engineering Studies & Services were deleted during pre-award to provide competitive offer | 1. CONTRACTOR claims that all studies (except 4) were deleted from its scope during the pre-award stage. This has caused prolong dispute and affecting some of the deliverable. | 1. Affecting commencement & completion of engineering deliverables 2. Cost & Schedule dispute with EPCC |  | 14579 - Action Taken: EPCC agreed to conduct all studies except for P-RBI with CMP, P-ELSOR and ESRS 14580 - Recommendation: To include technical persons during the pre-award discussion when involving engineering studies. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5456 | Engineering Studies which already specified in ITB not completed although construction and procurement started | 1. EPCC claimed that some of the studies are not applicable to the project (e.g. reliability study, earthing grid calculation etc.) | 1. Potential issues during commissioning |  | 14570 - Action Taken: Expedited EPCC to complete the studies prior to FAT at Factory for Electrical Equipment | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5605 | Engineering: Inexperience staff deployed by CONTRACTOR. | 1. Inadequate requirements for discipline engineer qualification and experience (other than lead) defined in the ITB. 2. Staff deployed to project upon award was different than the ones proposed during bidding. | 1. Poor quality of deliverables issued by CONTRACTOR. 2. Increased level of effort by OWNER. |  | 14886 - Action Taken: Sought assistance from core engineering. 14887 - Action Taken: OWNER interviewed new candidates proposed for replacement. 14888 - Recommendation: Specify the level of experience requirement for discipline engineer including lead engineer. 14889 - Recommendation: Secure contractor management confirmation for the availability of key staff before award. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5606 | Engineering: Unclear tag closure procedure. | 1. Project specification and memo does not explained on the process of the tag closure. | 1. Unnecessary argument with CONTRACTOR. |  | 14890 - Action Taken: Discussed and agreed the systematic procedure for individual tag closure. 14891 - Recommendation: Improve the procedure to include the individual tag closure during various model review. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5464 | Environmental Specialist is not clearly specified in ITB | 1. The criteria to have Environmental Specialist is only issued through Tender Bulletin, which specified in Sec C - Part II - 11.0. ENVIRONMENTAL MANAGEMENT_rev 1. But the requirement to have Environmental Specialist is not specified in Sec C - Part II - 13.0 KEY PERSONNEL EXPERIENCE REQUIREMENTS_rev 0 | 1. No dedicated competent personnel available to attend any Environmental issue |  | 14583 - Recommendation: The detailed requirement has to be specified at both places of the ITB. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5808 | EO Dispersion. | 1. EO dispersion study was finalized after design completion of IFC P&ID. 2. Revision on piping / instrument / steel structure design occurred. 3. The steel structure and other design was limited to increase of EO discharge elevation at this stage. | 1. No EO > 10wt% dispersion to ATM has not been found in other reference EO/EG processes. EO dispersion usually has little impact on design. 2. Several EO > 10wt% dispersion to ATM is stated in SHELL MASTER process design. EO dispersion has significant impact on design. |  | 15456 - Action Taken: Steam injection system was added to minimize impact on steel structure design. 15457 - Recommendation: Preventive Action. 15458 - Recommendation: Perform EO dispersion study once PSV design is confirmed at early stage. 15459 - Recommendation: Incorporate study results into P&ID before HAZOP. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5811 | EO Reactor Design Information Delay. | 1. Engineering information for EO Reactor such as nozzle orientation, platform plan and piping loadings had been confirmed lately comparing with Vendor’s engineering schedule. | 1. Novation transfer of EO Reactor was delayed for about 2 months. There was no sufficient time to finalize design information within Vendor’s request date. |  | 15467 - Action Taken: Early fixing EO Reactor P/F plan through 30% 3D modeling.Licensor confirmation for piping route in early stage. 15468 - Recommendation: Preventive Action. 15469 - Recommendation: Early Novation Transfer for proper schedule of design information. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | HSSE | 6266 | EPCC argue on local requirement for project | 1. Unfamiliar with local authority requirement. 2. No clear scope to describe the requirement. | 1. Delay on construction activities. |  | 16394 - Action Taken: EPCC to involve in workshop organized by Owner / RAPID. 16395 - Action Taken: Shared on latest SI and HSE program(i.e bulletins, flash, etc). | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5983 | EPCC commissioning team incompetent. Tools used for testing also just a basic tool. | 1. Lack of experience on commissioning team (electrical, mechanical) | 1. Only basic motor condition can be verified. |  | 15813 - Action Taken: Request have be done by Commissioning team to use advance tool for vibration and alignment tool for verification but not done. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5947 | EPCC constructed and install equipment with IFR drawing | 1. Delay in drawing approvals/revision due to ongoing comments 2. Late incorporating comments in the drawing | 1. Reworks 2. Huge amount of punch list |  | 15751 - Action Taken: Face to face discussion to speed the process/approval (offline approval) 15752 - Recommendation: Adherence to no construction to non-drawing approval | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Planning | 5286 | EPCC Contractor have only one DPR focal person and no back-up | 1. Inconsistency of Daily Progress Report (DPR) submission to iPMT | 1. Delay in submission of DPR to iPMT when the focal person is away from site |  | 14405 - Action Taken: EPCC Contractor to have workable backup plan for key personnel at working level and ensure proper handover | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5941 | EPCC CONTRACTOR shall follow internal Interdisciplinary Checking for those Instrument Drawings and Documents which need to be reviewed and commented by other disciplines of the EPCC CONTRACTOR. | 1. EPCC CONTRACTOR did not follow any documented and demon tractable Interdisciplinary Checking of Instrument Drawings / Documents. | 1. There were many inconsistencies between different Instrument Drawings/Documents and other discipline drawings / documents, as there were no Interdisciplinary Check performed by concerned disciplines. Examples: a) Details shown on HSE-F&G Drawings Vs. Inst.-F&G Drawings b) Data shown on Pressure Gauges Datasheets Vs. Line List Data c) DCS-VSDs and DCS-HV Motors redundant communication requirements. |  | 15737 - Action Taken: PMC-Instrument reviewed these Instrument drawings and documents with respect to other discipline drawings and documents and commented on the Instrument drawings and documents for EPCC CONTRACTOR to review and revise 15738 - Recommendation: EPCC CONTRACTOR shall follow quality control system which shall include demon tractable Interdisciplinary Check records. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5942 | EPCC CONTRACTOR shall use the drawings / documents prepared by them to follow and use them as basis for their own engineering, instead of treating those as if they have no relevance. | 1. There were many inconsistencies between CONTRACTORs requirements as per their own drawings and documents and what had been actually followed by CONTRACTOR during detailed engineering. Examples: a) Numbering Specification requirements. b) Cable Specification requirements (FGS-Core Vs. Pair Cables, Fire Resistance Vs. Fire Retardant). | 1. There were many instances that the EPCC CONTRACTOR had not followed their own Drawings and Documents resulting in inconsistencies and deviations. |  | 15739 - Action Taken: Inconsistencies were pointed out to the EPCC CONTRACTOR by Comments / Punches and requested for rectifications / resolutions. 15740 - Recommendation: EPCC CONTRACTOR shall use the drawings / documents prepared by them to follow and use them as basis for their own engineering. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5938 | EPCC CONTRACTOR should prepare and submit Instrument documents (Specification, Datasheets, & Material Requisition) with adequate details and quality, so that the same are reviewed / approved before placing the PO on the Instrument Vendors. | 1. Purchase Orders (POs) were placed by EPCC CONTRACTOR without obtaining appropriate approval of the Instrument documents. | 1. As the POs were placed based on preliminary Instrument Documents which were not defining the requirements clearly, later stage when revised Instrument documents were provided to the Vendors, there were issues / arguments on meeting the requirements resulting in controversies and associated delays. |  | 15730 - Action Taken: Conducted meeting with EPCC CONTRACTOR / Vendors to explain project requirements and to find way forward. 15731 - Recommendation: EPCC CONTRACTOR should have prepared Instrument Documents with adequate details and requirements, before placing POs. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5939 | EPCC CONTRACTOR should prepare and submit Technical Bid Evaluation with adequate details and quality, so that the same are reviewed / approved before placing the PO on the Instrument Vendors. | 1. As the POs were placed by EPCC CONTRACTOR without preparing TBE, EPCC CONTRACTOR took this process very lightly and not even bother to prepare proper quality Instrument Documents defining the requirements clearly and also did not meet the conditions given in Management letter. Hence, at later stage when revised Instrument documents were provided to the Vendors, there were issues / arguments and associated delays. | 1. Project Management had provided a specific exclusion to this EPCC CONTRACTOR to proceed with placing PO without waiting for review / approval of Technical Bid Evaluation (TBE) with specific conditions to be met by EPCC CONTRACTOR, in order to save time associated with the same. |  | 15732 - Action Taken: Conducted meeting with EPCC CONTRACTOR / Vendors to explain project requirements and to find way forward. 15733 - Recommendation: EPCC CONTRACTOR should take care of the conditions given in Management Letter when the concession regarding TBE-Approval was provided to EPCC CONTRACTOR. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5937 | EPCC CONTRACTORs Engineers who are actually experienced in Instrument Engineering and also familiar with use of Software for Instrument Engineering Deliverables to work on the project. | 1. Engineers who were not experienced enough in Instrument Engineering and also not familiar with Software (Smart Plant Instrumentation (SPI)) are working on the Instrument Engineering deliverables. | 1. EPCC CONTRACTOR did not complete the SPI-Instrument deliverables on time. Hence, the inputs were provided to Vendors in different formats and the changes were not tracked properly resulting in many inconsistencies, non-compliance and poor quality. Examples: a) Instruments procured using documents which were not produced from SPI. b) SPI: I/O Lists, Datasheets, Loop Drawings, Hook-up drawings, etc., were not prepared and not provided on time. |  | 15728 - Action Taken: Followed up with EPCC CONTRACTOR many times. 15729 - Recommendation: EPCC CONTRACTORs Organization Chart should have specifically included SPI Administrator position.CVs of SPI Administrator and users should have been provided by EPCC CONTRACTOR for review and approval before PO. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5940 | EPCC CONTRACTORs Lead Instrument Engineer to work at their Base Engineering office during peak Engineering phase, in order to lead the project. | 1. EPCC CONTRACTORs Lead Instrument Engineer was not available at their Base Engineering office continuously for about eight (8) months during peak engineering phase. This was due to his full time participation in DCS/ESD/FGS FAT at YKM-Puchong. | 1. PMC Instrument efforts to expedite engineering drawings / documents review comments close out and other issues by means of meeting / discussion as directed by Project Management could not be fully executed as EPCC CONTRACTORs Lead Instrument Engineer was not available for long duration. |  | 15734 - Action Taken: PMC-Instrument interacted directly with other Junior Instrument engineers in EPCC CONTRACTORs Base Engineering office in order to expedite review comment resolutions and other engineering issues, to the extent possible. 15735 - Recommendation: EPCC CONTRACTOR shall consider dedicated System engineers for DCS/ESD/FGS design and engineering so that the same engineers can take care of FAT also. 15736 - Recommendation: EPCC CONTRACTORs Lead Inst. Engineer shall not be involved full time in FAT activities for longer period which affects his main lead responsibilities. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5980 | EPCC failed to comply with correct phase rotation for most of the power distribution board due to wrong termination at power feeders | 1. EPCC not understand/following the project requirement/specification. 2. Project team failed to identify during construction/pre-com stage | 1. Confusion in future operators 2. Future extension projects also will be impacted |  | 15810 - Action Taken: SR already raised. Few discussions have been made with LLWT and PMC. Issue closed | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5978 | EPCC failed to comply with motor efficiency requirement. Got motor installed with IE1 efficiency. Project specification calls for minimum IE2 | 1. EPCC not understand/following the project requirement/specification. | 1. Power consumption higher. Lead to high power usage |  | 15808 - Action Taken: OPERATION is still under round check to get the total number of non-complying motor. PMC to advice on the way forward | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5981 | EPCC failed to comply with motor protection requirement (thermistor) for all their VSD motors | 1. EPCC not understand/following the project requirement/specification. 2. Project team failed to identify during construction/pre-com stage/FAT | 1. Motor protection not as per project specification |  | 15811 - Action Taken: SR already raised. Few discussions have been made with LLWT and PMC. Still pending closure | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5979 | EPCC failed to comply with power cable requirement for MOV | 1. EPCC not understand/following the project requirement/specification. | 1. Power cable are without steel wire armored (SWA) |  | 15809 - Action Taken: SR already raised. Few discussions have been made with LLWT and PMC. Still pending closure | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5972 | EPCC failed to comply with project requirement on ELR requirement for all motors. Only motor 30KW and above are installed with ELR and ZCT | 1. EPCC not understand the project requirement/specification. 2. EPCC failed to understand ITB requirement 3. EPCC failed do understand Electrical ESRR findings 4. Project team failed to identify during construction/pre-com/FAT | 1. No Earth Leakage protection for the said motor. Hazard to human |  | 15802 - Action Taken: SR already raised. Few discussions have been made with LLWT and PMC. Still pending closure | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5976 | EPCC failed to conduct protection coordination from UPS until the end load. MCCB sizing not properly coordinated | 1. EPCC not understand/following the project requirement/specification. | 1. No proper protection coordination. Upstream breaker will trip first rather than downstream breaker |  | 15806 - Action Taken: Few discussions have been made with LLWT and PMC. Still pending closure | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5977 | EPCC failed to distribute duty and standby loads at distribution panel | 1. EPCC not understand/following the project requirement/specification. | 1. Load are not properly segregated. Bus fault will lead to plant shutdown |  | 15807 - Action Taken: Few discussions have been made with LLWT and PMC. Still pending agreement between OWNER and PMC | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5957 | EPCC has constructed and installed certain equipment not based on approved drawing |  |  |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Project Management | 5412 | EPCC lack of awareness of the current regulatory procedures (i.e. DOSH, DOE, etc.). | 1. Incompetent local advisor. | 1. Delay in getting approval from regulatory bodies. 2. Potential stop work order. |  | 14476 - Action Taken: Brought in 3rd party consultant who is familiar with local authority requirements. 14477 - Recommendation: Proper review of personnel competency by iPMT prior to mobilization. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Procurement | 6365 | EPCC Late PO issuance | 1. Too many people (10-15) to review prior the approval. 2. Late decision from CMI management | 1. Impacted Engineering IFC. 2. Delay construction. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5965 | EPCC not conducting comprehensive inspection during pre-com | 1. Alignment is check during FAT but not verify after installation | 1. Delay on CS closure due to rectification in progress Few machinery (pump, blower etc.) failed due to high vibration cause by wrong alignment |  | 15792 - Action Taken: Call respective OEM to check the alignment and rectify the problem. Recommend to put alignment verification step in CS B 15793 - Recommendation: To verify equipment alignment at site after equipment installed | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Project Management | 6358 | EPCC not fully understand local requirement | 1. Stringent local government requirement (e.g. COA etc.). | 1. Material delivery |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5245 | Equipment dress up late in schedule for platform, insulation installation | 1. Manpower not sufficient and being moved around 2. No dedicated manpower for mechanical dress up , need to borrow from other discipline | 1. Equipment dress up late in schedule |  | 14338 - Action Taken: To have dedicated manpower for mechanical discipline and not share with steel structure to ensure meet deadline 14339 - Action Taken: To ensure early mobilization as per plan | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5242 | Equipment installation at site wrong orientation and cause delay in installation | 1. Both parties not confirm with Orientation until arrival at site 2. Miscommunication between EPCC and sub-con 3. Lack of competency by sub-con 4. Lack of supervision by EPCC | 1. Late installation for one day |  | 14334 - Action Taken: To do site visit between logistic and construction team at least one day before equipment installation 14335 - Action Taken: To do proper planning ahead of installation | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6091 | Equipment load chart wrongly estimated | 1. Complexity of the job and contractor inexperienced with the specialist work | 1. Work Progress and cost |  | 15569 - Recommendation: To engage experienced Project Manager or Construction Manager 15570 - Recommendation: To appoint competent subcontractor | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5265 | Equipment Painting: Different parts of equipment have different final coat depending on Contractors interpretation of the painting spec. | 1. The painting spec is open to interpretation when it comes to packages. Equipment coming under packages could be interpreted as following the main equipment painting | 1. Non-uniformity on painting for packaged equipment (i.e. white PV and static equipment vs green PV and static equipment within package) |  | 14372 - Action Taken: To clearly state the final color in the spec, whether it follows main equipment. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Procurement | 5407 | Equipment supplier does not agree in providing additional support beyond their contractual obligations after their equipment failed during shop testing e.g. sun dyne compressor. | 1. The cost for the additional support is not in their scope of work. | 1. After the warranty period, OWNER has to spend additional cost to rectify the faulty equipment. 2. Potential quality issue. |  | 14462 - Action Taken: Negotiating with EPCC on the additional support. 14463 - Recommendation: To consider putting condition for troublesome / problematic equipment before accepting test result. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5810 | ESD valve for Chiller Package. | 1. Additional ESD valves required for isolation of low pressure (LP) steam and cooling water (CW) to Chiller Package. | 1. No ESD valve requirement for Chiller Package in other reference EO/EG processes. 2. Chiller Package vendor did not clarify ESD valve requirement during bidding stage. 3. Refrigerant (LiBr) crystallizes under abnormal operating conditions. 4. Chiller Package for RAPID #11 process operates near crystallization curve. |  | 15465 - Recommendation: Preventive Action. 15466 - Recommendation: Confirm with vendor about ESD valve requirement during bidding stage to prevent unexpected impact. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5926 | Exhaust fan in battery room shall be continued running when hydrogen gas is detected, in order to dilute the hydrogen gas released from the batteries. Also, exhaust fan shall be designed with N+1 configuration. | 1. The design is in such a way that the exhaust fan is stopped when hydrogen gas is detected. Also, exhaust fan is not designed with parallel redundancy. | 1. Hydrogen gas is a highly flammable gas. If exhaust fan stopped when hydrogen gas is detected, explosion can occur when the explosive limit of hydrogen gas is reached. Hence, exhaust fan has to be running to dilute the hydrogen gas. |  | 15708 - Action Taken: Contractor shall re-design to ensure exhaust fan is running when hydrogen gas is detected. 15709 - Recommendation: Exhaust fan shall be designed with parallel redundancy configuration for safety reason. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5936 | Experienced Instrument Lead Engineer and Senior Instrument Engineers assignment for the Project. | 1. Lead Instrument Engineer who had no appropriate experience in leading a project was assigned as Lead Inst. Engineer. 2. There was no Senior Instrument Engineer with relevant experience assigned for the project. | 1. Timely inputs to Vendors were not provided as Instrument Team did not have any clue on what are the inputs to be provided, resulted in delays and poor quality Engineering. |  | 15726 - Action Taken: Engineering Management placed a PMC-Instrument Engineer at EPCC CONTRACTORs Engineering office for easy access by EPCC CONTRACTOR and quick resolution of issues. 15727 - Recommendation: Dedicated and experienced Instrument Lead Engineer and Senior Instrument Engineers assignment shall be confirmed before the PO is placed on an EPCC CONTRACTOR. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5088 | Extended MVL not reviewed by PMC technical team prior to the approval. | 1. Uncontrolled additional of vendor to MVL | 1. Technical aspect of extended MVL vendor is not properly evaluated 2. Late closure of deviation. |  | 14161 - Some of the vendor inside the MVL not get the RFQ from EPCC. 14162 - To ensure all the MVL get the RFQ from EPCC before proceeding with additional vendor to MVL. 14163 - To ensure technical team is involved in the extended vendor evaluation process. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Procurement | 5119 | Extended Vendor List (EVL) takes longer time | 1. MVL not comprehensive 2. Missing items/parts/equipments in MVL list 3. Prefered vendors by EPCC (not in MVL) 4. Extended vendor takes longer time due to unfamiliarity of the PTS requirements | 1. EPCC to source other vendors (EVL) which takes longer time |  | 14234 - Action Item: EPCC find another approved vendors to supply the items 14235 - Action Item: Intervention by Core Engineering team in KL to endorsed new vendors 14236 - Recommendation: To revised the MVL by including the missing items and new approved vendors 14237 - Recommendation: To minimize time taken for Approval procedure/process in extending the vendor list | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Interface | 6263 | Extra workload carried by PMT, PMT covering interface scope | 1. EPCC refuse to fully involve on interface scope. 2. System IPMS barrier. 3. Non standard scope by JV. | 1. ICTS backlog and late reporting. |  | 16390 - Action Taken: Owner engaged CD interface and coordinate work with EPCC. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | HSSE | 6268 | Extra workload for HSE management and site monitoring | 1. Lean org structure (1 HSE mgr only). | 1. HSE impact. |  | 16399 - Action Taken: Additional HSE supervisor for the project. 16400 - Recommendation: Follow HSE guideline on HSE manpower requirement. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5617 | Extruder packages (especially those under storage colour code - GREEN) are not stored in an enclosed premises as stated in manufacturers Long Term Storage & Rust Preventing Procedure at Site. | 1. All extruder packages regardless of storage colour code either GREEN or BLUE, are stored at open laydown. 2. CONTRACTOR delayed in submitting Material Handling, Storing & Preservation document to the Owner. | 1. Equipment may be exposed to extreme weather condition and damage. |  | 14916 - Action Taken: Advised CONTRACTOR to relocate the extruder packages into an enclosed premises, reviewing the Material Handling, Storing & Preservation document and comply to the prerequisite of the delivery. 14917 - Recommendation: To enhance ITB which request vendor to submit Preservation Procedure 1 month before shipment for Site to make necessary preparation. 14918 - Recommendation: Material Handling, Storing & Preservation document to be reviewed prior consignment arrive at site. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5742 | Eye wash in Battery Room for VRLA / Non Acidic Type: Eye wash requirement in battery room for vented type battery. | 1. Misinterpretation of HSE requirement for VRLA type battery. Thus the contractor did not provide eye wash in the battery room. | 1. This has caused different interpretation between the CONTRACTOR, OWNER, discipline i.e. Civil, Electrical, HSE. 2. Late engineering freeze. 3. There is still potential of acid leakage / exposure during the maintenance / replacement that can harm the personnel working on it. |  | 15309 - Action Taken: CONTRACTOR provide portable eyewash with individual water collection system. 15310 - Recommendation: Specification to be updated and to clearly indicate the requirement of eye-wash although for VRLA type battery. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Project Management | 6248 | Facilitation fund from Government UKAS (Unit Kerjasama Awam Swasta) | 1. Criteria for eligibility to apply i.e. green field project, project of National intrest etc. |  |  | 16367 - Recommendation: To check if eligible to apply for facilitation fund prior to to project sanction. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5943 | Factory Acceptance Testing (FAT) for DCS/ESD/FGS shall be taken up only after the required inputs are provided to the System Vendor and associated System configuration is completed along with associated completion of the Internal System Testing. | 1. EPCC CONTRACTOR organized the FAT for DCS/ESD/FGS even before all the required inputs were provided to the System Vendor and before associated System configuration is completed by System Vendor and before Internal System Testing work is completed by System Vendor. | 1. DCS / ESD / FGS FAT was not conclusive and prolonged for eight (8) months, though FAT was planned to be completed in eight (8) weeks, as the EPCC CONTRACTOR kept on providing additional and revised inputs. |  | 15741 - Action Taken: PMC-Instrument provided additional man-power and worked long hours to expedite the FAT completion at System Vendor Factory - YKM Puchong. 15742 - Recommendation: EPCC CONTRACTOR shall provide all the required inputs to the System Vendor and associated System configuration shall be completed along with associated Internal System Completion before the start of FAT. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5944 | Factory Acceptance Testing (FAT) Punches are to be closed at Factory before end of FAT and before dispatch of the DCS/ESD/FGS components to site. | 1. EPCC CONTRACTOR / System Vendor could not close all the FAT-Punches at Factory and decided to transfer about 874 nos. of FAT Punches to site, for closure at site. | 1. Due to very many activities at Site (Pre-commissioning, Commissioning, Start-up, etc.), EPCC CONTRACTOR and System Vendor resources are occupied and the FAT Punches are not fully closed. |  | 15743 - Action Taken: PMC-Management mobilized PMC-Instrument to site in order to oversee closure of DCS/ESD/FGS FAT Punches. As on 11 Sept. 2017, 753 nos. FAT-punches were closed at site and 121 nos. Punches are still open and yet to be closed. 15744 - Recommendation: EPCC CONTRACTOR / System Vendor shall ensure that all the FAT Punches are closed at Factory itself as required per Project Documents. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Engineering | 6041 | Failure of Plot C outfall after only a few months of completion. | 1. Inadequate design. 2. SI was not done, and lack of survey data. 3. Soft ground condition, easily scoured due to water action. | 1. Had to rework / redesign twice. 2. Cost impact to Owner. 3. Delay in impoundment activities. |  | 15602 - Action Taken: Rework (twice). 15603 - Action Taken: Treat outfall as a mega main structure so proper attention is given to its design. 15604 - Action Taken: Have proper review | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5768 | FEED construction execution plan not developed: Limited generic constructability review was done. | 1. Lack of SOW for construction strategy / constructability in FEED. | 1. The absence of a solid construction execution strategy, with progress objectives at FEED phase and EPCC award was a significant deficiency. |  | 15376 - Recommendation: The Construction Execution Strategy should be made a deliverable as part of the FEED SOW. 15377 - Recommendation: This deliverable should be finalized based on resolute technical definition, scope and project schedule that effectively reflect the estimated work volume / MTO. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Engineering | 5532 | FEED cost estimate requirement was not defined clearly in the FEED deliverables. | 1. Cost estimate methodology was not clearly stated in the FEED deliverables. | 1. Extended activities for the cost estimate |  | 14699 - Action Taken: Cost estimate requirement defined with Owner 14700 - Action Taken: Bulk MTO was performed key equipment requisition issued to obtain pricing from vendor. 14701 - Recommendation: To ensure cost estimate requirement clearly stated in the FEED deliverables. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5767 | FEED estimate: MTO not available as a deliverable, only adjusted / factored costs. | 1. FEED SOW not detailed enough. | 1. Lack benchmark when evaluating the quantities, resources and cost in bid proposal. |  | 15374 - Action Taken: This was mitigated by PMC Cost Estimation to fill essential gaps 15375 - Recommendation: Representative quantities / MTOs should be developed for effective tender evaluation. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5765 | FEED lack of definition: Lack in-depth in FEED on process ISBL. | 1. Control of FEED cost was given too high priority compared to project definition. 2. Too many changes. 3. Scope not detailed enough. |  |  | 15370 - Action Taken: Debottle necking done licensor and simulation studies done with contractor. 15371 - Action Taken: Add 5% extra margin in equipment design. 15372 - Recommendation: More importance should be given to the project scope definition at FEED stage. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5766 | FEED schedule: No level 3 or even level 2 schedule and no resource estimates. | 1. FEED SOW not detailed enough. | 1. Lack benchmark when evaluating the schedule in bid proposal. 2. Lack of guidance for bidders to prepare schedule in bid proposal. |  | 15373 - Recommendation: To ensure FEED Contractor develops a resource loaded Level 3 schedule, inclusive of labour curves as part of their SOW. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6080 | FEED was not done prior to package award | 1. Time constraint | 1. More adjustment work to be done during the package proceeding 2. Time and Cost impact due to change in work scope |  | 15547 - Recommendation: It is advisable to carry out FEED study before EPCC contract is awarded | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5770 | FEED: Late re-FEED design changes due to cancelation of other projects. | 1. FEL2 and FEL3 were implemented concurrently due to fast track implementation strategy adopted for the RAPID Project. | 1. Materials balance keep on changing and affected on scope definition of programs. |  | 15380 - Recommendation: To implement the FEL2 gate review very stringently. 15381 - Recommendation: FEL2 should provide options of configuration variations to enable selection of the most optimum. 15382 - Recommendation: Sometime should be allocated for Commercial Team to provide their inputs before the proceeding to the next gate. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Award/Contract | 5656 | FEL Stage: CHANGE MANAGEMENT: For Change Order process cycle, upon submission of CONTRACTORs Change Proposal is not properly guided. | 1. No proper guideline for change order approval since FEL stage. | 1. Due to urgency to close the Change Order subject, PD&T participation was delayed or was done after the fact, leading to governance issues with the Change Order process. |  | 15024 - Action Taken: PD&T would be engaged upon receipt of Change Proposal from CONTRACTOR. 15025 - Recommendation: By early engagement of PD&T team, sufficient time can be used to solicit assessment of PD&T team to support PMT paper to the Approving Authority. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Quality | 5652 | FEL stage: Construction forms was not in line with UPT developed System Handover Procedure & System Definition Procedure. | 1. Project Quality Management Systems-(Quality Planning activities) for UPT / PMT are not in place since FEL stage. | 1. Theres effort to make thing right or standardize but was been left without deep consideration by respective party. 2. Construction form was not been named as Quality Control Form (QCF) as per procedure instead only using Inspection Test Procedure (ITP) form. |  | 15013 - Action Taken: First initiation to highlight this concern has been made at site for further QAQC team and Commissioning team consideration and understanding with several emails discussion & reminder. 15014 - Action Taken: Further discussion need to be done and to finalize the way forward to reduce impact to current document issued which having risk for re-work. 15015 - Recommendation: All Quality form for Construction shall be following Pre-Comm & Commissioning for ease of handover process where continuity of system / sub-system information is referable from one step to another. 15016 - Recommendation: To provide a guideline on the on the Testing requirement for pre-comm & comm. Stage in order to have better plan and smooth documentation transfer between construction and commissioning. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5619 | FEL Stage: Miscommunication with few key stakeholders between CONTRACTOR, Consultant and Regulatory Authorities. | 1. Lack of communication procedures between CONTRACTOR, Consultants and Regulatory Authorities. | 1. Missing important information. 2. New regulation imposed by regulatory was not clearly cascade down to the project and contractor level. |  | 14922 - Action Taken: Conducted a regular meetings and engagement with various key Stakeholders. 14923 - Recommendation: To improve and / or establish the Communication Stakeholders Management. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Quality | 5647 | FEL stage: Project Quality Management Systems-(Quality Planning activities) for UPT / PMT are not in place since FEL stage. | 1. Project Quality Manager was recruited 6 months after project awarded to EPCC. 2. This has affected in slow strategizing of project quality implementation. | 1. Standardization of Project Mgt. activities can only be initialized during execution. 2. Delay in progress of reviewing EPCC procedures via PEDMS. 3. Affected the smoothness of Project Quality Implementation. |  | 14994 - Action Taken: Had advised new project team during PIR ITB that PMT Quality Manager must be enrolled at the beginning of Execution. 14995 - Recommendation: To plan for early mobilization of PQM for the projects together with other projects key personnel. 14996 - Recommendation: Must be implemented immediately for all PETRONAS future Projects. 14997 - Recommendation: Project Quality Management Systems-(Quality Planning activities) for UPT / PMT need to be established at the very beginning of project. (during FEL stage). | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5741 | Fence Material for Substation Cable Cellar and Yards: Fence design for substation (i.e. cable cellar and gate). | 1. Insufficient specific design details; made available after enquiry by UPT. 2. Issue was raised during ELSOR that required the fence to have features in resisting debris from explosion. Higher strength fence to be provided to reduce the risk. | 1. CONTRACTOR designed the fence for the cable cellar and yards, the same like the fence for plants / plots boundary, hence, requiring rework. 2. Potential claim by contractor. |  | 15307 - Action Taken: Central Engineering issued Job Bulletin specs out the requirement and to standardize the fence design for the substation. 15308 - Recommendation: Specification to be updated. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6181 | Few of deliverables are interdisciplinary dependent and share of ownership which has created prolong delay as other discipline is still holding the data, thus deliverable submission is affected. | 1. Detailed MDR was not properly finalized between disciplines 2. Deliverable Segregation. Few of deliverables are share of ownership between YKM & MIE which has created prolong delay as other party is still holding the data, thus deliverable submission is affected. 3. Gap in coordination between discipline and scope | 1. Early information need to be passed to P22 regarding the arrangement and loading of structure and equipment skid 2. Some equipment was not confirmed and lead to many revision of drawings and double works. 3. Required more manhours to revisit and update engineering documents. 4. Detailed discussion on MDR was not properly in place between YKM & MIE, as most of the discussion are too related with commercial during the initial stage. 5. Few doc not updated and need another series of review |  | 16205 - Action Taken: Alignment session was conducted to ensure MDR finalization and scope content of documents is achieved. 16206 - Action Taken: Discussion on MDR shall be strictly convened at the beginning of the project so as to reduce the magnitude of work & any redundancy can be eliminated. 16207 - Action Taken: Clear work demarcation & alignment shall be realized and agreed by all parties with everything is in order starting from ENG, PMT, PRC, CON team. 16208 - Action Taken: Proceed with such alignment as per direction from YKMs PM 16209 - Action Taken: Coordination meeting between discipline, and update of all changes during the meeting. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6018 | Fibre optics cables, has to be spliced and tested (OTDR) while the underground cable trench is still open. | 1. Fiber optics cables has high data loss in the OTDR test reports. | 1. Fiber optics cables were only tested after backfilling the trenches. |  | 15874 - Action Taken: New fiber optics cables to be repulled 15875 - Recommendation: The cables can be tested while the trenches are still open so that if there is high loss, a new cable can be repulled. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Project Management | 5110 | Filling in CRS during the implementation of POL system | 1. OWNER requirements | 1. Taking too much time and effort in completing the CRS instead of reviewing the documents |  | 14214 - Recommendation: CRS shall be completed by EPCC instead of OWNER | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5484 | Final discount (removing piling scope due to geotechnical condition finding from Soil Report Assessment) given by the bidder during pre-award was not fully technically verified/reviewed by the SME | 1. CONTRACTOR disputes that the current soil condition is not the same with soil condition as per FEED. 2. OWNER commitment to provide good compaction soil (N=7 or more) but in actual it is not (despite the document was issued after award). 3. Site prep was conducted but was not compacted as per N=7 or more. 4. Discrepancy of geotechnical condition from FEED data and replicated EPCCs Soil Investigation after award. | 1. Previously, piling scope was removed from the EPCC scope 2. Changed order |  | 14612 - Recommendation: To reinforce the clauses in the Contract in favor of OWNER. 14613 - Recommendation: Contractor should be responsible to conduct their own SI and not fully reliance on OWNER provided data. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Document Management | 6322 | Final documentation(as built) unable to be submitted on time | 1. Late compilation | 1. Unable to Handover |  | 16503 - Action Taken: Meeting and routine follow up, auding on contractor work 16504 - Recommendation: Contractor should set up the document handling over team, in earlier stage of the project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5397 | Finalization of design blast pressure for blast proof / resilient buildings pending on detailed OWNER QRA Report. | 1. Detailed QRA assessment was delayed. | 1. Potential risk arise when Contractor proceed on their design based on individual assessment of design blast pressure. |  | 14445 - Recommendation: Early finalization of FEED QRA related to blast pressure for major structures prior to commencement of EPCC package. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Procurement | 5115 | Fire incident during transportation of equipment | 1. Non-compliance to SOP by the operator 2. Improper logistic arrangement form MOLF to laydown area | 1. Potential schedule delay and equipment repair 2. Potential cost impact on repair works |  | 14223 - Action Taken: Ongoing. Expedite on the replacement of affected equipment. 14224 - Action Taken: Immediate suspension of the transport operator and new appointment of alternate operator (Tiong Nam) 14225 - Recommendation: To take extra precautions on the procedures and SOP. 14226 - Recommendation: OWNER to ensure all critical items are being escorted during the transportation | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5502 | Fire proofing enclosure for On / Off Valve in fire zone | 1. Malfunction due to exposure to environment/ whether conditions. | 1. Shorter design life from the 20 years RAPID Complex life span. 2. May not have enough protection in case of fire. |  | 14638 - Action Taken: Accepted FR jacket enclosure since metal enclosure is not clearly specified in the project requirement. 14639 - Recommendation: Metal enclosure requirement shall be clearly specified in the ITB. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5503 | Fire Water Line Design Temperature of 75 deg. | 1. Over designed in FEED. | 1. Unnecessary expense (higher cost) due to over design. |  | 14640 - Action Taken: Design temperature has been reduced to 38 deg, aligned with OUI-JV fire water design temperature. 14641 - Recommendation: To consider lower fire water design temperature, especially if the line runs underground. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Interface | 6027 | Fire water underground piping damaged during excavation work | 1. Joint survey was not conducted between P14 and P16B | 1. Asset damage |  | 15892 - Action Taken: Do permanent repair | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Undefined | 5999 | Firm MTO not available for effective monitoring and control. | 1. Basis of measurement was not aligned. 2. Disputes on quantities continue during construction between PMC and Contractor. | 1. Delay in finalizing commodity tracking report. 2. Delay in finalizing manpower requirement. |  | 15839 - Action Taken: Joint discussion between PMC and Contractor held. 15840 - Action Taken: Preliminary quantities of key commodities to be submitted by Bidder during bidding stage. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6182 | Flow of deliverables submission are bit unrealistic | 1. Flow of deliverables submission are bit unrealistic, which resulting re-verification need to be done prior next issuance i.e. submission of MR while Specification is still in IFR stage. 2. Long lead items/equipment are late to resolve on all technical requirement which has impacted the equipments ETD. | 1. Intense pursuit of goals to reach certain project progress and milestones at earliest, supposed not to deter the engineering work to be carefully design with various input/design consideration |  | 16210 - Recommendation: A comprehensive strategy plan in identifying the criticality of equipment which favor an intense focus, shall be review by all parties prior implementation. 16211 - Recommendation: Discussed and agreed with PRPC, such MR may submitted once IFA of specification is achieved | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Construction | 5705 | Formwork Design: Insufficient diagonal support of formwork during concreting. | 1. Failure to submit formwork calculation prior concreting. | 1. One of the foundations side formwork failed during concreting. |  | 15221 - Action Taken: Collapsed concrete removed. 15222 - Action Taken: Additional diagonal supports provided. 15223 - Action Taken: Investigation concluded that insufficient diagonal supports were provided. 15224 - Recommendation: Subcontractor shall submit calculation and typical formwork detail to Main Contractor for review and approval. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6172 | Foundation engineering design and construction involved interfaces with other package (P22) which already ahead in schedule whom responsible for the design and construction - Front work | 1. Design engineering and construction of foundation is included in P22s contract 2. Award timing not inline between P22 and P32 3. Frequent changes plot plan review 4. Limited information during early stage of the project | 1. Early information need to be passed to P22 regarding the arrangement and loading of structure and equipment skid 2. Some equipment was not confirmed and lead to many revision of drawings and double works. 3. Frequent changes plot plan review 4. Limited information during early stage of the project |  | 16172 - Action Taken: Submitted preliminary Loading Data for Foundation Design to P22 for information and coordinate with P22 on the changes. 16173 - Action Taken: Over estimation of foundation sizing to cater for uncertainties in equipment size. 16174 - Action Taken: Proposed chemical bolting method and pocket for anchor bolts for unconfirmed equipment 16175 - Action Taken: Owner take out scope from P22 16176 - Action Taken: Align timeframe with P22 16177 - Action Taken: Few sessions of internal plot plan review has been done 16178 - Action Taken: Work closely with Piping discipline to produce overall 3D model 16179 - Recommendation: To ensure that the schedule of interfaces is in line and more sensible for smooth progress of work. 16180 - Recommendation: To improve on overall progress planning inter-discipline to suit the interface schedule 16181 - Recommendation: Early award to consider interface issue - working in brownfield area 16182 - Recommendation: To conduct schedule internal meeting for better coordination between all discipline | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5267 | Foundation: Foundation of pumps hacked too much. | 1. Chipping using incorrect tools | 1. Higher grouting thickness |  | 14374 - Action Taken: Monitor chipping process and mechanical to be involved in acceptance of foundation. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B2-MOLF RAMUNIA | IO-P20B2-MOLF RAMUNIA | Construction | 6094 | Frequent Breakdown of Construction equipment | 1. Contractors marine equipment are not at tip top conditions for such a fast track project | 1. Low productivity and slow work progress |  | 15514 - Action Taken: Requested Contractor to have regular inspection and services of the equipment 15515 - Action Taken: Requested to have full time maintenance team on site 15516 - Recommendation: Recommend to provide additional equipment for standby 15517 - Recommendation: Recommend to provide good working condition equipment 15518 - Recommendation: Recommend project team to carry out pre-mobilization inspection | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Project Management | 6361 | Frequent change of Sub Contracting strategy / PO | 1. Cost driven. | 1. Schedule impact. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Planning | 5283 | Frequent changes in Construction quantity resulting in inaccurate project planning and progress reporting | 1. EPCC Contractor Engineering team and material control lacks the experience in estimating construction quantities. 2. EPCC Contractor has poor communication between engineering, procurement and construction in verifying the quantities and materials purchased. | 1. Project control team is required to frequently update and change the construction quantities causing inaccurate schedule and manpower planning and further causing confusion to the construction team. |  | 14399 - Action Taken: iPMT and EPCC Contractor Project Control team stepped in to coordinate the changes in construction quantities. 14400 - Action Taken: EPCC Contractor to engage quantity surveyor to estimate quantities and materials required. 14401 - Action Taken: Engaged construction subcontractor to verify quantities and material purchased. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Project Management | 5534 | Frequent clarification from EPC, bidders on cooling tower effluent specification | 1. Discrepancies in reference ITB on effluent specification. | 1. Numerous clarification |  | 14704 - Action Taken: Rectified discrepancies during technical clarification phase. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6174 | Frequent design changes | 1. Many comments on design changes related to P&ID at the end of the project 2. Short of focal person related to engineering e.g P&ID, specifications, 3. Design elements were not available at the time when other interface points have already progressed 4. Changes from other discipline were realized last minute in later stage of design 5. Input and basis given by client for calculation are not fixed. Thus, calculation need to be uprev. Several times. 6. Portable fire extinguisher rating for outdoor specified by P32 contractor done based on the Project Specification. 7. Design or Data Changes. Numerous design Comments/changes were not received within the planned baseline | 1. Causes document delay 2. Additional manhours spent to revise the approved document. No impact in cost since equipment is still not being purchased. 3. Abrupt changes of data/information caused quite significant delay in overall deliverables |  | 16185 - Action Taken: Frequent face to face session with epcc to minimize changes 16186 - Action Taken: Contractor was requested to revise the specification and layout related to fire fighting equipment. PMT shared a PDR raised by another package Contractor related to this request. 16187 - Action Taken: Improvement in overall design data / changes management. 16188 - Recommendation: Empower PM/PD 16189 - Recommendation: Frequent face to face interface meetings among packages | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | HSSE | 6269 | Gap on HSE implementation at early project stage (pre-award) | 1. Late appointment of HSE personnel. | 1. Delay in kick-off, setting up HSE site requirement. |  | 16401 - Action Taken: HSE scope covered by discipline engineer. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5201 | Geographical Limits & Interfacing. | 1. In some cases, there are many interfacing required even within the same package / unit. For e.g. in FOS, interfacing involved: P3-P2; P2-P14; P14-P3. | 1. Interfacing requiring alignment of many information across several parties, which can be simplified. 2. Difficulty in decision making by Owner on disputes between Contractors of different Packages. |  | 14256 - To minimize many parties interfacing within the same package for future projects. 14257 - Owner should lead all discussion and become referee on all disputes. 14258 - Minimize option on the interfacing. 14259 - PMC to have similar view as Owner. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Engineering | 6281 | Global lightning arrester system not adequate | 1. Lightning strike on items such as CCTV. | 1. System Breakdown 2. CCTV Malfunction |  | 16425 - Action Taken: To provide additional global earthing system 16426 - Recommendation: Design to consider impact of EMF, to provide lightning surge protector during construction phase. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2087 | Good attitude and cooperation from the contractors Project Manager and project team. Listen to the suggestion made to improve work progress | - Good team work | - Smooth work recovery progress. | - Weekly meeting and consisten site coordination to monitor the productivity. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Project Management | 5987 | Good EPCC top management cooperation with PMC in handling project management issues | 1. Good support and cooperation from EPCC top management in handling project issues | 1. Many issues resolved through guidance and support by the management team. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6086 | Good HSSE performance | 1. Contractor management emphasize on HSSE implementation 2. Contractor responsive to Owner requirement on HSSE | 1. Zero LTI 2. Achievement of 1.2 million man-hour |  | 15560 - Action Taken: Contractor cooperation to develop safety procedure and invest in safety equipment to enhance good safety approach. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B2-MOLF RAMUNIA | IO-P20B2-MOLF RAMUNIA | HSSE | 6098 | Good HSSE Performance | 1. Zero LTI had been achieved in P20B2 | 1. No HSSE issue 2. Achievement of 382,625 manhours |  | 15524 - Action Taken: Safety awareness has been successfully promoted through safety programs and implementation of reward system 15525 - Action Taken: CONTRACTOR had a competent HSE Manager in this project 15526 - Action Taken: Commitment shown by CONTRACTORs top management 15527 - Action Taken: Practicable safety training and drill were regularly carried out | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5962 | Good implementation of Simultaneous Operation (SIMOPs) during Construction and Commissioning | 1. During the initial commissioning phase, approved SIMOPs guideline was not available causing confusion at site (i.e. demarcation for construction and commissioning area) | 1. A session was conducted to finalize SIMOPs guideline and prompt implementation at site. Clear compliance to SIMOPs was demonstrated at site and acknowledged by PRPC HSE |  | 15788 - Action Taken: Demarcation of commissioning area with orange net and controlled by security 15789 - Action Taken: PTW briefing and control by commissioning team 15790 - Recommendation: Guideline should be finalized prior to starting commissioning | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6087 | Good materials management system i.e. quarry product supplied by Menta Quarry | 1. Contractor stockpiled in advance most of the quarry product and controlled the | 1. Able to maintain a good quality of quarry product whereby only 2 NCR issued by the client and 3 internal NCR to improve the quality. |  | 15561 - Action Taken: CONTRACTOR implemented a QMS. Procedure are in place to monitor measure and analysis these process. 15562 - Action Taken: Good communication adopted with the client representative in inspection and testing coordination. 15563 - Action Taken: Work in progress is inspected and tested as required. 15564 - Action Taken: QAQC surveillance program were conducted on average monthly basis on specific activities. 15565 - Action Taken: Contractor management demanding quality product from the subcontractor. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5848 | Gratings and handrail typical design from FEED does not properly reflect the market availability of the materials and also the loading condition was not properly checked. | 1. FEED drawings was not reviewed properly. 2. Tecnip personnel not allowed to access to P7 documents due to IP restriction | 1. Schedule impact. |  | 15113 - Recommendation: FEED drawings to be reviewed and approved properly, and all drawings intended to be used as RAPID general project specification and drawings to be updated regularly to reflect the current changes and OWNER’s requirement. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5615 | Ground level is not suitable for heavy machinery to manoeuvre at Lot 53B Laydown Area. | 1. Crush run are wavy after one month unloading / loading activities of STL / STR at Lot 53B Laydown Area - movement of forklift ranging from 5T to 25T, shore cranes and trailers. | 1. Steel plates 2T had to be placed on the ground to provide a stable ground for unloading purposes. However, steel plate placement is not a long term solution, where it covers small area. |  | 14912 - Action Taken: Advise CONTRACTOR to level the ground at the entire Laydown Areas (Lot 53B & Lot 141) once a month, or if required. 14913 - Recommendation: Strict enforcement of PTW & JHA - Contractor must ensure working areas are safe prior commencing works. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5102 | GRP vendor confirmed that they can fully comply with requisition’s requirements on TBS stage. But on the VDR stage, CCSM observed that the joint type was “Adhesive Bonded Joint Type” which is different from requisition requirement “Lamination Joint Type”. | 1. GRP vendor breached requisition’s requirement and TBS’s result. 2. ITB is not clearly specify the details option | 1. All Adhesive Bonded Joint Type were cut and modified to Lamination Joint Type, then the site UG schedule will be impacted seriously. |  | 14198 - Recommendation: When nonconformance with requisition is observed on VDR stage, vendor shall be requested to improve promptly. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5472 | Guideline for Phased Array Ultrasonic Testing (PAUT) /Time Of Flight Diffraction (TOFD) | 1. Such guideline is not available during tendering stage. | 1. NDT could be expedited. |  | 14593 - Action Taken: Refer to Job Bulletin, RAPID-P0024-PMC-END-JB-0001-0007 14594 - Recommendation: To incorporate the requirement in the ITB. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5451 | Guidelines for Colour Coding and Coating system which not cover in the PTS. | 1. The information provided for auxiliary piping of Rotating Equipment during the tendering stage is insufficient/unclear (PTS 31.38.01.11 RAPID-FE1-TPX-PIP-DES-0001-0002_3). 2. All final painting color for major rotating components has been clearly specified such as: Pump, Compressor, Motor and its accessories: Mid Green (BS 4800, 14 E 53/RAL Equivalent) Base plate: Silver grey (RAL 7001) Coupling Guard (Orange). However, for valves & piping for rotating equipment packages, color coding shall follow as per PTS 30.48.00.31-P amended as PDR RAPID-P0024-PMC-PIP-PDR-0001-0008. Each vendor interpretation of the PTS are differs. | 1. Some Vendor has provided different color coding for auxiliary piping of rotating equipment. Potential rework at site. 2. Potential approval of documents with need revisit again. |  | 14561 - Recommendation: To provide Guidelines for Color Coding as per Memo: RAPID-P0024-PMC-PMG-MEM-0112 & RAPID-P0024-PMC-PMG-MEM-0008 14562 - Recommendation: PTS to be revised to specify color coating / painting for mounded vessel 14563 - Recommendation: Design team / central core team to clearly specify the color code of respective piping / valve associated with rotating equipment package in order to avoid different interpretation by vendor on the piping / valve color. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Award/Contract | 6064 | Handover to operation. | 1. Done at 11 hour. 2. Operation inputs were minimal. 3. Conditions of operation not clearly specified in coc (CCC requirements). | 1. Hiccup in operation. 2. Change order - cost impact. 3. Reputation - not ready. 4. Idle cost to PDTV. |  | 15646 - Recommendation: Operations to be identified early. 15647 - Recommendation: CCC should be clearly clarified. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5891 | Have spent too much time on back and forth modification which is relatively meaningless and really consumed team members passion and killed enthusiasm of all. |  |  |  | 15186 - Applied Solution: Make sure to have a fully discussion among TCM/HQC and client when there is a divergence in design perspective / suggestion before conveying massages of modification downward to designers. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5852 | HAZOP Chairman (3rd party by contractor) not consistently comply to the Project Procedure especially while discussing on the Consequence and Recommendation | 1. Possibly due to different practice/underst anding of worst case scenario while recording the consequence | 1. May lead to inadequate identification of the hazards and missing of recommendation |  | 15119 - Recommendation: To ensure understanding of HAZOP Procedure and requirement. 15120 - Recommendation: Participants need to closely review the recording of HAZOP worksheet 15121 - Recommendation: At least participants need to understand the basic HAZOP process 15122 - Recommendation: To propose HAZOP to be conducted by mandatory by PTGSSB | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5746 | Hazop: The prepared P&ID for Main Hazop by contractor was not up to date. | 1. The prepared P&ID for Main Hazop and Package Hazop were obsolete version. | 1. Waste of time as no proper preparation were made. |  | 15322 - Action Taken: Comment were made directly to specific parties. 15323 - Action Taken: SC managed to provide the latest version. 15324 - Recommendation: Contractor to put some attention on main workshop preparation. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2076 | High turnover of Safety manager at Package Contractor | -Lack of safety manager with adequate skill and competency as per project requirement | -Interuption to HSSE management system | -To consider the implemention of Verification of Competency (VOC) for future project | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5486 | High turnover, including Lead Engineer positions | 1. Unattractive remuneration package. | 1. Lack of continuity and knowledge transfer. |  | 14615 - Recommendation: Selection of CONTRACTOR with strong financial capability. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5395 | Hoisting facilities for compressors. | 1. PTS 31.25.00.10 is not clear on the lifting requirement for single stage compressor. 2. Category 1, 2, 3 listed state multistage compressor. The requirement for single stage compressor is not stated. | 1. Contractor taking advantage stating that only manual operated crane is sufficient for single stage compressor. |  | 14442 - Recommendation: PTS 31.25.00.10 to consider including single stage compressor with critical rating 1. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5439 | Hoisting Requirement for Pump Maintenance | 1. Silence on the hoisting requirement for pump maintenance. 2. Unclear / not detailed in PTS | 1. Delay in approval of documents. 2. Taking a lot of time on discussion and review the documents |  | 14540 - Recommendation: To specify the requirement of hoist (manual/ motorize), railing, etc. for pump stations with operation team 14541 - Recommendation: PTS to be revised to specify Hoisting Requirement for Pump Maintenance | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Quality | 6059 | Honeycomb: a rough, pitted surface or voids in concrete resulting from incomplete filling of the concrete against the formwork, often caused by using concrete that is too stiff or by not vibrating it sufficiently after it has been poured. | 1. Poor coordination between site team and batching plant. 2. Site is not ready when the concrete arrived at site. | 1. Rectification work. 2. Extra cost incurred. |  | 15638 - Action Taken: Applying construction grouting. 15639 - Action Taken: To have a proper coordination with batching plant. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5673 | HSE engineer of OWNER has pointed out that Main Loop Condenser has to move out from pipe rack. | 1. In the FEED plot, condenser is located below pipe rack and licensor has provided the result of stress analysis for piping system regarding condenser. Because of those, SC has kept the location of condenser. 2. OWNER HSE engineer has requested to provide distance between condenser and pipe rack as per PTS. He has explained that the reason why space requirement is to protect pipe rack for the case of firing on the condenser. | 1. SC has tried to discuss/suggest to OWNER several times for the Licensor Requirement and Practical Design, SC has followed OWNERs comment. 2. It lead lots of changes and spending personal efforts around and after 60% model review. |  | 15071 - Action Taken: SC has to discuss with OWNER regarding discrepancy between FEED and ITB during proposal stage or early stage of engineering. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5776 | HSE engineering stage reviews. | 1. PMT suffered from lack of focal person. | 1. Delay of DHSSE deliverables review by OWNER. |  | 15395 - Action Taken: Eventually focal person appointed but shared with LLDPE project, however by then a backlog had developed. 15396 - Recommendation: To allocate HSE lead from the ITB stage. 15397 - Recommendation: Practice PCB with Contractor. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | HSSE | 5641 | HSE implementation not fully complied to OWNERs requirement. | 1. CONTRACTOR hired unexperienced HSE Management Team. 2. CONTRACTOR HSE Management team not well versed on OWNERs HSEMS. 3. CONTRACTOR did not practice standard procedure in document review (JHA, Risk Assessment, PIR). | 1. Nonconformance on HSSE requirements. 2. Potential HSSE incident. 3. Lack of proper and comprehensive risk assessment on all activities prior to project execution. 4. Potential ZeTo Rules Violation, increased the risks of lifting activities and increased risks of incident. |  | 14972 - Action Taken: Communicated and enforced SC to adhere to OWNERs HSEMS requirements. 14973 - Action Taken: Enforce CONTRACTOR to submit documents in advance for review, comment and sharing to workers at site. 14974 - Recommendation: Ensure CONTRACTOR to hire experienced HSE Management Team. 14975 - Recommendation: Proper planning before project execution. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5903 | HSE Studies close-out activities - Vendors follow-up activities All the items and packages analysed by means the HSE studies (e.g. HAZOP, SIL, HRA, etc.) |  |  |  | 15206 - Applied Solution: Project team has considerably put under control the Vendors activity trying to accelerate and to receive all the HSE close- out sheets reducing any possible delay 15207 - Suggestion for Improvement: Vendors Close-out activities shall be clearly identified on the MR documentation and shall be associated to the liquidate damages in order to ensure that the Vendors will complete all the follow-up activities | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5082 | HSSE: Continues struggle by EPCC in managing the project HSE issues. Regular occurrence of misconduct / noncompliance to HSE Requirement at site. | 1. Noncompliance to the HSE requirement in ITB /contract. ( young and inexperienced HSE resources, sub-con work supervisors unable to communicate in English ). | 1. Miscommunications and project HSE requirement are often not met. Regular ZETO Rule violations. |  | 14107 - Enforcement of the contract actual HSE requirement on the EPCC Contractor at the very early stage of the project, failing which PMT HSE has to take direct & active involvement in managing HSE related issues with subcontractors. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5080 | HSSE: Effective management of subcontractors HSE performance. | 1. Consequence Management has been put as KPIs for contractor. Trending of Consequence Management is tracked and analyzed on monthly basis and action plan is drafted/carried out to improve the HSE performance of the subcontractors. | 1. Significant improvement of subcontractors HSE performance. Less ZETO Rules non compliances. Motivate subcontractors management to be accountable and actively support HSE related initiatives/improvement. |  | 14105 - Recommend to implement the trending analysis on consequence management by project team. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5081 | HSSE: Risk related to critical activities are effectively manage | 1. Specific focal person / discipline in HSE Team (IPMT/EPCC and Sun Contractor) i.e. Scaffolding, PETI, Lifting and Confined Space. | 1. Quick and swift actions taken by respective sub-contractors. Contribute in meeting the project KPIs |  | 14106 - Continue engagement with the respective focal persons ( PMT/EPCC/Sub cons) via regular schedule TBM and walkabouts. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5714 | HVAC: Difference in PTS requirement between INST & HVAC on cable entry. | 1. INST PTS specifies top entry but HVAC PTS specifies bottom entry. | 1. Delay in design freeze for HVAC. |  | 15240 - Action Taken: Get GTA and PTA to agree on standardization of cable entry for HVAC. 15241 - Recommendation: Revision in INST PTS. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6189 | IDC (Inter Discipline Check) for Vendor Documents | 1. Sub vendors to be instructed to strictly maintain the IDC procedure within their company | 1. Will lead to compromise on document quality if IDC procedure is not followed by sub-contractors. |  | 16225 - Recommendation: EPCC to ensure that the respective sub- contractors follow IDC procedures to ensure no compromise on quality. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Procurement | 5862 | Identify Beijing Office Centre Gaps in Inspection and Expediting for Chinese Vendors | N/A | 1. Gaps caused delay in delivery |  | 15139 - Action taken: Dedicated Resident Inspector for Criticality 1/2 for China | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5757 | Impact assessment when there is scope reduction / transfer between UPTs. | 1. UPT exercised bidders alternative proposal to obtain cost saving by removing LCR 541 and relocating pertinent equipment to FAR 523. However, sufficient impact assessment on other UPTs were lacking. | 1. Migration of equipment to Tank Farm area involves significant changes to interfacing scoping with OUI-JV, causing variation in engineering design at OUI-JV side. |  | 15349 - Action Taken: Alignment with OUI-JV and SD-4 conducted for engineering design change and scope addition during engineering execution. 15350 - Recommendation: Overall cost benefit analysis to be thoroughly done involving cross Sub-Directorate level (SD) to ascertain group cost benefit, and scope of work change prior to EPCC award. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Award/Contract | 6065 | Impact of emergency arrangement to Project operation. | 1. Water shortage at Lebam. 2. Request from State. | 1. Warranty period of certain equipment affected. 2. Helps state alleviated water shortage. 3. Manage to shorten construction period. 4. Cannot recover operation cost. 5. Enhance reputation of PETRONAS in CSR. |  | 15648 - Recommendation: To review consequence before committing to help state. 15649 - Recommendation: Operation cost to be agreed upfront. 15650 - Recommendation: To review and manage warranty period. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5466 | Implementation of Dyke Wall (concrete) against Bund Wall (earth) | 1. PTS allows both walls as secondary containment for the tank farms. However, it does not address the expansion due to heat, etc. if the dyke wall is very long. | 1. Potential crack to the dyke wall |  | 14585 - Action Taken: Provide expansion joint 14586 - Recommendation: A clear requirement has to be specified prior award, e.g. in Project Specification, etc. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5398 | Implementation of double compartment manhole for AOC / ACC system for change of pipe diameter larger than 500mm is not suitable. | 1. Implementation of double compartment manhole for AOC / ACC system for change of pipe diameter larger than 500mm. | 1. Weir (inside double compartment manhole) loss dominates all hydraulic losses among the system, and AOC system should therefore be deeper to overcome it. |  | 14446 - Action Taken: PDR raised to omit the double compartment manhole for change of pipe diameter larger than 500mm. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Precommissioning/Commissioning | 5667 | Implementation of the SSP by CONTRACTOR taking longer time. | 1. Lack of understanding of the SSP and support from SD3. 2. Unavailability of the SSP SME to support in implementation. | 1. Late of SSP implementation. |  | 15054 - Action Taken: Communication and requested for kickoff meeting from SD3 established. 15055 - Action Taken: Conducted SSP briefing by SSP SME. 15056 - Action Taken: Conducted SSP workshop between CONTRACTOR and OWNER to develop Key Success Area (KSA) and flaw identifications exercise. 15057 - Recommendation: Dedicated SSP personnel for LLDPE package required. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Procurement | 5220 | Improper categorization in MVL, i.e. HVAC | 1. Mixture of different type of vendors, i.e. packagers, manufacture, contractor etc. | 1. Prolong evaluation award process. |  | 14294 - Choose and decide on one (1) category of vendor in the MVL to avoid confusion. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5541 | Improper culvert used for road crossing. | 1. Clogged spun pile with minor slope collapse at temporary road crossing. | 1. Cut off pile is used to act as temporary culvert at road crossing. 2. Causing water backflow and minor slope collapse. |  | 14735 - Action Taken: Proposed to CONTRACTOR to use proper concrete culvert. 14736 - Action Taken: Instructed CONTRACTOR to reinstate the affected temporary road and clear the clog. 14737 - Action Taken: Instructed CONTRACTOR to clear the clog regularly. 14738 - Recommendation: To spell out technical requirement to use proper concrete culvert for temporary road crossing during construction. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Quality | 6061 | Improper Internal cement lining done by sub-contractor. | 1. Non-performance of sub-contractor. 2. Lack of monitoring by OWNER. | 1. Rework. 2. Potential confines space issue. 3. Delay project completion. |  | 15642 - Action Taken: Quality monitoring and checking by both main-con and consultant. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5924 | Improper Package Unit design (Sludge Dryer Cooling Tower) | 1. Sludge Dryer Cooling Water System vendor data submission was late & incomplete. Because limited data was available from Vendor and unavailability of Vendor Process Design engineer, Project team was not able to review and comment the cooling water system design on time. 2. Language barrier issue had caused delay in solving any technical query and issue. 3. Lack of specialist involvement. EPCC Contractor including their Sludge Dryer Package Vendor is not familiar with cooling water system design and requirement. | 1. Design of the cooling water system was not following RAPID Utilities conditions & specifications. This had caused rework on the design. 2. Automatic Chemical Injection Facilities was not provided for treatment of the cooling water as what normally practiced at other PETRONAS OPU. 3. Installation of equipment of less proven track record and difficult to operate and may cause higher operating cost. |  | 15702 - Action Taken: Project team had officially requested EPCC Contractor to provide automatic chemical injection facility for treatment of the cooling water to ensure reliable cooling system. 15703 - Action Taken: Proposed EPCC Contractor to engage Water Technology Vendor to execute the chemical treatment 15704 - Recommendation: Deliverables and target submission date by Package Vendor must be clearly defined. Vendor discipline engineer must be present at least during the Kick Off meeting with Owner/Project team. 15705 - Recommendation: More involvement in the evaluation and selection of specialized package equipment. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5896 | Improvement of Communication procedure in between various centres. Whenever engineering activities are developed in multiple centres, frequently it happen that project team is not fully aligned regarding priorities, project targets and information status. |  |  |  | 15192 - Applied Solution: Mobilization of a resident project reprehensive in the secondary center. 15193 - Suggestion for Improvement: Whenever activities are developed in multiple centers, it is important to establish a regular monthly or bi-monthly coordination meeting for almost the entire project development in order to keep informed and aligned | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5910 | Improvement of Coordination and Monitoring of Contract Conformance (Contract Conformance post award) |  |  |  | 15218 - Applied Solution: Monitoring and coordination of the whole conformance cycle achieved through the implementation of dedicated excel database, structured filing of documents and segregation of documents under discussion and final versions 15219 - Suggestion for Improvement: Implement and regularly update dedicated monitoring tools 15220 - Suggestion for Improvement: Carry out organized and tidy filing of documents and carefully segregate documents under discussion from finalized documents | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5498 | In Administration Building Structural Drawing the Locations / Co-ordinates was not indicated which is generally provided by General Civil Plot Plan Drawing. | 1. IDC will be issued to PD / GC for coordinates and location review | 1. Location / Coordinates for Structures |  | 14630 - Recommendation: Orientation of structure and co-ordinates of working point as per Plot Plan / Equipment Layout is required to be given by General Civil and/or Piping and accordingly the coordinates will be given in the relevant structural drawing. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Procurement | 5764 | Inaccuracy of TBE report. | 1. Initially bidder had confirmed compliance to UL / FM and UV Cert. However, in actual vendor is in process of being accredited. | 1. UL / FM butterfly valve failed the testing. 2. Late delivery of valve at site. |  | 15367 - Action Taken: Vendor has modified the design of the dics to comply with the testing. 15368 - Action Taken: Retesting has to be conducted. 15369 - Recommendation: Contractor to provide all the evidence in TBE report. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Project Management | 5536 | Inaccurate attachment of documents in the ITB | 1. Lack of checking | 1. Clarification from bidders. |  | 14706 - Action Taken: Rectified discrepancies during technical clarification phase. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5873 | Inadequate manpower resources for Project Control team | 1. Project Planning and Control cannot cope with the additional scope of work e.g. during the week of Project Monthly Meeting, VDRL monitoring and for monitoring the subcontractor’s activities. | 1. Insufficient monitoring on project planning, especially on subcontractor scope. 2. The Project Control team seems to lose focus when the workload suddenly spikes e.g. during the week of Project Monthly Meeting, VDRL monitoring and monitoring of subcontractors. 3. Many Project Control scope are neglected. |  | 15157 - Recommendation: Ensure Contractor provides the full Project Control team at the start of the Project. The Contract should be the Governing document to ensure this. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Document Management | 6026 | Inappropriate timing for migration of document database. | 1. Migration from POL to PEDMS happened at a very late stage of Engineering when documents were rigorously updated and manpower resources are limited. | 1. Delay in upload, receive and review of document. 2. Considerable amount of time taken to familiarize new system and workflow 3. Offline review and commenting had caused some inconsistencies e.g. comments not incorporated, CRS reply from EPCC missing, incorrect document status i.e. closed action on POL indicated as pending action on PEDMS. |  | 15890 - Action Taken: Practiced offline document review and temporarily utilizing another database provided by the EPCC (FTP server). 15891 - Recommendation: To review timing and avoid unnecessary changes on the document database that may impact completion of engineering document. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | HSSE | 6056 | Incompetency of Machine Operators. | 1. No proper control / monitoring by main contractor. | 1. Potential reputation / penalty / stop work. |  | 15630 - Action Taken: Conduct on-site training. 15631 - Action Taken: Impose penalty. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5844 | Incomplete HAZOP & IPF study due to time-constraint. EPCC Contractor fails to establish proper approved engineering documents prior the study. EPCC Contractor lump together the studies within the same period. | 1. EPCC Contactor fails to do full engineering prior the study. 2. EPCC Contractor heavily relied on VENDOR capability to provide info during the study. 3. EPCC supposed to ensure complete readiness for fruitful HAZOP & IPF studies. | 1. Major discrepancies on the vendor documents vs. EPCC documents. 2. Major changes on package P&IDs. 3. HAZOP findings need to be evaluated after the session for clarification. 4. Ad Hoc changes on IPF initiator & final elements. |  | 15107 - Recommendation: EPCC Contractor shall provide OWNER with approved documents prior HAZOP & IPF session. 15108 - Recommendation: EPCC should conduct internal session 15109 - Recommendation: EPCC should engage reputable third party consultant for HAZOP. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5488 | Incomplete material ordered for Underground Piping Requirement. Lamination kit was not ordered | 1. CONTRACTOR is inexperience in executing underground piping installation. | 1. Delay in commencement of underground piping 2. Impact on construction work front activity |  | 14618 - Action Taken: Delivered by air freight | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5632 | Incomplete of Engineering Reviews / Studies by CONTRACTOR. | 1. Some of the Engineering Reviews / Studies are not listed in SC Engineering Review / Study. 2. Some conducted in adhoc basis. | 1. Required extra manpower planning. |  | 14953 - Action Taken: Lead Engineer from iPMT and CONTRACTOR shall review the ITB and ensure all the Engineering Review / Study are provided. 14954 - Recommendation: Awareness of Projects ITB. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5919 | Incomplete process design review i.e. HAZOP studies | 1. Contractor had no experience conducting HAZOP 2. List of nodes defined for HAZOP not properly discussed and agreed with the Project team. 3. Lime & Magnesium and Sludge Dryer Package Unit Vendors changed their design post HAZOP study despite knowing that design should be finalized prior to the study. | 1. HAZOP study for utilities system in RWTP was not complete. High pressure water distribution system, service water tank & potable water system have not been reviewed. 2. Changes on Vendor Package unit design i.e. for Lime, Magnesium and Sludge Dryer unit post HAZOP studies were not re-HAZOP. |  | 15685 - Action Taken: Project team had officially instructed EPCC Contractor to complete HAZOP review for the remaining utility system and conduct re-HAZOP on the changes done. 15686 - Recommendation: Ensure that the scope and list of nodes defined for HAZOP are properly discussed and agreed. 15687 - Recommendation: Finalize all design including vendor info before conducting any detailed HAZOP review. Major design change should not be allowed post the study to minimize rework. 15688 - Recommendation: Any design change shall be strictly controlled and documented in accordance of Project Specification on Management of Change. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Undefined | 6311 | Incomplete review by OWNER/PMC | 1. Lack of resoruces from OWNER/PMC | 1. OWNER/PMC facing problem in reporting |  | 16485 - Action Taken: To have a dedicated Planner 16486 - Recommendation: To have a dedicated Planner | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Planning | 6270 | Incomprehensive baseline schedule for construction and commissioning phases | 1. EPCC depend on detail schedule by subcontractor (level 4). | 1. PMT unable to review detail work sequences. 2. Jeopardize critical path. 3. EPCC unable to justify to PMT. |  | 16402 - Action Taken: Individual level 4 schedule based on contractors scope. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5389 | Inconsistencies in PTS has resulted in design requirement disputes for requirement of DIVs in toxic service. | 1. Inconsistency of PTS requirements. 2. Contract refers to less stringent PTS. | 1. PEPI claim for change order based on their interpretation. |  | 14432 - Action Taken: Inconsistency was advised to PTS custodian. 14433 - Recommendation: To rectify the requirements in PTS at earlier stage. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Document Management | 5288 | Inconsistency of document numbering | 1. Contractor did not follow thorough the procedure / guideline. No monitoring from PMC/PMT | 1. Difficult to track |  | 14408 - Action Taken: Contractor to submit initial MDR and review by iPMT | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Project Management | 5995 | Inconsistent information | 1. Lack of coordination communication within project team |  |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5235 | Inconsistent pipe spool shipment | 1. Poor planning 2. Insufficient forwarders capacity | 1. Late spool arrival at site and cause delays in construction |  | 14320 - Action Taken: Increase shipping frequency 14321 - Action Taken: Maximize shipping capacity 14322 - Action Taken: Develop priority list | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Project Management | 6357 | Inconsistent standard apply within P28B (e.g. different spec / criteria between HSE and general piping spec i.e. hydrogen services line) | 1. HSE criteria | 1. Process safety design. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Planning | 6028 | Incorrect information taught during training (SW Pit Pump start-up procedure. LLWT asked to isolation transmitter to prevent pressure spike which result to pump trip) | 1. Trainer lack or experience and knowledge | 1. Bypass safety critical equipment which may endangered equipment. |  | 15893 - Action Taken: To send experienced and knowledgeable personnel as trainer | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Construction | 6262 | Incorrect volume of work for E&I | 1. Info in MTO/CCI not updated 2. Incorrect planning and mitigation at site 3. No 3rd party review i.e. owner | 1. Schedule impact. |  | 16389 - Action Taken: Update the CCI during construction | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2083 | Increase of Binder Course thickness (from 50 mm to 75 mm) | Early decision by Engineering team | - Avoid the progress slipage. - Avoid reworks and extra costs. | All IFC drawings were amended accordingly. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5684 | Increase the quantity of hydrant | 1. During fire safety 3D review, OWNER has pointed out that SC didnt follow the requirement of distance between 2 hydrants. 2. ITB requirement presented maximum 60m distance between 2 hydrants. SC has applied 60m distance with diagonal length, but OWNER insisted it has to be the length of X-Y axis. | 1. SC follow OWNERs comment. So, 2 hydrant are added to total quantity. Because this is related with U/G piping, engineering team informed to construction team about design change and construction team adjusted the sequence of U/G work to minimize impact. |  | 15082 - Action Taken: Try to find an ITB requirement that can be interpreted differently as per the view point of each person. If it is figured out, discuss with OWNER as soon as possible. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5975 | Indoor lightings installed throughout plant (except LCB) not as per project requirement. | 1. EPCC not understand/following the project requirement/specification. | 1. Lightings are with bare fitting. Electrical parts are exposed. No protection to human, dust and water ingress |  | 15805 - Action Taken: SR already raised. Few discussions have been made with LLWT and PMC. Still pending closure | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2088 | Induction of manpower and machinery inspection delay | -Contractor underestimate of HSSE induction requirement -Limitation of induction facilities | Contractor cant mobilize | -Expedite and follow closely 3rd party induction. -Pre-pack basic mobilisation and machinery inspection should be given to contractor in advance. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Document Management | 6069 | Ineffective document control process. | 1. Drawings / documents shared are not circulated to all relevant parties. 2. No centralized system utilized between Site team, HQ team and contractors. | 1. Delay in information distribution (drawing). 2. Misunderstanding of updated drawing which leads to Rework. |  | 15655 - Action Taken: To have centralized document control system (e.g. PeDMS, POL etc.). | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Interface | 6264 | Inefficient interface coordination | 1. Change of RAPID interface focal persons. 2. Change of interface programs / meeting. 3. Only working level involved. | 1. Overloaded resources. |  | 16391 - Action Taken: Owner engaged CD interface and coordinate work with EPCC. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6077 | Inexperienced in specialist work i.e. dredging work | 1. Contractor has limited dredging experience encounter specialist work in the past. | 1. Subcontractor dictate their work programme and commercial terms, 2. Slow work progress and high cost impact |  | 15543 - Action Taken: OWNER PMT intervened by assist in managing subcontractors 15544 - Recommendation: Contractor to have experienced dredging specialist | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5629 | Input for PCB report from team members was not obtained on time. | 1. Team members were too occupied with their own tasks, unable to provide inputs timely. | 1. PCB agent and PM have to put in extra effort and time to meet the timeline. |  | 14947 - Action Taken: The Project Manager and PCB agent helped to fill in the gaps. 14948 - Recommendation: Initiative from each team member to take ownership and contribute positively. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Engineering | 5529 | Input parameters should be defined prior to start of FEED | 1. Accelarated FEED 2. Absence of dedicated OWNERs team. | 1. Unnecessary additional work to FEED team. 2. Rework due to inaccurate input data. 3. Delay in getting infromation from other EPCC |  | 14695 - Action Taken: Conducted several face to face meeting with OWNER and other packages to close the issues. 14696 - Recommendation: Have defined basis prior to start of FEED. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Quality | 6316 | Inspection arrangement by Contractor resulting work are required to be carried over to DLP | 1. No sufficient manpower to support the inspection | 1. Impacting issue of PA |  | 16494 - Action Taken: Additional resource to complete the work 16495 - Recommendation: Work need to be completed as per the schedule, a close monitoring or micro manage is required | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5545 | Inspection tools (clamp meter) for monitoring the welding parameter is not available. | 1. Inspection tools was not calibrated and was not available at site to monitor / verified the requirement needed base on specification and ITP. 2. Improper work planning and resources allocation by CONTRACTOR. | 1. Potential delay on welding work. |  | 14745 - Action Taken: CONTRACTOR have provided the clamp meter dedicated at fabrication area for verification purpose. 14746 - Recommendation: Include inspection point for monitoring the welding parameter in Inspection Test Plan. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5542 | Installation of scaffolding for construction not following project requirement. | 1. Scaffolding installation without proper design and by incompetent personnel. | 1. The structures was unsafe for personnel access and need to be isolated from being used. 2. Potential HSSE incidents. |  | 14739 - Action Taken: Issued a reminder to CONTRACTOR regarding compliance with project requirements & Malaysian law and stop work to use scaffolding until further notice. 14740 - Recommendation: To clearly mentioned in ITB that CONTRACTOR shall provide only material and competent person approved by OWNER for scaffolding works. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5906 | Instrument Numbering for Major Packages. Instrument Numbering has been changed after first issue of Vendor P&ID to avoid conflict with existing Instrument Numbering of the Plant. |  |  |  | 15209 - Applied Solution: Additional comments on Vendor P&ID. 15210 - Suggestion for Improvement: Instrument Numbering Range to be assigned to the Package shall be defined within Kick-off Meeting with Vendor. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5601 | Instrument: Analyzer house didn't require blast resistance initially. | 1. Misinterpretation of specification led to requirement of blast resistance. | 1. Different parties (Core Engineering and UPT) with different interests, interpreting an issue differently. |  | 14876 - Action Taken: Communicated with all parties concerned and came to a mutual way forward to raise PDR. 14877 - Recommendation: Setting guidelines very clearly, not open to interpretations. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5604 | Instrument: CONTRACTOR did not select vendor as per the requirement of PETRONAS Category Management as stated in the ITB. | 1. CONTRACTOR included bidder from outside of Category Management OEM. 2. CONTRACTOR overlooked the requirement for bidder lists. | 1. Cancellation and re-ordering of item resulting in delay. |  | 14884 - Action Taken: Reminded CONTRACTOR to comply with PETRONAS Category Management requirement and order to the acceptable bidders from PETRONAS Category Management for that item. 14885 - Recommendation: OWNER to ensure compliance of ITB requirement by the contractor. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5603 | Instrument: CONTRACTOR did not submit Instrumentation job specification. | 1. CONTRACTOR overlooked the ITB requirement. | 1. Delay in finalization of IFE MR / TBEs. |  | 14880 - Action Taken: Discussed with CONTRACTOR and explained the ITB requirement and emphasize for the compliant. 14881 - Action Taken: CONTRACTOR submitted job specification. 14882 - Action Taken: OWNER team highlighted in MDR for including this specs. 14883 - Recommendation: Alert CONTRACTOR to include job specification in the MDR in the 1st issuance. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5015 | Instrument: Engineering Document: No clash checks on secondary routing & support causing hard for execution team to execute the job. This problem also may cause maintenance team to have problem in order to maintain the equipment i.e. control valve | 1. Secondary routing & support is not part of EPCC deliverable to project | 1. Clashing and rework at site causing delay of installation for cable tray, instrument stanchion & location |  | 13965 - Action Taken: Reconfirm modelling and check at site 13966 - Recommendation: Sequence of inter discipline execution based on priority. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5014 | Instrument: Engineering Document: Relentless documents/drawings updating causing the work at site to be delayed due to rework that needs to be done after the drawings is updated. Package items not included instrument data list | 1. No finalize documents issued for work execution 2. Improper engineering update by engineering team | 1. Delay in construction progress due to awaiting of drawings 2. Rework 3. Idle manpower at site 4. No final approved drawings issued by engineering team thus causing workers to start doing termination inside FAR using vendor drawing in order to catch up with progress 5. Waste of materials i.e. cables |  | 13962 - Action Taken: Consistent reminder & follow up with EPCC engineering team on daily meeting 13963 - Recommendation: To have dedicated EPCC reps. 13964 - Recommendation: Owner to consider to have dedicated reps for selected critical package. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5017 | Instrument: EPCC Construction team are not aware/fully understand/sensitive with project specification. | 1. Not familiar with PETRONAS project requirement 2. EPCC does not briefed project workforce on contract requirement & specifications | 1. Construction does not follow PETRONAS requirement in ITB |  | 13970 - Action Taken: Debrief EPCC contractor on PETRONAS requirement 13971 - Recommendation: Continuous cooperation between owner and EPCC. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5016 | Instrument: EPCCs guidelines and procedure for calibration too generic to cover all devices | 1. No comprehensive calibration procedure provided by EPCC engineering & construction team. 2. Inexperience manpower hired by EPCC to perform the tasks. 3. EPCC manpower does not follow the approved procedure and guidelines. 4. EPCC based on past experienced which is not relevant. | 1. Results and quality of the calibration is questionable |  | 13967 - Action Taken: EPCC to submit manpower CV to be reviewed & approved by PMC. 13968 - Action Taken: EPCC to produce comprehensive guideline and procedure on calibration. 13969 - Recommendation: To come out with mock up calibration for each device types. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5596 | Instrument: It was found some Orifice installation were considered without straight line requirement. | 1. CONTRACTOR overlooked the ITB requirement. | 1. Potential wrong design PO placement. |  | 14866 - Action Taken: Crossed check with Manufacturer recommendation and also to rectify the installation practices. 14867 - Recommendation: To ensure each clause of Project Specification is fulfilled, and to raise deviation if some areas cannot be achieved. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5598 | Instrument: It was found that incoming and outgoing cable entry of HVAC Control Panel are from the top. | 1. Conflicting specification between instrument specification and HVAC specification, due to usage of old PTS revision. | 1. Top entry could potentially lead to short circuit due to water ingress. |  | 14870 - Action Taken: Redesigned the HVAC Control Panel for bottom cable accessibility and also to rectify the installation practices to prevent tripping hazard. 14871 - Recommendation: To ensure OWNER PTS does not conflict with each other. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5599 | Instrument: It was found that Safety and Process Control PLCs are not physically separated. | 1. CONTRACTOR engaged a vendor who supplies integrated PLCs. | 1. Violation of Project specs requirement. |  | 14872 - Action Taken: CONTRACTOR to confirm with package vendor and to redesign accordingly. 14873 - Recommendation: OWNER to ensure that contractor complies with project specification diligently. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5023 | Instrument: Lack awareness on document/site preparation/training prior system energization | 1. Lack of understanding for ITB requirement | 1. Delay in system energization |  | 13984 - EPCC to conduct training and frequent follow up according to ITB requirement such as ITR, LOTO, rescue plan | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5021 | Instrument: Late construction schedule from P14 | 1. Late cable trench readiness from P14 | 1. Delay in backfilling for instrument P1 trench and late in handover to civil |  | 13980 - Action Taken: Executed backup plan. 13981 - Recommendation: Executed backup plan. 13982 - Recommendation: Escalate to higher management. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5597 | Instrument: Mismatches and lack of complete coverage of 3D fire and gas mapping report during model review. | 1. Contractor did not thoroughly go through the list of fire and gas related documents. | 1. Not all scenarios were weighed upon, hence the detector placements and numbers were not optimized. |  | 14868 - Action Taken: Model review comment tags were created and this will be responded to PGTSSB to be incorporated. 14869 - Recommendation: To have continuous engagement with PGTSSB and HSE, Instrument and Operation to fulfill all requirements. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5022 | Instrument: Poor drainage system during weather condition / monsoon season |  |  |  | 13983 - To consider internal drainage to cater monsoon season | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5020 | Instrument: Poor interface issue with other discipline between owner and EPCC i.e. civil & mechanical | 1) Late of readiness from other discipline for instrument to start work such as instrument trench, piping routing and etc. 2) Poor coordination meeting between discipline. | 1. Delay in work execution progress 2. In some cases also involving rework and repair due i.e. instrument cable damage due to excavation work 3. Storage obstruction/access towards location caused by other discipline that hinder our progress |  | 13977 - Action Taken: Direct site coordination. 13978 - Action Taken: Direct site coordination. 13979 - Recommendation: Immediate information sharing to respective discipline. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5012 | Instrument: Procurement & Warehouse : Material procurement late delivery | 1. Late confirmation & approval from EPCC engineering team prior to vendor manufacturing 2. Interface issue between discipline and EPCC | 1. Delay in work execution progress |  | - | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5013 | Instrument: Procurement & Warehouse: Improper material handling during receiving of the equipment. No dedicated manpower/focal person to monitor preservation status. No proper material preservation strategy & reporting. No proper facilities for preservation | 1. Insufficient & improper storage area 2. Lack of facilities & equipment for handling, storage & preservation 3. No routine inspection by EPCC warehouse team on item stored at warehouse especially at open area 4. Non localized manpower hired by EPCC | 1. Rework on to rectify the defect equipment 2. Equipment damage before installation 3. Improper understanding for language and requirement on contract requirement |  | 13959 - Audit & hire competent manpower to manage storage item at warehouse 13960 - Add facilities & equipment 13961 - Consistent follow up on the status of stored items | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5602 | Instrument: PSV TBE is supposed to be reviewed by multidisciplinary e.g. Piping & Instrument. | 1. PSV from PETRONAS point of view is to be reviewed by Instrument, but from SC point of view this is under the purview of piping. | 1. PO placement halted due to Instrument comments were not inserted in the document. |  | 14878 - Action Taken: Quickly requested CONTRACTOR to postpone the PO placement and retracted the document to include Instrument reviewers. 14879 - Recommendation: Constantly update the DDM to identify and include all reviewing discipline. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5600 | Instrument: Weight of valve shown in 60% model review (including control valve) were not reflecting the actual weight. | 1. Unavailability of approved Vendor data. CONTRACTOR specified wrong weight. | 1. Wrong implementation of data in the model review which subsequently leads to wrong design. |  | 14874 - Action Taken: CONTRACTOR was asked to negate the irrelevant weights and provide only actuator weight. 14875 - Recommendation: CONTRACTOR need to have more awareness on specific requirements. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5950 | Instruments & Hook Up drawing was rejected however construction still proceed. | 1. Tubing hook up & installation are not consistence. Resulting conflict in instruments measurements. | 1. Resulting delay in commissioning activity due to taping has to be changed & experimented until desired pressure obtained. Impact to maintainability resulting in maintenance issues. |  | 15759 - Action Taken: Joint meeting with PMC, EPCC together with operation were conducted to discuss way forward. 15760 - Recommendation: Construction should refer to approved drawing only. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5904 | Instruments Typical Installation In standard Basell design, reference is made to typical for instruments installation that are not aligned with latest engineering development and with client requirements |  |  |  | 15208 - Applied Solution: Instruments typical installations foreseen by Licensor have been updated during engineering phase with impacts on several engineering activities such as I/O list finalization, P&ID development, instrumentation purchase etc. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B2-MOLF RAMUNIA | IO-P20B2-MOLF RAMUNIA | Construction | 6030 | Insufficient Experience of CONTRACTORs site team | 1. The site team personnel are young and insufficient years of experience for this type of work | 1. Slow in work progress 2. Unclear decision making on the part of contractor |  | 15510 - Action Taken: Owners engagement to guide and assist the Contractor in the work progress 15511 - Recommendation: Recommend to scrutinize the contractor manpowers experience | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Project Management | 6246 | Insufficient laydown area | 1. Small TCF area available for project. | 1. Late delivery of equipment. |  | 16366 - Action Taken: Additional space rental. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Project Management | 5990 | Insufficient manning to execute scope of the project (management, procurement, engineering) | 1. CONTRACTORs is too depending on certain key persons for a lot of tasks. | 1. Focal persons were loaded of multiple tasks at the same time which resulted in him priotising the jobs and delaying certain tasks 2. High turnover |  | 15823 - Action Taken: EPCC were asked to add extra manpower to assist. 15824 - Recommendation: To properly assess the required manning number and competency for the projects. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Procurement | 5913 | Insufficient manpower | 1. Lack of monitoring 2. Late engineering confirmation 3. Not familiar with documentation process / control 4. No proper management in repaired material expediting | 1. Contractor Procurement team work load is heavy and unable the deliver the required deliverables. Appointment of Expeditor quite late and station at Contractor main office. |  | 15667 - Action Taken: OWNER/PMC stationed at Contractor office to assist and expedite review and approval process 15668 - Recommendation: Emphasize on Implementation of Material Management during early stage 15669 - Recommendation: To have dedicated Expeditor position | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Quality | 5649 | Insufficient numbers and late allocation of Project Vehicle assigned to PMT Staff. | 1. Too many application from other packages at same time causing longer waiting time. | 1. Restricted movement and mobility for site staff of different disciplines to go for inspection and supervision at various locations. |  | 15001 - Action Taken: Discussed with CONTRACTOR on the PMT specific requirement for Project Vehicles. 15002 - Action Taken: Submitted vehicles application form 2 months in advanced. 15003 - Recommendation: To ensure specific requirement to supply of Project Vehicle by CONTRACTOR is clearly described in the ITB document. 15004 - Recommendation: Sufficient numbers of Project Vehicle assigned to PMT Staff. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5923 | Insufficient Process Engineer | 1. Underestimate of the amount of Process engineering work that had to be done. | 1. Delay in completion of remaining Process deliverables and DCS/ESD logics testing progress. The dedicated Process Engineer was relieved from his scope towards the end of engineering, leaving all the tasks to the Project Engineer who had to take care of multidiscipline deliverables. |  | 15700 - Action Taken: Insist advanced copies of Process document from EPCC Contractor and practiced offline commenting to avoid recycle of documents. 15701 - Recommendation: To ensure EPCC Contractor provides adequate manpower resource. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5960 | Insufficient spares for faulty equipment by EPCC | 1. Late issuance purchase order for the additional spares. 2. Less reviewer during engineering stage | 1. Not all commissioning spare parts available at site especially for specialty equipment such as ABB relay. Commissioning activity was delayed due to awaiting shipment of repair parts from oversea |  | 15782 - Action Taken: Constant follow up with vendor to expedite delivery. 15783 - Action Taken: Alternatively the required parts (i.e. thermal overload relay) was solicited locally but to no avail since not compatible 15784 - Recommendation: Commissioning spare list should be more extensive inclusive of spare parts for package equipment’s | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6079 | Insufficient support from Engineering Design Consultant i.e. discovery of hard layer | 1. The Engineering Consultant did not have the similar specialist work design experience | 1. Slow in design work progress 2. Design detailing was late finalized and affected the construction progress i.e. seabed hard strata |  | 15546 - Recommendation: To engage qualified and experienced engineering consultant in the similar work | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5945 | Integrated Factory Acceptance Testing (IFAT) of DCS shall be conducted with associated Subsystems at Factory. Integrated Factory Acceptance Testing (IFAT) of FGS shall be conducted with associated Subsystem at Factory. | 1. EPCC CONTRACTOR had not conducted the IFATs, but shipped the DCS and FGS without conducting the IFATs with associated Subsystems. EPCC CONTRACTOR had informed that the Integrated Site Acceptance Testing (ISAT) will be conducted to test the same. IFATs not conducted for: - DCS IFATs with Pkg. PLCs, VSDs, HV-Motors, etc. - FGS IFAT with Main Fire Alarm Panel PLC. | 1. There were very many communication issues between DCS and its subsystems and FGS and MFAP causing delay at site. DCS-VSDs, and DCS-HV Motors communication redundancy resolutions still pending with EPCC CONTRACTOR. DCS-Sludge Dryer PLC - ISAT is being conducted. |  | 15745 - Action Taken: Many meetings were conducted with EPCC CONTRACTOR and Vendors to find resolutions for DCS-VSDs communication. Final way forward is still pending. DCS-HV Motors Communication redundancy implementation and testing still pending. 15746 - Recommendation: Basic requirements like IFATs shall be conducted by EPCC CONTRACTOR without any deviation in order to avoid unforeseen communication issues and associated time delay in fixing these issues. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5391 | Integration between Mumbai Office and the leads in KL office. | 1. Different location. | 1. Poor quality of 3D model and Engineering deliverables, delay in 30% model review, 60% review and approved equipment layouts. |  | 14436 - Action Taken: Ensuring Contractors org charts are supported with CVs of the Sub contractors team members to ensure qualified and experienced personnel are mobilized. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6023 | Integration Factory Acceptance Test, iFAT was not carried out during FAT. | 1. Delay in Pre Com & Commissioning activity. | 1. Longer time required for troubleshooting & to integrate other party system. |  | 15884 - Action Taken: Vendors conducted integration activity at site. 15885 - Recommendation: Integration should be done at factory. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5929 | Inter-discipline review for any vendor equipment submission supposedly to be implemented throughout the Vendor Data Review stage | 1. No focal person from other discipline is dedicatedly assigned for vendor data review | 1. Inter-discipline review was not done properly and consistently. |  | 15713 - Action Taken: The related discipline who supposed to review the document, must stamp the document to prove that document has been satisfactorily reviewed by them. 15714 - Recommendation: All discipline has to appoint a focal person to be assigned as a reviewer for any related vendor data. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6187 | Interface communication with other contractors need to be more efficient in the form of frequent face to face meetings | 1. Delay in resolution of issues by interacting through emails | 1. Possible impact on rework of documents, extra cost and schedule impact |  | 16222 - Action Taken: Weekly / Bi-weekly meetings with other contractors on a regular basis | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5856 | Interface data was not updated during bidding stage. Utilized old data for Feed stock. Contractor didn't validate and finalize interface data Feed stock information | 1. Different design pressure at Battery Limit applied by FEED supplier to end user 2. Contractor didnt update and pass information to sub-contractor based on the new updated data | 1. Upgraded pipe rating and some purification section need to be designed for higher pressure |  | 15131 - Recommendation: To ensure any design development should be finalized timely and both parties (OWNER & Contractor) should agree and signed off the conditions 15132 - Recommendation: During bidding (prior award), another review of interface table to take place before concluding technical evaluation | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5226 | Interface issues between Structure, Architecture, Electrical, Instrument and HVAC in building construction. | 1. Late material arrival of certain equipment 2. HVAC requirement contra with building structural drawings 3. Simultaneous activity inside building | 1. Late handover from one discipline to the others 2. Reworks 3. Lower productivity and creating hazard at work area |  | 14303 - Action Taken: Coordinating interface meeting 14304 - Action Taken: Joint inspection | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Interface | 6201 | Interface with P14 | 1. Different Project execution time frame between P32 and P14. 2. EPCC did not proactively take charge to ensure P32 requirement met by P14 during initial stage. 3. EPCC (P32 & P14) lack of understanding of actual interfacing work. ie: LIMS 4. Different Directorate | 1. Gaps in P14 design execution and scope is not well define leading to attempt change order. 2. Delay and rework |  | 16256 - Action Taken: Provided information required during FEED at early Engineering to P14. 16257 - Recommendation: LIMS package should have been awarded to local capable vendor instead of vendor from abroad. 16258 - Recommendation: Execution phase should have started at the same time for P32 & P14. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Interface | 6200 | Interface with P22 (Punj Lloyd) | 1. Different Project execution time frame between P32 and P22. 2. Frequent change of P22 focal person 3. EPCC did not proactively take charge to ensure P32 requirement met by P22 during initial stage. 4. Project awarded during P22s execution phase which reflected additional work scope to P22 | 1. Gaps in P22 design execution and scope is not well define leading to change order. 2. P22 do not have continuity in work execution. Did not honour previous agreement. |  | 16251 - Action Taken: Provided information required during FEED at early Engineering to P22. 16252 - Action Taken: Execution phase should have started at the same time for P32 & P22. 16253 - Action Taken: EPCC to provide more detailed CP justification and Owner (P22) to review thoroughly. 16254 - Action Taken: EPCC to take the lead and organized interface meeting regularly. 16255 - Recommendation: Execution phase should have started at the same time. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6180 | Interfaces Data Management / Interfaces Data (BLIT Execution) | 1. Delayed Information and Data from P22 Interfaces (extreme low response) has resulted an inaccuracy within Piping Modelling. Interfaces Data may include Tie-in Coordinates, Specifications (PTS and PMRC MARS) used / modifications, general design philosophies, etc. | 1. BLIT was introduced and interfaces discussion had been conducted. Unfortunately, even with the presence of Client (PRPC) during the BLIT meeting, interfacing parties had not been giving their project/design information in time. |  | 16203 - Action Taken: Better controllability of BLIT 16204 - Recommendation: To consider descoping for non performance EPCC | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2073 | Interfacing and constraints due to delay in granting site possession (land acquisition matter) | -Delay in relocation of residents. (Bayu Damai) -Judicial review for individual lot -Cemetery relocation | -Delay in overall project completion -Cost overrun -Local Sensitivity | -suggest to segregate the affected area. -Release in stages -workfront | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5626 | Interfacing issues. | 1. Deliverables still pending for submission. 2. Demarcation of the boundaries is not clear between CONTRACTOR (OUI-JV and SC). 3. SOW was not clear between CONTRACTOR (OUI-JV and SC). | 1. Late submission of document. |  | 14936 - Action Taken: IPAD Closure. 14937 - Action Taken: Ongoing interfacing meeting as planned. 14938 - Action Taken: VC between OUI-JV, CONTRACTOR and OWNER. 14939 - Action Taken: Face to Face meeting took place at the CONTRACTOR Office. 14940 - Recommendation: Close monitoring and frequent follow up with Interfacing Mgr. and Project Manager. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Construction | 6258 | Interruption on tank erection works. | 1. Sub-contract between EPCC & tank contractor not appropriate for RAPID requirement. | 1. Schedule impact. 2. Cost impact to EPCC. |  | 16382 - Action Taken: EPCC took responsibility for any additional RAPID requirement. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5259 | IPMT Site team is not aware of signed and commented FTQ/DCN that have been reviewed by Engineering Team. | 1. No distribution by DCC | 1. For FTQ - IPMT Site Team is not aware if the proposed solution by Contractor is accepted by IPMT Engineering. For DCN - IPMT Site is not aware of any comments given by IPMT Engineering. This could result in non-compliance in construction if Contractor do not follow IPMTs comments |  | 14360 - Action Taken: Distribution system should be established by DCC to include notification for Site Team when DCC return the document to Contractor | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Project Management | 5413 | Issuance of Job Bulletin / Memo at late engineering stage and some during construction. | 1. Engineering changes. | 1. Variation Order. |  | 14478 - Action Taken: Implementation subject to cost and schedule impact for each packages. 14479 - Action Taken: Consolidate all the RC packages impact and response to Core Engineering. 14480 - Recommendation: To limit changes at end of engineering phase. 14481 - Recommendation: Core Engineering to present to Technical Change Committee (TCC) prior to execution by UPT. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5635 | Issuance of Job Bulletin upon award of package. | 1. Job bulletin are issued to supplement specification. | 1. Potential change order. |  | 14959 - Action Taken: Communicated with CONTRACTOR to implement in design. 14960 - Recommendation: To include in the ITB. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Award/Contract | 5519 | Issuance of LLI ITB to the wrong bidder | 1. Contractor did not follow the contractor list as per PRPC tender plan. 2. Confusion on similar vendors name i.e. Belleli vs. Bellelli | 1. Deviation to Tender Plan 2. Loss of potential competitive bidders. |  | 14674 - Recommendation: OWNER to thoroughly review and validate FEED contractors bidder information | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5453 | Issuance of SmartPlant Seed Files (patches) | 1. There is no latest date for SmartPlant seed files issuance. | 1. Delay in 3D Model |  | 14567 - Recommendation: Latest date of SmartPlant seed files issuance shall be indicated. Otherwise engineering cannot be frozen. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5756 | Issuance of technical specification by EPCC. | 1. EPCC Contractor declined to issue Technical Specification as ITB Project Specification is available and deemed sufficient for requisitions and procurement activities. | 1. EPCCs hesitancy to issue Technical Specification to optimize engineering man hour, causing late issuance of Technical Specification. |  | 15347 - Action Taken: Multiple clarifications done with EPCC Contractor, identifying contractual requirement and technical risk of not issuing technical specification, resulting in issuance of Technical Specification. 15348 - Recommendation: Clarification during bidding is required specifically identifying the requirement to issue Technical Specification to avoid lengthy argument during execution. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | HSSE | 5878 | It’s observed that during HAZOP for Process and Packages, correction on the P&IDs are required. | 1. The P&IDs not adequately review by Contractor and late submission to UPT prior to HAZOP. Some P&IDs only have red-line mark- up. There are a case where P&IDs not submitted to UPT for review. Change of the design of main process | 1. Drawing error may lead to wrongly analyzing the hazard and consequences as well as making recommendation 2. Lead to loss of focus during HAZOP where participants intended to discuss on the design. 3. Need to re- HAZOP the related process line while conducting HAZOP for Packages |  | 15164 - Recommendation: Ensure that P&IDs were properly review by Contractor and PETRONAS prior to proceed with HAZOP | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Project Management | 5993 | ITB not clearly stated on specific requirement | 1. Some crucial PTS requirement was removed from ITB i.e. trench | 1. Reworks 2. Long term maintenance |  | 15830 - Recommendation: Comprehensive functional ITB description | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5963 | ITB requirement stated contractor should carry out Smooth Start-up Program (SPP) however there is no sample attached on the guideline of SSP. EPCC may be able to produce their own version of SSP | 1. No guidelines/sample in ITB for SSP process | 1. Delay in project execution as EPCC takes time to understand |  | 15791 - Recommendation: To include SPP process/guidelines in the ITB | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5674 | ITB requirement Type of Construction - Outside screw and yoke, Type of bonnet/cover - Screwed for gate valve, Spring Ball Type below 50DN for check valve. | 1. There is no vendor to comply those requirement. 2. PTS specification is come from Shell specification. Some part is not updated latest situation of EPC business. | 1. SC has prepared production range for every bidder and explained that bidders of RAPID PJT are in the 1st, 2nd place for the bronze valve and they are supplying to other pkg also. |  | 15072 - Action Taken: If ITB requirement shows high specification compared with other project, issue the quotation earlier than usual and consider the time to check capability of bidder in advance. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Quality | 5414 | ITP for package equipment not properly reviewed. | 1. Focal point for quality not available. 2. Earlier arrangement of Third Party Inspection (TPI) being managed by directorate team without the proper notification to the UPT. | 1. iPMT / main contractor responsibilities during fabrication of these equipment are not properly defined. 2. Quality inspection totally dependent to third party contractor inspector. |  | 14482 - Action Taken: PMC established SQS (under quality central directorate) as the centralized body to govern quality. 14483 - Action Taken: UPT direct involvement via focal point to ensure compliance to project specifications and proper review are being done. 14484 - Recommendation: Standardize a minimum ITP for overall RAPID. Any additional EPCC requirements will supplement the minimum ITP. 14485 - Recommendation: Early appointment of quality focal point in UPT. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Interface | 6074 | JKR road widening side by side with PAMER (ROW). | 1. Late finalization by JKR on the widening of road reserve. | 1. Soil erosion. 2. Drainage blockage. |  | 15663 - Action Taken: Owner complained to JKR. 15664 - Action Taken: JKR lowered their culvered invert level. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5231 | Joint integrity due to flooding, material handling | 1. Poor drainage 2. Late backfilling 3. Poor workmanship | 1. Delay the construction 2. Rework 3. Waste of material |  | 14312 - Action Taken: Increase water pump 14313 - Action Taken: Introduced partial backfilling 14314 - Action Taken: Review SOP, multiple pre-heat at joints | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5086 | Lack of active participation in various workshops like HAZOP,IPF, ECA,etc | 1. Limited/lack of experience within contractors team 2. No operational background 3. Clash of important HSE and Engineering study that required participation from all discipline engineer | 1. Over reliance to IPMT engineers to provide input 2. Incomplete initial design, leading to longer discussion to closure 3. Reschedule the workshops |  | 14156 - Action Taken: Established platform to get mutual understanding on the requirements of the having the workshop. 14157 - Recommendation: Contractor to actively contribute during the meeting/review/workshop to ensure the scenarios are fully understood. 14158 - Recommendation: To ensure proper schedule and fully participation of key personnel from OWNER and EPCC | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Quality | 5650 | Lack of Awareness on RAPID PMC Plan, procedures & guidelines for UPT Project Team by Directorate Quality. | 1. Project Staff unaware of PMC Plan & Procedures - breadth and depthness for the work execution. | 1. Project team referred to wrong procedures for project implementation. E.g. Technical Query. 2. Unaware of the latest inspection requirement specific for RAPID project. |  | 15005 - Action Taken: Communicated with Quality Dept of GPD PD&T to address the requirement in PTS Project Quality Management. 15006 - Action Taken: Communicated with RAPID SME (Subject Matter Expert) team on the latest project requirements. 15007 - Recommendation: PTS for Project Quality Management need to be in established. 15008 - Recommendation: To ensure Project Quality Leader employed have vast knowledge on Project Quality Implementation for project of this scale. 15009 - Recommendation: Planning for Project Quality Implementation need to be embedded for every PETRONAS projects. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Procurement | 6232 | Lack of communication between local and oversea freight forwarders during early stage | 1. Unfamiliar between local and oversea forwarders. | 1. Schedule impact. |  | 16344 - Action Taken: Intervention by Owner. 16345 - Action Taken: Frequent engagement between all parties during early stage. 16346 - Recommendation: Frequent engagement between all parties during early stage. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5103 | Lack of communication detail between analyser / DCS / AMADAS | 1. The detail requirements of communication are not specified in Project specifications. It only mentioned to be discussed during detail design stage. | 1. After the detail has been finalized by Owner / PMC / CCSM / vendor, there is an additional cost raised from vendor to CCSM. |  | 14199 - Action Taken: Since there is no specific requirement in project specifications, CCSM / vendor proceeded with vendor standard first. But after long discussion and change, the design of this portion was hold until it finalized. 14200 - Recommendation: The detail requirements shall be specified in Project specifications in order to let all EPCs / vendors to follow and design in the same standard. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Project Management | 6307 | Lack of coordination between design engineer and site office | 1. OWNER / PMC did not have a dedicated Field Engineer, full time on site | 1. Late confirmation |  | 16476 - Action Taken: Home office provided an engineer for on and off basis 16477 - Recommendation: A full time field time is required to support the site team | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Award/Contract | 5653 | Lack of coordination on Subcontracting Work Execution conformance to the CONTRACT requirements. | 1. Misunderstanding by the SUB-CONTRACTOR. 2. SUB-CONTRACTOR try to minimize the liability on the defect. | 1. CONTRACTOR misalignment on warranty issues between OWNER and SUB-CONTRACTORS. 2. OWNER may run in difficulty to get the CONTRACTOR reliable on warranty issue. |  | 15017 - Action Taken: Incorporating in Subcontracting Plan. 15018 - Action Taken: Early award and execution of work at site. 15019 - Recommendation: CONTRACTORs understanding of OWNERs expectations post Final Acceptance. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5093 | Lack of co-ordination within contractors disciplines / organisation structure (project management) | 1. The roles and responsibilities for the disciplines in contractors organisation needs to be addressed seriously. | 1. Sub-standard and incomplete work offered for PMC review e.g. DCS graphics. |  | 14173 - Recommendation: Do not accept to review untill minimum level of completeness and quality is achieved. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5703 | Lack of detailed information especially on the equipment sizes. Strict optimization and plot was locked based on insufficient information / normal industry practice. Changed from Licensors requirement to PTS requirement during detailed engineering. | 1. Stringent PTS requirements 2. Insufficient information 3. Discrepancies between PETCHEM industry practice and PTS | 1. Further expansion of battery limit required during engineering stage 2. Delay in 90% 3D Model Review |  | 15089 - Recommendation: PPMS Gate Review to be done during FEED 15090 - Recommendation: PTS shall be flexible/adoptive to the Licensors requirements 15091 - Recommendation: Gaps identification between those 2 requirements done at early stage of the project 15092 - Action Taken: Issued PDR 15093 - Action Taken: Rigorous follow up by engineering team 15094 - Action Taken: Prioritization of the findings according to the criticality 15095 - Action Taken: Conducted counter- measure assessment to meet overall schedule as per requirements | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Document Management | 6321 | Lack of documentation management | 1. It was found that the Contractor document is missing/damaged. | 1. Unable to Handover |  | 16501 - Action Taken: Retraced and reproduce the document if found missing 16502 - Recommendation: System of archived need to be established. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Engineering | 6288 | Lack of effective design coordinator (OWNER & contractor) | 1. Lack of coordination | 1. Schedule delay |  | 16438 - Action Taken: Ensured appointed design coordinator present 16439 - Recommendation: To ensure design coordinator post present in the org chart from beginning of the project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Undefined | 5996 | Lack of EPCCs Project Control personnel. | 1. Contractor out-sourced project control function to another Company. Own staffs were occupied with other projects. 2. Only 1 person assigned to undertake all tasks. | 1. Submission of PC deliverables delayed with sub-standard quality. 2. PC personnel did not get enough support from other disciplines/JV Company. 3. Continuity affected due to change in personnel during the course of execution. |  | 15832 - Action Taken: Issued letter for Contractor to add PC personnel and the same was highlighted in Sponsors meeting. 15833 - Recommendation: Joint discussion between PMC and Contractor held. 15834 - Recommendation: Preliminary quantities of key commodities to be submitted by Bidder during bidding stage. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | HSSE | 5276 | Lack of experience and fresh Site Safety Supervisors from the sub-contractors side. | 1. Poor problem solving skills and hazard identification. 2. Lack of legal requirements knowledge. | 1. Unable to advice the sub-contractors management with regard to legal requirements. 2. Poor risk management and works coordination. |  | 14392 - Action Taken: To conduct sharing and compact workshop to all of the fresh Site Safety Supervisor. 14393 - Action Taken: To establish a Mentor-Mentee Program. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5840 | Lack of focus on planning and what required to be produced for engineering by contractor e.g. documents preparation and coordination | 1. Late finalization of Master Deliverable Register (MDR) | 1. Missing deliverables where some is required or pre- requisite for some activities not available 2. Difficult for the team to monitor the deliverables and delays 3. Difficulties in resource planning/ allocation due to late finalization of master deliverable list |  | 15097 - Recommendation: To agree, documented and approved MDR before the development of project schedule 15098 - Recommendation: To propose MDR to be part of progress payment milestone to contractor | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5843 | Lack of INC development / progress in 30% and 60% 3D Review. Major comments / findings by PMT & External reviewers. | 1. Lack of inter- discipline review by EPCC engineers. 2. Lack of supervision of EPCC Eng Manager. 3. Late finalization of design due to incompetent engineers in the project. 4. Lack of aggressiveness to complete and satisfy the 3D review session by EPCC engineers. 5. Lack of stewardship among EPCC lead engineers for Inter- discipline check (IDC) | 1. Major findings during the session. 2. Incomplete check / review on INC item in the 3D review. |  | 15103 - Recommendation: PMT Eng requested on separate 3D review session for INSTRUMENTATION. 15104 - Recommendation: Propose on Major Item by 30% and to include others by 60%. 15105 - Recommendation: To complete the INC 3D review for 90%. 15106 - Action taken: Conducted at 75% Model Review dedicated for the E | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2099 | Lack of infra support (internet connectivity) to POL system | Poor internet connectivity within RAPID site | Download / upload doc problem | Contractor has setup office off site RAPID in order to have better internet connectivity (streamyx). | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Quality | 6274 | Lack of inspection coordination by EPCC | 1. No dedicated competent QC inspectors. | 1. Multi tasking for EPCC personnel. 2. Integrity issues (no check and balance). |  | 16406 - Action Taken: PMT appointed additional inspectors. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Interface | 5425 | Lack of integration amongst packages on Engineering issues. | 1. Unavailability of a common engineering discussion platform under RC. | 1. Common issues that had been resolve by other packages have not been shared to other packages. |  | 14512 - Action Taken: Conducted a weekly RC Engineering meeting to discuss on common issues. 14513 - Recommendation: To have engineering meeting amongst the RC packages at early stage. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6013 | Lack of inter-discipline check | 1. Pipe clashing during installation | 1. Poor execution of 3D model review contribute to rework on Piping works more than 20%. |  | 15864 - Action Taken: Rework 15865 - Recommendation: Clash check during model review and revise isometric accordingly | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5239 | Lack of manpower and machinery |  | 1. Delay the construction 2. Not achieving construction target |  | 14329 - Action Taken: Increase manpower and machinery 14330 - Action Taken: Increase productivity rate 14331 - Action Taken: Introduce automated welding machine | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Construction | 6291 | Lack of manpower plan in the initial stage of the project. | 1. Late award to subcontractor | 1. Unable to start work |  | 16444 - Action Taken: Expedited the subcontracting plan 16445 - Recommendation: To ensure contractor different in house subcontractor | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Construction | 6292 | Lack of permitting manpower in the initial stage of the project. | 1. Permitting problem from the authorities for foreign labor. | 1. Unable to start work 2. Schedule delay |  | 16446 - Action Taken: Worked closely with relevant authority. 16447 - Recommendation: Project to identify total number of workers and categories of specialization. 16448 - Recommendation: To liaise with relevant authority prior to start work. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Quality | 5281 | Lack of preservation of uncoated bolt and nuts | 1. Damage SS/DSS material as not clearly stated in drawing | 1. Bolt and nut become rusty. Required cleaning or replacement of flange and bolt and nut |  | 14396 - Action Taken: To detail in AFC drawing on requirementTo specify clear requirement for bolt/nut protection from corrosion before operation in Project Specs. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5083 | Lack of skills/knowledge/experience by Contractor, teamwork is crucial in resolving issues within the agreed timeframe. | 1. Limited experince within contractor engineers 2. Unfamiliarity of the PTS requirements 3. Language barrier between EPCC and OWNER | 1. Increase in number of rework 2. Misunderstanding on the project requirements |  | 14108 - Action Taken: Hand holding to ensure correct understanding in project requirement 14109 - Recommendation: To work together with Contractor, focus to solve the problem and consequently close the issue. 14110 - Recommendation: May not necessarily to open another issue on top of existing issue. 14111 - Recommendation: To provide clear and precise instruction to Contractor to avoid any miscommunication. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2090 | Lack of supporting documents for claim processing | -Problem to close Request For Inspection notice due to delay report from 3rd party geotechnical lab. -Limited of independent Lab Testing in Johor | Contractor cannot claim for actual work done until the RFI closed. | PMC requested the approved testing labs to increase their resources and facilities. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5092 | Lack of technical analysis in studies / issues | 1. Contractor just passing off the Vendors or Licensors information to PMC without adequate technical analysis 2. Contractor not getting further clarification with the Licensor 3. Lack of details by Licensor in providing the technical query respond | 1. Contractors casual approach is a matter of worry as PMC has to intervene every time on such issues which otherwise is the primary responsibility of the contractor. 2. Rework 3. Potential schedule delay 4. Potential cost impact |  | 14171 - Insist on the contractors role, responsibility and accountability. 14172 - Conducted discussion between Contractor, CORE engineering team, Licensor and OWNER to get better understanding for the acceptance | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5089 | Lack of understanding on P-Risk Based Inspection (RBI) process that created delay of respond from vendor to P-RBI vendor | 1. Lack of understanding on PRBI requirement 2. Lack of attention given to the studies requirement | 1. Delay response from PRBI vendor and resulting late in report finalisation |  | 14164 - To well explained the requirement of P-RBI and how the importance of the readiness of the sub-system of P-RBI to construction phase e.g.: TML marking, cathodic protection, corrosion coupon location. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | HSSE | 5274 | Last minute deployment of local subcontractors and vendors’ personnel. | 1. Poor work planning from the EPCC and sub-contractors in the sense of mobilization and deployment. | 1. Vendors and subcontractors personnel tend to manipulate the security access and tend to pretend as visitors. |  | 14388 - Action Taken: To ensure that all works shall be planned and local workers shall possess valid CIDB Green Card prior to mobilization. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5783 | Late appointment of Operations Team and leader. |  | 1. Inputs from operation team coming at advance stage of engineering. |  | 15410 - Action Taken: Commissioning team to play bridging role. 15411 - Action Taken: Involved O&M representative in audit and design workshop session. 15412 - Recommendation: Much better for this to be done at time of approval of ITB scope of work and specification, and to be involved in bid technical evaluations. 15413 - Recommendation: To have permanent O&M attached to PMT. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5384 | Late changes by PEPI after closure of Engineering Office. | 1. Major changes keep on happening after closure of engineering office such as SRU stack bellows, Caustic injection pumps, WHB Tubesheet which was not closed by process properly. | 1. Safety issues if not properly reviewed. |  | 14422 - Action Taken: Closing the DCN notice while evaluating the impact to the progress. 14423 - Action Taken: Engineering team was maintained from engineering to construction phase to ensure continuity. 14424 - Recommendation: To maintain the same team from engineering to construction to ensure continuity. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5958 | Late completion of commissioning docs. - Procedures should be completed 3 months before commissioning start | 1. Ineffective Contractors commissioning manager in producing the documents due to unfamiliarity with procedures | 1. Documents submission completed 4 months after commissioning started, with close monitoring by PMC |  | 15771 - Action Taken: Instructed contractor to engage external parties for document writing. 15772 - Action Taken: Mobilize contractor document writer to PMC office to work together with discipline engineers in order to minimize revision 15773 - Recommendation: More stringent interview session and technical requirement specified in ITB for selection of key position (i.e. commissioning manager) 15774 - Recommendation: Lack of comments from identified reviewers based on system distribution matrix 15775 - Recommendation: Late comments (after consolidated) 15776 - Recommendation: Late and unsatisfying resubmission | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5959 | Late completion of training as per schedule and before Handover phase | 1. Late construction completion causing On Job Training(OJT) unable to be done. Only classroom training conducted which received unsatisfactory feedback from participant | 1. Frequent revision of training list causing difficulty in coordinating schedule with vendors and additional cost incurred |  | 15777 - Action Taken: Recall vendor that conducted classroom training only to also do OJT 15778 - Action Taken: Communicate with all parties to finalize training list before handover 15779 - Action Taken: Conduct in-house training to minimize additional cost for re-calling vendor 15780 - Recommendation: Training should only started when construction and pre-commissioning of system completed 15781 - Recommendation: Training agenda should be reviewed by all parties before finalizing training list | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Procurement | 6324 | Late confirmation by OWNER of specialist IT equipment (switches, servers) | 1. Discrepencies between ITB specs and finalized design | 1. Schedule delay |  | 16507 - Action Taken: OWNER through PMC ICT took over scope of procurement and installation 16508 - Recommendation: To explore the free issue materials or equipment for specialized items | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Engineering | 6286 | Late confirmation by OWNER on the drainage outfall | 1. Frequent changes by OWNER on the outfall design to suit the overall RAPID drainage system. | 1. Schedule delay |  | 16434 - Action Taken: Re-phassing the construction works. 16435 - Recommendation: Fundamental design parameters to be finalised before issuance of tender. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Procurement | 6236 | Late delivery of cable tray | 1. Procurement of cable tray under E&I subcontractor. 2. Subcontractor placed order after contract awarded. | 1. Schedule impact. |  | 16351 - Action Taken: Expedited subcontractor to meet the schedule. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5546 | Late delivery of concrete for continuous concreting work. | 1. Lafarge prioritize large concrete amount supply for other packages. Concrete supply for P6A package was delivered at late time of a day. | 1. Interruption of concreting work. |  | 14747 - Action Taken: Early notification given to the batching plant coordinator prior to concreting schedule. 14748 - Action Taken: Recommended to CONTRACTOR to record the proof of deliveries to monitor Lafarge supply. 14749 - Recommendation: CONTRACTOR to establish regular coordination with batching plant in anticipation of delay. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5859 | Late design change and unnecessary PDR e.g. contractor assume and do not go to specific details requirements. Hence deviations could be the result. | 1. EPCC Contractor ignorance of project specific requirements or PTS. 2. EPCC failed to take seriously information by OWNER. Relied more on their experience (Underestimate of PTS requirements) | 1. Project non- compliance 2. Issuance of PDR which caused longer time for approval process |  | 15136 - Recommendation: Realignment of PTS and industry practice to be conducted between contractor and Owner emphasize during Kick-off project meeting 15137 - Action Taken: Issued PDR | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5839 | Late design change and unnecessary vendor PDR (VCR) | 1. Late sharing of vendor documents by EPCC | 1. Non- compliance to project specification 2. Delay in delivery of the material to site |  | 15096 - Recommendation: Timely submission of document with plan to reflected in the project schedule in key documents. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | HSSE | 6002 | Late Engagement of Process Safety personnel from EPCC & PMC at early stage of Project | 1. Process Safety Engineer (Design) was engaged only few months after the design stage started. 2. No Process Safety Engineer engaged during Construction and Pre-commissioning phase. | 1. The safety system design (engineering documents) wasnt being reviewed during the first and even second revision of engineering design stage as no Process Safety Engineer available. No representative from Process Safety:- - to reply on the TEQ. - to follow up on the close out of safety related workshops/ audits. - to handle process safety related issues at Site. |  | 15843 - Action Taken: Started to review the safety system design when the incumbent was on board. 15844 - Recommendation: Process Safety Engineer must be engaged at the start of the Project. Do it right at the first time | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5779 | Late EPC stage change for EOEG to provide tanker loading facilities for butadiene loading was difficult to solve technically. | 1. Lack of information about the customer’s transport tankers, and came too late in the schedule so inevitably delayed numerous common deliverable items for the main project. The reason was again due to late changes in the Petchem complex configuration. | 1. The perception from EOEG viewpoint was that the lack of viability of certain Petchem units must have been visible and calculable at a much earlier stage, and waiting until EPC companies have spent heavily to bid the project before eventually cancelling it is actually a high risk way to proceed. |  | 15399 - Action Taken: Change order issuance. 15400 - Action Taken: Extend PMT and EPCC resources. 15401 - Action Taken: Visited to butadiene customer facilities. 15402 - Recommendation: The FEL 1 and FEL 2 Gates should have been applied much more strictly and rigorously than they were in practice. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2089 | Late final handing over document for project closure | Underestimate of final handing over docs requirement. | Delay in Project closure | -Start preparing the final doc from early project stage. -Engage dedicated team to do final document from start project with close monitoring | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Project Management | 5869 | Late finalization of Project Master Document Register (MDR) (more than 6 months) | 1. Overall Deliverable List C.D + 30 days and Further updates shall be provided through the Master Document Register | 1. Late finalization of PEDMS DDM |  | 15152 - Recommendation: MDR to be part of project Milestone Payment | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5752 | Late formalization of integrated contract details e.g. Telecom Integrator (TI). | 1. Telecommunication scope of work and engineering design is still ongoing, with Job Bulletin issued during EPCC execution. | 1. Impacting EPCC execution due to contractual scoping (variance to original scope). |  | 15338 - Action Taken: Core Engineering expedited the scope of work and engineering design, with alignment done at UPT levels to facilitate execution. 15339 - Recommendation: Central level integration contract and engineering design to be established prior to EPCC execution. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5385 | Late highlight of design issues. | 1. PEPI late information on major changes as above has lead to schedule impact which if has been taken cared of earlier will minimize this impact. As review was done by leads in KL, this leads to overlook of issues until approval. | 1. Safety issues if not properly reviewed. 2. Schedule impact. |  | 14425 - Action Taken: Minimized the TEQ which impacted major Engineering before mobilizing to site. 14426 - Recommendation: Ensure continuity and collaboration between other packages and core engineering. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Quality | 5651 | Late hiring of Quality inspection support by PMC. | 1. Unclear roles and responsibilities on the Quality inspection between UPTs and PMC due to iPMT formation. | 1. UPTs Inspectors are over worked and lost focus to own projects. 2. Some UPTs has to rely on Inspectors from other packages. |  | 15010 - Action Taken: Provide input to PRPC & Petchem management and GPD Quality management. 15011 - Recommendation: To structure a standard way to manage projects inspection. 15012 - Recommendation: To provide clear roles and responsibilities between PMC and UPTs. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B2-MOLF RAMUNIA | IO-P20B2-MOLF RAMUNIA | Quality | 6099 | Late in compliance with Project Quality requirements | 1. Quality control was not acting as independent party. 2. The engineering consultant was not in control and set quality goal for the construction work. 3. Contractor management lack of participation in the quality complaint 4. Contractor was not familiar with Petronass requirement | 1. Repairing work and touch up work were required at the beginning of the project 2. Documentation quality not in order at the early stage |  | 15528 - Action Taken: Owner guided Contractor on quality requirements 15529 - Action Taken: Owner demanded Contractors top management commitment in QAQC 15530 - Action Taken: Quality Procedure was set up 15531 - Action Taken: Close monitoring work | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Document Management | 6319 | Late in correspondent sending and receiving | 1. There is no online system in the initial stage of the project. Hand delivery | 1. Late in communication |  | 16500 - Action Taken: Delivery by Hand and regular meeting | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Project Management | 6359 | Late in increasing manpower loading to meet tight engineering schedule (e.g. civil, piping, electrical & instrument) | 1. Tight schedule. | 1. Schedule impact. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5482 | Late information for Surge Analysis Definition. | 1. The philosophy of Surge Analysis is not defined at early stage | 1. Rework |  | 14608 - Action Taken: Issuance of project memo 14609 - Recommendation: Define the philosophy in the ITB. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Interface | 5524 | Late information regarding the interfaces with other EPCC’s due to frequent changes of scopes by other existing EPCCs | 1. Lack of communication between EPCCs with regards to interfaces 2. Poor interfaces integration between EPCCs 3. Tendency of packages to work in silo 4. The fact that EURO 5 Mogas came late while other existing EPCC are already in progress | 1. The impact is not only to piping, but also the civil disiplines and more specifically the latest updated 3D model of the adjacent units/areas. 2. Example: Piping routing for P-30 EPCC package is interfering with P-28 package in P-28 storage area. 3. Example: The information of the location of the CNHT-2 piping tie-ins, as per P-3 EPCC study, came too late to be incorporated into the IPS deliverables |  | 14683 - Action taken: Appointed dedicated personnel to monitor and keep updating the interfaces changes by other EPCCs 14684 - Recommendation: To ensure only minimum design changes allowed when project is in progress 14685 - Recommendation: To have ahead discussions on the interfaces | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6339 | Late issuance of critical vendor drawing | 1. Late PO issuance. | 1. Schedule impact. 2. Impact to civil to issue IFC drawing for equipment foundation. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Construction | 6257 | Late issuance of materials and piping ISO release | 1. Depending on CMS Database by EPCC. 2. Only 1 focal personel to issue the release. | 1. Schedule impact. |  | 16380 - Action Taken: Weekly meeting to monitor the progress. 16381 - Action Taken: Identified upfront materials readiness prior to fabrication sequence. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5477 | Late issuance of Model Review Checklist | 1. Model Review Checklist is not Available at earlier stage | 1. Conflicts of reference during Model Review |  | 14600 - Action Taken: Provided Model Review Checklist as per RAPID Memorandum RAPID-P0024-PMC-PMG-MEM-0098 (3D Model Review Checklist) | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5390 | Late issuance of Pipe support standard. | 1. PEPI delay in issuance of standard. 2. Lack of resources. | 1. Delay in issuance of ISO. 2. Delay in fabrication. |  | 14434 - Action Taken: Expediting issuance of ISO. 14435 - Recommendation: Timely issuance of this document could have saved several man-hours wasted due to rework in modelling. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Procurement | 5509 | Late issuance of RFP by FEED contractor in the EPC business as compared to initial schedule | 1. Contractor not familiar with PRPC procurement system and pending PRPC direction to issue the RFP. | 1. Delay in finalising LLI procurement items. 2. Impact schedule delivery |  | 14655 - Action Taken: Expedited the evaluation process to meet schedule 14656 - Recommendation: To brief FEED contractor on OWNER requirements at the early stage of project 14657 - Recommendation: FEED contractor to select/appoint right personnel (experience and competent) | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5463 | Late issuance of System Integration Procedure | 1. There is a detailed procedure for Interface, but the Integration procedure was only issued after several months of the project. | 1. Many issues involving other EPCCs cannot be resolved |  | 14582 - Recommendation: The procedure shall be issued the earliest possible. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5473 | Late issuance of Vendor Data Book & Manufacturing Data Report | 1. Vendor Data Book & Manufacturing Data Report not available. | 1. Late compilation activity (submission by 3months before PA) |  | 14595 - Recommendation: To provide Typical Index / Content of Vendor Data Book and Vendor Manufacturing Data Book. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5229 | Late material delivery i.e. lamination kit for UG | 1. Mis-management of material stock take | 1. Delay the construction |  | 14308 - Action Taken: Purchase extra material by adding to the construction contingency 14309 - Action Taken: Air freight material | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5441 | Late Mobilization of Discipline Head and Discipline Engineers during early stage of Engineering. Engineering Manager resigned after KOM and no replacement for 2 months. Only 2 - 3 Discipline Leads remained after the KOM. | 1. EPCC is not strong in Engineering. EPCC fully subsidiary engineering arm, Punj Lloyd Engineering (PLE) has insufficient manpower during the early stage and EPCC had to source workforce after the KOM. | 1. Late start of Engineering. Progress could only be seen after 3 - 4 months after KOM. |  | 14543 - Action Taken: Provide guidance to EPCC to move the Engineering progress. 14544 - Recommendation: Selection of CONTRACTOR with strong financial capability. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Project Management | 6249 | Late mobilization of EPCC key personnel | 1. Late permit approval. 2. Change of proposed personel. | 1. Late decision making. |  | 16368 - Action Taken: Multi tasking by EPCC. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Quality | 5871 | Late mobilization of EPCC Quality ‘required’ personnel (Site Quality Manager & Civil Inspector) to site | 1. Lack of interpretation of contract requirement relevant to site quality personnel. Sec C, Part II - “…shall be mobilized within one (1) month after EFFECTIVE DATE.” | 1. Improper arrangement of Quality upfront activities including; 2. Late approval of Site Quality Plan 3. 2nd Site Quality Meeting has delayed for almost 30 days 4. Delaying other site Quality Program (e.g. Site Quality Walkabout, Quality Surveillance, Quality day and etc.) |  | 15154 - Recommendation: To mobilize the key person for current activities i.e. Site Quality Manager & Civil Inspector 15155 - Recommendation: Early planning on manpower mob-demob | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Award/Contract | 6301 | Late mobilization of equipment | 1. Poor subcontracting - equipment such as piling not deliver on time | 1. Schedule delay |  | 16467 - Action Taken: Mobilized additional sub-contractor 16468 - Recommendation: To perform resources assessment prior to the award. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5442 | Late Mobilization of Field Engineers to Site & Contractor Field Engineers during field engineering phase | 1. Field engineers not present at site despite construction is achieving more than 20% progress. 2. Difficulty to discuss with counterpart from contractor. | 1. This may result in quality issue. 2. May delay on the decision making. |  | 14545 - Recommendation: To specify the requirement in ITB. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Project Management | 6196 | Late mobilization of key personnel | 1. Limited resources from PD&T. 2. Unavailability of dedicated planner. | 1. Delay in doc submission. 2. Few PMG doc not as per requirements. 3. Unneccesary loading of project management works to other disciplines. 4. Overloading personnel with multiple tasks. 5. Compromise in document work quality and rework. 6. QAQC doc not update / not address the QAQC concern on the details task / not submitted/ delay. 7. No dedicated person to monitor / expedite / rationalize project progress. |  | 16234 - Action Taken: Engaged resources from core team 16235 - Action Taken: Ensure dedicated personnel take charge in each discipline / task. 16236 - Action Taken: Request each discipline to details out the list. 16237 - Action Taken: Ensure availability of dedicated planner at UPT office. 16238 - Recommendation: Recruit new experience team member 16239 - Recommendation: Consider recruitment from 3rd party | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Quality | 5648 | Late mobilization of Project Quality Team to project team. | 1. Delay in recruiting the quality engineer by HR due to HR received no official request from Project. | 1. Delay in mobilizing Project Quality Team has limited the Project Quality Manager (PQM) functions that should be focusing more on strategizing project quality implementation. |  | 14998 - Action Taken: Conducted TA early for Project Quality Team and requested PM to expedite the matter with HR. 14999 - Recommendation: To plan for early mobilization of Project Quality Team together with PQM for the projects together with other projects key personnel. 15000 - Recommendation: Must be implemented immediately for all PETRONAS future Projects. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | HSSE | 6313 | Late mobilize of safety personnel | 1. Delay in completing HSE procedure | 1. Holding back construction to start work 2. Schedule delay |  | 16488 - Action Taken: Mobilized experience HSE Manager 16489 - Recommendation: To have an experience HSE Manager | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Procurement | 5916 | Late of additional material delivery | 1. No coordinator managing bulk procurement materials 2. Procurement personnel not familiar with specification 3. MTO not freeze until very late and not communicated to procurement team | 1. All communication to Vendor done at Contractor main office that contribute late instruction to Vendor to attend meeting/assistant required at site. Ordering additional/shortage of Equipment/Material were done via main office |  | 15676 - Action Taken: OWNER/PMC full time Procurement Coordinator on daily basis expedite the matters by communicate directly with Contractor Procurement team. 15677 - Recommendation: Contractor Procurement team shall roll over to site after completion issuance purchase order to vendor | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2101 | Late of handover part of Zone 3 area | Delay of site preparation works due to villages relocation. | -Schedule slippage. -Low productivity | Redesign road allignment into free incumberances area. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5623 | Late Project Document templates finalization by RAPID Core. | 1. Late approve of issuance the final template (e.g. PETRONAS logo / PMC logo etc.). | 1. Conflict of project deliverables document template submitted by CONTRACTOR. 2. Observation for improvement by GPD audit team. |  | 14930 - Action Taken: Various discussion has be conducted with RAPID Document Manager to ensure the Project Document templates are fixed. 14931 - Action Taken: Various discussion has be conducted with RAPID Document Manager to ensure the Project Document templates are fixed. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6012 | Late purchase of integration software license (i.e. Modbus license for PLC packages) | 1. IFAT was not conducted at vendor factory. | 1. Interdisciplinary check was not carried out and resulting insufficient cable and also contribute delay to instrument control e.g. Poly and Sludge Package. 2. Delay on the loop check for ISAT |  | 15862 - Action Taken: The vendor provided demo modbus trial license. 15863 - Recommendation: To conduct the IFAT for each package PLCs with the MAC. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5470 | Late purchase of Systemization / Handing Over Software / etc. as required in ITB | 1. CONTRACTOR has not purchased the WINPCS software (handing over software) at the end of engineering phase. | 1. Delay in population of data for handing over |  | 14590 - Action Taken: EPCC has agreed to purchase Streamline software in replacement of WINPCS 14591 - Recommendation: The use of handing over software, such as WINPCS shall start towards the end of engineering phase, so that the data could be populated in advance. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5769 | Late redesign due to cost reductions items / PDRs. | 1. Value Engineering and cost savings initiative were not concluded during FEED. | 1. Many smaller cost negatives were nominal compared to the efforts of implementation and may off setted the savings (i.e.) 5 batches of PDRs prior to award. 2. Some large simple ones were cost effective. |  | 15378 - Recommendation: More critical SOW definition before ITB release (ROI vs CAPEX assessment). 15379 - Recommendation: Cost reductions should be carried out more selectively if required during bidding. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2093 | Late requirement by JKR for Road safety audit | Part of JKR requirement to gazette the road as public road | -Schedule and design impact to the project -Delay of road opening will cause delay J52 closure and site prep. Works. | Compliance to RSA mitigation plan | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Planning | 6272 | Late requirement by RAPID during execution phase - early N2 supply requirement for RC commissioning | 1. Change of scope from RC EPCC to ASU. | 1. Change order. 2. Compressed schedule. 3. Cost impact. |  | 16404 - Action Taken: Expedite the new requirement after approval by JVco board. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Document Management | 5521 | Late respond of commented document review via P-EDMS | 1. Based on the initial setting of P-EDMS, Lead Mechanical was assigned as Consolidator, not as Reviewer in the system. The delays of any document review from other disciplines were not notified to Consolidator | 1. Delay of Document review 2. Late submission of some project documents |  | 14677 - Recommendation: To establsish SOP for number of days to respond | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5206 | Late respond to engineering drawing and technical query | 1. Unstable/slow internet connection | 1. Decision making process delayed |  | 14265 - Ensure during bidding stages EPCC to provide fast internet, to ensure timely engineering activity | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2091 | Late response for potential additional scope quotation requested by PMC/Owner | Contractor policy that centralized process and decision only can be made by their HQ. | Delay in Decision making. | -Expedite full support from HQ -Engage contract manager to expedite the process. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5263 | Late response from EPCC in decision making leading engineering issue is being settle for less due to meet project schedule | 1. Technical compliances found after PO 2.Found out in later stage of design and give way to meet project schedule. | 1. VO 2. Delay in schedule 3. Technical compliance on Project Specification and PTS 4. Maintenance issue during operation |  | 14367 - Action Taken: Alignment and understanding between SEG and PMC / Owner team (technically and working method) need to be periodically gauge to align back with target, between project management and working level. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5465 | Late response of TEQ by CORE team | 1. There was an instruction to discipline engineers that all TEQs need to be referred back to the core team. | 1. This has caused delay in many TEQ response to CONTRACTOR. |  | 14584 - Recommendation: Provide a more details guidelines on TEQs that need to be responded by the core team. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Construction | 6290 | Late site procession due to unsubmitted HSE document | 1. Unable to proceed HSE Document | 1.Schedule delay |  | 16442 - Action Taken: Submitted all HSE document stipulated in the contract 16443 - Recommendation: To ensure Contractor have all HSE document required by the ITB prior to the award. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5234 | Late start at prefab shop | 1. Late material delivery 2. Prefab shop not ready to start work 3. Late AFC issuance | 1. Delay the pre-fabrication |  | 14319 - Action Taken: Adjust fabrication sequence | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5253 | Late start for cable pulling work | 1. Engineering - changes of power cable drawing and cable schedule not finalized. 2. Civil - late cable trench handover due to weather, machinery and access issue. 3. Unclear work scope for subcontractors. 4. No priority list for cable delivery to site. | 1. Affect other discipline work progress (steel structure, AG & UG piping’s, Mechanical) due to open trench. 2. Delay pre-commissioning activities. |  | 14353 - Action Taken: Priorities cable pulling area and accept partially cable trench handover. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Document Management | 6070 | Late start in preparation of handling over document (e.g. checklist / punch list as-built). | 1. No dedicated QC person from consultant. 2. Poor planning from PCC contractor. | 1. Affect Initial Acceptance (IA) process. 2. Delay project. |  | 15656 - Action Taken: To conduct proper planning at the early stage of handover. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Construction | 6255 | Late start of piping fabrication due to unavailability of material. | 1. Material stranded at port. 2. Late COA approval. 3. Slow respond to mitigate late delivery (local sourcing). 4. Insufficient welders. | 1. Schedule impact (fab & filed). 2. Slow fabrication progress. |  | 16375 - Action Taken: Source from local supplier. 16376 - Action Taken: Additional manpower. 16377 - Action Taken: Dedicated full time construction manager at shop. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Construction | 6256 | Late start steel structural fabrication | 1. Late issuance of AFC drawing. | 1. Schedule impact. |  | 16378 - Action Taken: Expedited engineering to ensure AFC issued based on construction sequence. 16379 - Action Taken: Additional manpower at shop. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Project Management | 5991 | Late started with WINPCS system | 1. Unaware the requirement of turnover system ( WINPCS) 2. Late appointment of operators C8 | 1. Delayed readiness of check sheets 2. Insufficient time to prepare proper check sheet and system/subsystem review. |  | 15825 - Action Taken: PMC reminded contractor during the weekly meeting to appoint turnover system. 15826 - Recommendation: Contractor to appoint turnover software early during the project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6173 | Late study completion | 1. No simulation software. Eg: Aspen HYSYS, Pipenet | 1. Takes time and impact the dateline, especially when the third party license already due when document need to be updated |  | 16183 - Action Taken: Need to hire third party organisation. 16184 - Recommendation: In house software from contractor to be checked by project team prior award | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5660 | Late Submission of Baseline packages as per agreed timeline. | 1. Low quality of Level III schedule produced resulted in various submission / revisions that lead to the late finalization and establishment of overall Baseline packages. | 1. Delay in submission has impacted the overall tracking and monitoring / project progress reporting to Management. |  | 15033 - Action Taken: Conducted Schedule workshop between OWNER team and CONTRACTOR. 15034 - Action Taken: Continuous discussion and provides feedback to CONTRACTOR on the requirements. 15035 - Action Taken: Requested additional support from CONTRACTOR for the development and as quality control prior to submission. 15036 - Action Taken: Provided sample templates to understand the requirement. 15037 - Recommendation: Full experience and capable PCM from CONTRACTOR to lead on the development of the required deliverables as well as to conduct series of internal disciplines check prior to submission to OWNER. 15038 - Recommendation: To Consult with OWNER team prior to submissions. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B2-MOLF RAMUNIA | IO-P20B2-MOLF RAMUNIA | Construction | 6093 | Late submission of project documentation | 1. CONTRACTOR relied on third partys input to complete the method statement 2. CONTRACTOR was not familiar with PETRONAS requirement | 1. Late approval of documentation 2. Low quality in documentation |  | 15512 - Action Taken: Owners engagement to guide and assist the Contractor in the documentation 15513 - Recommendation: Recommend to scrutinize the contractors manpower and experience | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Construction | 6254 | Late submission of RT report | 1. Poor monitoring of report submission. | 1. High rejection number. 2. Slow improvement / mitigation. 3. Impact on the quality KPI. |  | 16372 - Action Taken: Daily monitor on welder performance update. 16373 - Action Taken: RT report submission a day after conducted the RT work. 16374 - Action Taken: NCR. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5662 | Late submission of Unpriced PO copies to OWNER for review. | 1. PO placement was delayed as their in-house system is not ready. | 1. Contractor issued LOIs to vendor instead of PO placement. 2. Some discrepancies in delivery schedule as well when compared to LOI. |  | 15041 - Action Taken: Close monitoring of PO dates with respect to LOI dates for any shift. 15042 - Action Taken: Follow-up with contractor to improve delivery dates. 15043 - Action Taken: Informed contractor to submit all POS through PEDMS for all Disciplines review. 15044 - Recommendation: Readiness of Contractor In-house procurement software to support issuance of POs on time to avoid discrepancy in delivery dates when compared to LOI. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5549 | Late supply of steel material at site for construction work. | 1. Steel material is pending due to COA. | 1. Sequence of work for steel structure installation needs to be revised and stopped several times due to unavailability of steel material. |  | 14758 - Action Taken: OWNER assisted CONTRACTOR to monitor on COA approval with Customs & CIDB. 14759 - Recommendation: CONTRACTOR shall able to communicate effectively with their fabricator for shipment planning based on construction sequence and priority list. 14760 - Recommendation: CONTRACTOR should have proactively identified these requirements in advance prior to shipment. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5230 | Late trench handover | 1. Civil sub-con has limited resources | 1. Delay the construction |  | 14310 - Action Taken: Additional resources 14311 - Action Taken: Prioritize trench handover | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5457 | Lead Engineers for EPCC shall be supported by senior engineers | 1. Insufficient support team at site | 1. Engineering documents being delayed |  | 14571 - Action Taken: OWNER / PMC facilitated in expediting engineering document closure | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Engineering | 6240 | Less involvement by Petronas during Engineering | 1. JV business model. 2. Engineering offices located at different regions. | 1. Minimum technological / knowledge transfer. |  | 16357 - Action Taken: Maximized involvement during stage gate review / design review. 16358 - Recommendation: Owner to be part of engineering team as capability building. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5775 | Licensor reviews. | 1. Insufficient scope of reviews (review limited to IFC deliverables / vendor print). 2. Licensor key resources are limited and sometimes busy / not available. | 1. Comments from licensor at advance stage of the project which pose design changes and schedule risk. |  | 15392 - Action Taken: Active engagement with licensor to mitigate technical issues and safeguard schedule. 15393 - Recommendation: Possibly more time should be allowed in schedule for reviews, and some reviews could be done earlier. 15394 - Recommendation: Need more negotiation with Licensor for their involvement in review of earlier revisions. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5616 | Lifting Plan was not available prior to delivery at site. | 1. Lifting plan for unloading at TCF warehouse Lot 141 was unavailable. | 1. Two cranes were repositioned twice in order to realign boom reach. 2. HSSE issue. |  | 14914 - Action Taken: Advise CONTRACTOR to provide all important documents prior delivery at site. 14915 - Recommendation: Method Statement should state clearly all the steps taken for lifting heavy equipment (including crane position at working area). | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5986 | Lightings design thorough plant not covering requirements of non-industrial area such as building corridors, entrance, process area at cooling tower and aerator | 1. EPCC failed to follow project specification/requirement 2. PMC engineering failed to address this requirement during review stage | 1. Poor lighting lux at the mentioned placed. Modification need to be done at the end of project stage |  | 15816 - Action Taken: PMC engineering to check in detail during review stage. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5925 | Lightning conductor test link shall be installed on building wall as per project drawing. | 1. Operator cannot conduct test on the lightning protection system conveniently whenever it is called upon to do so. | 1. Test link were not provided. |  | 15706 - Action Taken: To include the test link at site. 15707 - Recommendation: Contractor shall always refer to the approved drawings for installation works at site. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5455 | Lightning Protection for Floating roof tank not done | 1. EPCC engineer has no experience in doing it | 1. Delay in procurement of lightning protection materials |  | 14569 - Action Taken: Educated EPCC on how to do the lightning protection study | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6022 | Lightning protection test link not mounted as per drawing at external wall | 1. As per specification and standard test link has to be install at 1.5meter height | 1. Lightning down conductor (Y 10 rebar earthling) not projected out for connection before exiting to earthling chamber. |  | 15882 - Action Taken: Separate earthling straps has to be install to create for lightning test link to comply with specification 15883 - Recommendation: Test link plate has to install before column casting. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Interface | 6325 | Limit of work for fibre optic | 1. Scope and limit of work not clearly defined at early stage of project | 1. Scope and quality overrun 2. Schedule delay |  | 16509 - Action Taken: Works finalized during course of work 16510 - Recommendation: To engage and involve OWNER ICT at early stage of project | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5693 | Limitation of dummy support usage. | 1. As per ITB, dummy support cannot be used for corrosion risk. | 1. Basically, most of support has been changed from dummy to shoe and issued/confirmed PDR for the exception. |  | 15088 - Recommendation: ITB requirement is not aligned with general practice of contractor has to be discussed with OWNER in the bid stage or early stage of engineering to minimize design change. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5232 | Limited access due to construction sequence | 1. Poor planning | 1. Delay the construction |  | 14317 - Action Taken: Prioritizing construction works | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5237 | Limited laydown area | 1. Sharing with other materials | 1. Congested laydown area and slow down the spool segregation |  | 14324 - Action Taken: Increase additional laydown area | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5860 | Load Combination as per RAPID FE1 document | 1. Missing information and the basis of load combination does not reflect the requirement in MS / Eurocode. | 1. Cost and schedule impact. |  | 15138 - Recommendation: All missing information from FE1 documents to be used as project documents to be updated. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5690 | Location of manhole with Internal Arrangement | 1. Manhole location of suction KO drum was designed without consideration of internal arrangement in the early stage of engineering. | 1. Design was changed but it was not lead impact because it was found before manufacture. |  | 15087 - Action Taken: To minimize design change, study BP and LL in the early stage or engineering. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5402 | Logical Sequence: A large number of documents being issued for review before related precedent supporting documents have been issue. Such as required supporting document to review Process / Mechanical Deliverables. | 1. Desperation from EPCC to get approval before properly review the actual supporting documents. | 1. The quality of engineering deliverables may result in an unwanted negative impact on The Project due to rework. 2. Burden on the OWNER to review the supporting documents on behalf of EPCC. |  | 14451 - Action Taken: Contactor is advised to ensure that the issue of documents follows a logical sequence, as any premature documents issued which do not follow logical sequence to allow for effective review will be returned without review. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Procurement | 6230 | Long clearance for CIDB COA issue | 1. Underestimate CIDB COA requirement (EPCC decided without consulting PGSSB/LEMY). 2. No communication between Procurement team and site construction team. 3. Logistic coordinator based location away from site. 4. Additional testing done in Malaysia (SIRIM) which taking longer time. | 1. Schedule impact. |  | 16339 - Action Taken: Bought from local supplier. 16340 - Action Taken: Owner engaged with CIDB to expedite the process. 16341 - Recommendation: Preapprove mills list to be included in the ITB. 16342 - Recommendation: Prioritize to purchase from local supplier. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5241 | Long holidays |  | 1. Delay the construction due to lack of manpower (crane operator) |  | 14333 - Recommendation: To consider off-day during festive season in construction planning | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5492 | Long pending decision on PDR from Engineering CORE team | 1. PDR process flow is take few months to get endorsement by authorized party. | 1. A lot of rework need to be executed since early design has been approved and communicated to subcontractor / vendor. |  | 14622 - Recommendation: To speed up the design change process especially decision on technical aspects of changes. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Engineering | 6239 | Longer P&ID review session | 1. Too detail and many dwg pages. 2. Non standard compared to O&G. | 1. Additional review time |  | 16356 - Action Taken: Prioritize HAZOP review. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2074 | Low productivity during monsoon season against the forecast (Project Control) | -Unexpected heavy downpour in the 4th quarter of 2014 | -Delay in schedule | -Contigency plan for progress recovery -Mobilize additional sub contractor | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Project Management | 6048 | Lump sum with BQ better approach rather than Lump sum without BQ. | 1. Fast track. 2. Civil project with a lot of site prep & coordinator with authorities. | 1. More competitive bidding. 2. Less change order. |  | 15620 - Action Taken: More time for bidding. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Quality | 6317 | M&E coordination, pipe leaking, wrong termination, etc | 1. Insuffcient inspecting engineer from contractor | 1. NCR |  | 16496 - Action Taken: Rework 16497 - Recommendation: To provide sufficient inspector and to ensure the contractor issue coordinator services drawing prior to start work. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5479 | Machine Monitoring System (MMS) | 1. The requirement to have MMS was deleted from P-22 as value engineering due to cost saving initiative (offline monitoring) | 1. Cost saving but noncompliance to PTS requirements |  | 14603 - Recommendation: As this is a PTS requirement, further discussion is required if the MMS is to be deleted from the scope. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5212 | Machine Monitoring: During audit, it was found that some equipment (i.e. motors) are not being online monitored | 1. There are several discrepancies between project specifications (i.e. Rotating Specification, Instrument Specification, and Electrical Specification). For example, although the machine monitoring calls for monitoring, the electrical spec does not mention any monitoring based on power rating. | 1. Possible change order and VO 2. Impact during maintenance |  | 14275 - Recommendation: Each discipline spec should clearly mention the required instrumentation and should be consistent throughout the project. 14276 - Action Taken: Implement the audit findings. 14277 - Recommendation: Difference discipline specification need to be addressed in PTS. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5683 | Maintenance access for OSB | 1. Since the location of OSB is outside of process ISBL as per the contract, SC didnt provided any access way. SC has assumed it is the responsible of OUI, because the work scope is OUI between SC process area and OSB area. 2. During 3D model review, OWNER requested to SC to provide access way for OSB. | 1. SC Provide min, asphalt for compressor maintenance for access to HVAC rooms. (Not road, no drainage, no lighting, and etc. as per result of discussion with OWNER) |  | 15081 - Action Taken: The work scope and interface with other contractor has to be discuss and finalize in the bid stage or early stage of engineering to avoid late design change. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5676 | Maintenance space for fixed tube type heat exchanger | 1. For the fixed type H/Ex, PTS mentioned Sufficient space shall be provided for bonnet removal (bonnet length plus 1.5 meters). 2. There is difference to interpret between OWNER and SC for the starting point of space. | 1. SC has followed OWNERs comment and issue PDR for the exception. |  | 15074 - Action Taken: Try to find an ITB requirement that can be interpreted differently as per the view point of each person. If it is figured out, discuss with OWNER as soon as possible. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5208 | Major standardization between package to avoid discrepancies among RAPID package (i.e. ASME Code edition) | 1. Different standard being practiced across RAPID | 1. Different in maintenance practices |  | 14269 - More involvement from Core team to resolve standardization | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5845 | Manholes and drain location under pipe rack. New revised PTS stated that non-compliance to process safety requirement | 1. Update of latest PTS shall follow Process Safety Review requirement. 2. Old PTS in use for RAPID and project specification was not updated accordingly. | 1. Schedule and cost impact since HSE PTA wants the new PTS to be followed. |  | 15110 - Recommendation: All required and mandatory changes should be updated in the RAPID project specification and documentation to reflect OWNER’s stand in mandatory issues. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2077 | Manhours without LTI (3.3 mil manhours) - P18B | -continuous awareness of safety -Trainings | -Good reputation -No LTI | -Recognition and Reward to the project team member | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5664 | Manpower / organization chart not as per contract. | 1. Project Control Manager resigned from contractor office. | 1. Project Control Manager was not sighted after 3rd quarter of 2016. 2. Quality of the reporting affected. 3. Relevant report submission was delayed. |  | 15045 - Action Taken: Reminder letter sent to CONTRACTOR on the absent of Project Control Manager. 15046 - Action Taken: OWNER requested replacement for the vacant position as per contract requirement. 15047 - Recommendation: Any change / replacement of contractor personnel shall get approval and Owner consent. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Precommissioning/Commissioning | 6289 | MASTER FIRE ALARM PANEL: constantly open circuit | 1. Due to changes there is a jointing in the LAN cable, which result tripping. | 1. The signal is unstable has prolonged the duration of commissinoning |  | 16440 - Action Taken: The Fluke Tests & programming takes a long time to complete after the cabling rectification works is done. 16441 - Recommendation: To have overall design finalization by the consultant before the installation. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6177 | Material Selection of piping and equipment (over or under design) | 1. Specification of unsuitable (over or under design) material for piping & equipment from previous engineering phase could pose cost impact during execution | 1. Specification of unsuitable (over or under design) material for piping & equipment from previous engineering phase could pose cost impact during execution |  | 16194 - Action Taken: Material selection for piping and equipment shall be re-evaluated during initial phase of detail engineering 16195 - Recommendation: To further study on the project specifications to avoid over / under spec to minimize cost impact | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5233 | Material shortage (AG) | 1. Late MTO cut off 2. Late PO issuance | 1. Delay the construction |  | 14318 - Action Taken: Purchase extra material by adding to the construction contingency | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5228 | Material shortage (UG) | 1. Late MTO cut off 2. Late PO issuance | 1. Delay the construction |  | 14306 - Action Taken: Purchase extra material by adding to the construction contingency 14307 - Action Taken: Air freight material | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Quality | 6005 | Material to be used to be submitted for approval prior to order & delivery | 1. Material approval submission not being carried-out. The material used without BOMBA certificate | 1. Unapproved material being utilized on-site, e.g. fire stop material |  | 15849 - Action Taken: Other material with BOMBA cert has been submitted & approved. The rejected material has been removed & replaced with the approved one. 15850 - Recommendation: Follow material approval procedure | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5809 | Max. Skin Temperature Requirement. | 1. Cooling water (CW) side skin temperature in clean condition shall not be higher than 52°C (PTS 20.21.00.31 Para 2.2.(C)). 2. 3220-E-214 : CW consumption needed to be increased by 317% (~2,650 ton/hr) to meet PTS. However, this would exceed total CW available for import from OSBL. 3. Possible mitigation: Install air fin cooler. However, impact on plot & main pipe rack. | 1. Purpose of PTS requirement: To prevent fouling due to CW chemical deposition. 2. Low possibility of fouling due to high fouling resistance, high CW velocity, and low skin temperature during normal case. |  | 15460 - Action Taken: Increased CW flowrate for 5 items. 15461 - Action Taken: Added heat exchanger with 50% duty (3220-E-215) as spare during maintenance of 3220-E-214. 15462 - Recommendation: Preventive Action. 15463 - Recommendation: Review whether PTS requirement can be relaxed. 15464 - Recommendation: Clarify max. Skin temperature requirement during early stages of design. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5467 | Maximum Real Fluid Temperature Inside the Line (T-Flex) is not clearly defined in the ITB. | 1. The definition of Maximum Real Fluid Temperature Inside the Line is not clear. | 1. Pipe will fail if the temperature is higher than design temperature. |  | 14587 - Recommendation: To define Maximum Real Fluid Temperature Inside the Line is when the condition of fluid is not moving. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5146 | May not have fully utilized internal / external lessons learnt and best practices. | 1. Unclear process for accessing database - if any. 2. Lack of communication / sharing on the improvements from previous PLL. | 1. May have missed opportunity to adopt best practices - for e.g. the implementation of flow meter unit measurement; segregation of HP Compressors (big motor) to substations. |  | 14245 - Propose to have a clear central database accessible for Projects. 14246 - Propose to have PLL session at the early stage of the project phases. 14247 - Propose to have periodical PLL session (based on project progress - %) 14248 - Operation team and construction team to be involved at early engineering stage (part of project team) | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5621 | MDR submitted to OWNER is not comply with ITB requirements. | 1. List of the submitted documents is not as per OWNER requirements. | 1. Late submission of documents as per schedule. 2. Identified redundancy of documents need to be reviewed by OWNER. |  | 14926 - Action Taken: Specific meeting between OWNER and CONTRACTOR in regular basis has been held to ensure that all requirements listed in ITB are comply by CONTRACTOR. 14927 - Recommendation: CONTRACTOR need to incorporate and resubmit the updated MDR for OWNER review and approval. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5578 | Mechanical / Rotating: Best Practice: Continuous communication between Contractor and Owner during engineering | 1. Continuous discussion and clarification before official issuance for every deliverables MR, MDS etc. 2. Mutual understanding and cooperation. Every personnel play their role very well. | 1. Improve deliverables schedule |  | 14830 - Action Taken: Initiated Official Internal weekly rotating discipline meeting and continuous unofficial discussion. 14831 - Recommendation: To apply across all disciplines. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5723 | Mechanical Rotating / Package: Design change after PO placement | 1. Few pumps need to be re-size due to battery limit requirement change. | 1. This impacted the cost and delivery schedule. |  | 15262 - Action Taken: Discussed with relevant parties to fixed and freeze the battery limit conditions ASAP to minimize impact. 15263 - Recommendation: Battery limits conditions shall be reviewed and fixed as early as possible and if there is unavoidable changes, this shall be communicated properly at the earliest to all relevant and concerned parties due to change in condition. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5725 | Mechanical Rotating / Package: Late comments from some disciplines / parties. | 1. Few of important document (For e.g. Material Requisition, Vendor GA / Datasheet / P&IDs) were not reviewed on the first submission / revision by some parties. | 1. Delay in work progression (PO placement, equipment fabrication, etc.). |  | 15267 - Action Taken: Keep reminding relevant reviewers to review the document on first submission. 15268 - Recommendation: Improve document distribution matrix by limiting the reviewer only to 1 reviewer per discipline and only on first submission. 15269 - Recommendation: Subsequent submission shall only be distributed to focal person/consolidator. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5724 | Mechanical Rotating / Package: Non-detail review by Samsung on Vendor Documentation. | 1. Noticed that there are few occasions that Samsung did not performed a thorough and detail review on Vendor documentations. | 1. Samsung missed to comment on major mistakes and incompliance to Project Specs. |  | 15264 - Action Taken: Commented the missing comments on behalf of the Samsung. At the same time, gave personal advice to Samsung to do detail checking on future Vendor document. 15265 - Recommendation: Only experience engineers shall be accepted, as coordinating engineer, in the project (suggested more than 8 years experience for the coordinating engineer). 15266 - Recommendation: CTR job / junior engineers to be assigned to limited number of Package Equipment for better focus. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5722 | Mechanical Rotating / Package: Some of major PO was placed prior deviations approval by PTA. | 1. Due to schedule driven project, Samsung requested Owner to give at least Code 4 (Approved with Minor Comments) in order for them to proceed with PO placement, otherwise overall project schedule will be impacted. |  |  | 15257 - Action Taken: Insisted Samsung / Vendor to minimize and withdraw the deviations in order to expedite the review and approval from relevant parties. 15258 - Action Taken: For those pending deviations approval, OWNER agreed to give Code 4 with condition that Samsung shall absorb all the risks / impacts incurred due to non-acceptance of the deviations by PTA. 15259 - Recommendation: Ample time shall be given for TBE. 15260 - Recommendation: Contractor shall improve in negotiating with Vendors and reviewing the deviations as there are some deviations are non-technical related issue. 15261 - Recommendation: Package engineers to carefully check how schedule critical their TBEs are (check float). | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5721 | Mechanical Rotating / Package: There are vague and contradicting requirement between Project Specifications. | 1. MMS instrumentation requirement for API pumps are not specifically specified in Project Specification. For e.g. Project Specs only mentioned online monitoring to be provided for certain pump ratings but does not mentioned what instrumentation to be monitored. 2. MMS for motors does not specified in any of Project Specs. |  |  | 15255 - Action Taken: Negotiated with Contractor to follow the MMS being implemented for Refinery Projects. 15256 - Recommendation: Specific requirement for MMS shall be dictated in relevant Project Specifications. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5726 | Mechanical Rotating / Package: Vendor documents were not properly distributed to correct reviewers. | 1. This is because of unclear instruction / procedure of Vendor Document Distribution Matrix, as well as inexperience DC. | 1. Vendor documents were not properly distributed to correct reviewers. Document Controller (DC) need to ask engineers manually for distribution in the system. |  | 15270 - Action Taken: Engineer manually marked-up the Vendor Print Index to indicate the reviewers for each Package Equipment for DC to distribute in the P-EDMS. 15271 - Action Taken: Engineers need to manually re-assign the review to other relevant disciplines. 15272 - Recommendation: Clear and specific procedure for Vendor Document Distribution Matrix. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5586 | Mechanical Rotating: Best Practice: All equipment Testing Procedures shall be approved and make ready prior to any Testing to be carried out at Factory. | 1. Test Procedures are approved with Comments upfront prior to actual testing. | 1. The testing able to be conducted with highest integrity and full compliance to project requirements once OWNERs comment properly resolved. |  | 14846 - Action Taken: Prior to the actual Test at factory, technical clarification meeting was conducted between Owner, Contractor and Vendor to clear all owners open comments and agreement from all parties. Finally, test are conducted as per agreed procedures 14847 - Recommendation: Ensure all Test Procedures are finalized and approved prior to any test conducted. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5587 | Mechanical Rotating: Best Practice: Meetings through VC with 3 parties / locations. | 1. Vendors proposed schematic is meeting all requirement, but the scheme proposed is confusing and require details explanation. This meetings conducted via VC due to geographical location limitation. | 1. Immediate decision was able to be made by core engineering based from vendors explanation. |  | 14848 - Action Taken: Video Conference Meeting was conducted between Owner, Core Engineering Team, Contractor & Vendor to discuss and further clarify any arising issues. 14849 - Recommendation: Video Conference can replace face to face discussion in addressing any technical issues between multiple parties. Video Conference is a better solution compared to telephone calls or e-mail discussion. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5584 | Mechanical Rotating: Best Practice: Timely approval of VCR that involves multi discipline. | 1. VCR for Rotating Package that require input from Electrical discipline was approved by Core EM within required time. | 1. VCR that timely approved allows vendor to proceed with their work swiftly in order to meet overall delivery schedule of equipment. |  | 14842 - Action Taken: Prior to issuance for approval, the details was discussed offline within between Rotating and Electrical discipline, and any correction was made before submit to higher approving authority to avoid re-work. 14843 - Recommendation: Continuous communication with other discipline on issues that require multi-discipline input. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5580 | Mechanical Rotating: Comment from OWNER on Vendor Print to be communicated to Vendor, any disagreement to be informed to OWNER immediately for resolution. | 1. OWNER did not received any feedback on the comment. | 1. After 3 revision, only to find out the comment was not incorporated by Vendor. |  | 14834 - Action Taken: Immediately communicate to Vendor via contractor to resolve the issue. 14835 - Recommendation: Continuous updates / communication is required. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5003 | Mechanical Rotating: Compressor testing procedures contained lots of technical comments from PMC causing delay in procedure approval. | 1. Contractor reviewed and approved the procedures as per their previous project experiences. 2. Late vendor respond to PMCs comments. | 1. Delay in procedure final approval by PMC. 2. Compressor testing schedule impacted, hence delivery of the equipment also impacted. |  | 13944 - Critical equipment testing procedure shall be submitted earlier (2 months in advance before testing schedule) for reviewed by Owner. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5579 | Mechanical Rotating: CONTRACTOR agreed to response to OWNERs comments after review of documents. | 1. CRS is submitted together with updated document. | 1. Issuance of revised documents shall proceed after the agreement of CRS for each of the comments. |  | 14832 - Action Taken: Advised CONTRACTOR to discuss on the comment and issue draft revised document for review. 14833 - Recommendation: To include additional step in document review management. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5002 | Mechanical Rotating: Due to limitation of skills by Contractor, teamwork is crucial in resolving issues within the agreed timeframe. | 1. Limited experience within contractor engineers. | 1. Increase in number of rework. 2. Need hand holding to ensure correct understanding in project requirement. |  | 13939 - Action Taken: To work together with Contractor, focus to solve the problem and consequently close the issue. 13940 - Action Taken: May not necessarily to open another issue on top of existing issue. 13941 - Action Taken: To provide clear and precise instruction to Contractor to avoid any miscommunication. 13943 - Recommendation: Contractor to perform proper screening for mechanical rotating millwright | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5585 | Mechanical Rotating: High number of deviations submitted by Vendor are passed to Core team and PTA for their review and approval without UPT level review. | 1. The deviation list is not properly filtered and reviewed in UPT level. | 1. Core team and PTA are overwhelmed with high numbers of deviation submitted and impacted the approval time. |  | 14844 - Action Taken: UPT discipline engineer to review and filter the submitted deviations before pass to Core for review and approval. Only true and genuine deviations shall be considered, where deviation that commercially driven are not accepted. 14845 - Recommendation: Role by UPT Engineer to continuously review the deviations and not simply pass the documents to core team. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5582 | Mechanical Rotating: Inconsistent data / information across different documents issued by CONTRACTOR. | 1. CONTRACTOR do not thoroughly check the document prior to issuance to OWNER | 1. Poor quality of deliverables issued by CONTRACTOR. 2. OWNER to allocate unnecessary time / resources. |  | 14838 - Action Taken: CONTRACTOR to issue draft in order to reduce the official cycle of review. 14839 - Recommendation: CONTRACTOR lead engineer should have taken more responsibility and checked before issuance. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5581 | Mechanical Rotating: Issuance of Vendor print and CONTRACTOR document is outdated. | 1. Untimely cycle issuance of VP and CONTRACTOR document. | 1. The data information in the document contradict to each other, not sure which one is up to date for example data sheet from contractor and from vendor issue at the same time |  | 14836 - Action Taken: Clarify back to contractor to send according to the plan cycle. 14837 - Recommendation: CONTRACTOR should have verified which document is up to date and which are not before issue. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5004 | Mechanical Rotating: Rotating equipment - Several VCR raised from I&C due to not meeting project specification i.e. thermowell, pressure gage specification, Level indicator glass type | 1. Lack of communication and continuous follow up between Rotating and I&C team from Contractor side on reviewing vendor documentation. | 1. Most changes cant be make because the fabrication works / orders have been completed |  | 13945 - To clearly clarify / inform vendors project engineer of I&C deliverables as per project specifications. Early identification of PDR can be reviewed and approved. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5583 | Mechanical Rotating: Submission of vendor print. | 1. Some of vendor print did not transmit to OWNER for review. When it reached OWNER, the vendor print is already in revision D or E. | 1. Noncompliance of vendor skid to project requirement. |  | 14840 - Action Taken: OWNER has to give the major input for rearranging the equipment in the skid with vendor through responsible contractor engineer in order to reduce the rework at vendor end and cause delay. 14841 - Recommendation: CONTRACTOR Document Controller to automate the transmittal to vendor and send parallel to OWNER. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5565 | Mechanical Static / Piping: 3D Model Review workstation is not available for OWNER team to review. | 1. Misinterpretation by CONTRACTOR for ITB requirement. | 1. OWNER cannot review the 3D Model design progressively. |  | 14794 - Action Taken: OWNER team discussed and explained the ITB requirement and emphasize the need for installation of fully functional workstation. 14795 - Action Taken: CONTRACTOR installed workstation with the required software and keep on updating model file (transfer through FTP Server) on weekly basis. 14796 - Recommendation: Reword the contract to bring more clarity on scope covering software required for viewing. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5719 | Mechanical Static / Piping: Additional anchor bolt for testing at site. | 1. According to CTR, this requirement should not be applicable as anchor bolts are supplied by respective vendors and not by CTR (bulk quantity). | 1. CTR did not considered this requirement and supplied only actual required number of anchor bolts for Static equipment. |  | 15251 - Action Taken: CTR was asked to satisfy project specification requirement OR shall supply 3.2 type material certification. 15252 - Recommendation: CTR should have raised TEQ to obtain OWNER concurrence during the early Engineering stage (before PO placement). | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5569 | Mechanical Static / Piping: Baffle material shall match with tube material as per OWNER interpretation of PTS 31.21.01.30 table A-2. | 1. Contractor misinterpretation of PTS. | 1. Based on the data sheet prepared by contractor, the material of baffle was selected as CS instead of SS (as per OWNER interpretation of PTS table A-2 to match with tube / tube sheet material). 2. Based on issued MR -data sheet material the material procurement was initiated by vendor based on CS baffle. |  | 14804 - Action Taken: Commented on PDR submitted by contractor for same the equipment (for dissimilar metal weld) to revise the material of baffle to SS to ensure PTS requirement is fulfilled. 14805 - Recommendation: Project spec / PTS shall highlight that, for the selection of baffle material and tube bundle material shall match with tube / tube sheet as per table A-2. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5571 | Mechanical Static / Piping: Best Practice: Good presentation of 3D model and relevant documents simultaneously by CONTRACTOR. | 1. Use of multi-screen projectors and proper venue for the model review. | 1. Smooth review session and prompt verification of vendor documents. |  | 14810 - Recommendation: To maintain the similar activity for future projects. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5573 | Mechanical Static / Piping: CONTRACTOR does not follow sequence of project schedule for the documents submission. | 1. CONTRACTOR issued MR-IFP before Award recommendation submission. | 1. MR-IFP returned with code 2 since award recommendation not submitted / approved. |  | 14818 - Action Taken: Informed CONTRACTOR to ensure Award recommendation first before MR-IFP. 14819 - Recommendation: CONTRACTOR to follow the deliverable flow according to schedule. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5567 | Mechanical Static / Piping: Contractor does not used the approved MVL. | 1. TBE submitted bidders are not matched with approved bidders list. | 1. In the TBE the bidders were different / or from different location. |  | 14800 - Action Taken: Resubmission of bidders list for the new bidder / reason for different location justification. 14801 - Recommendation: CONTRACTOR should have verified with bidders and their planned execution location and should have submitted the bidders list according to that. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5568 | Mechanical Static / Piping: Documents were not reviewed by the correct people at core level. | 1. Documents distribution matrix issued by core engineering did not cover distribution for all documents. 2. PEDMS was introduced first time for use and many of the core engineering staff did not have access and training for PEDMS. | 1. Some comments were not made on time. |  | 14802 - Action Taken: Consolidator have to distribute the documents offline through email to the relevant people who did not received the documents at the first place in PEDMS. 14803 - Recommendation: DDM should be clearer and detail enough to cover all types of documents. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5718 | Mechanical Static / Piping: Fluro carbon coating for external bolting. | 1. Vendor claimed that they did not considered 2 coats of lining on external bolting as per project specification requirement and considered only one coat of lining for bolting fabrication (Project specification requirement was not correctly read and understood by Vendor). | 1. CTR / Vendor claimed around 4 weeks delivery impact for all 4 plate type heat exchangers. |  | 15248 - Action Taken: CTR / Vendor were asked to put extra effort for refabrication of external bolting with 2 coats of lining (without claiming delivery impact). 15249 - Recommendation: During Bid clarification meeting with Vendors, CTR shall discuss and specifically highlight / explain all such requirements. 15250 - Recommendation: Also inspector should be more vigilant to ensure consideration of all such requirements by Vendor in early stages of fabrication. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5570 | Mechanical Static / Piping: Incomplete inter-discipline 3D model review by contractor before presenting to OWNER. | 1. Lack of internal checks by contractor for ensuring full compliance with project specs and P&IDs. 2. Unavailability of vendor prints. | 1. Model is not as per specs. 2. OWNER spends more time for checking and commenting. 3. Potential rework in field. |  | 14806 - Action Taken: Extended model review session by OWNER. 14807 - Action Taken: OWNER emphasis to contractor the need for inter-discipline model review shared before presenting to OWNER. 14808 - Action Taken: Additional model review was conducted. 14809 - Recommendation: Contractor to engage dedicated checker and only experienced staffs for project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5575 | Mechanical Static / Piping: Issue of Pre-Q much ahead of TBE submission. | 1. TBE is ready to be submitted but Pre-Q submission with missing information. | 1. TBE approval / PO placement delay for platform and ladder. |  | 14822 - Action Taken: Informed CTRs procurement provide all necessary info for PRE-Q approval. 14823 - Action Taken: Submission of Pre-Q shall be much ahead of TBEs submission. 14824 - Recommendation: CONTRACTOR to submit the PRE-Q much ahead of TBE (during bid offer review stage) to ensure PRE-Q approved on time and TBE submission and PO placement as per schedule. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5716 | Mechanical Static / Piping: Mill limitation to perform 3LPE on fittings. | 1. Some limitation to manufacture factory-made 3LPE on fittings and small bore piping due to geometry and shape of the fittings. 2. No coating applicator can perform 3LPE coating on fittings and small bore piping. End up Contractor to deviate from project specification. | 1. Delay in procurement. 2. Delay in receiving UG fittings at site. |  | 15244 - Action Taken: PDR was issued to use Liquid Epoxy Coating (LEC) to replace 3LPE 15245 - Recommendation: PTS and project specification to be updated to use alternative coating method such as LEC for fittings and some small bore fittings. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5566 | Mechanical Static / Piping: Some safety distance between equipment did not comply the project specs. | 1. Lack of understanding of RAPID spec by Contractor. 2. Lack of clarity in RAPID Project Specs (RAPID-FE1-TPX-PIP-DES-0001-0001, Appendix 1) for definition of Main Equipment Structure. | 1. Noncompliance of project specification for safety distance between pipe rack and equipment (Main Equipment Structure). |  | 14797 - Action Taken: Discussion with Contractor for interpretation of project spec and RAPID Project Specs (RAPID-FE1-TPX-PIP-DES-0001-0001, Appendix 1) requirement to ensure ultimate safety of the plant. 14798 - Recommendation: OWNER and contractor establish join discussion to discuss on the key highlight of specification and get same understanding. 14799 - Recommendation: Provide definition of Main Equipment Structure. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5720 | Mechanical Static / Piping: Uncommon type of support for equipment (i.e. hanging spring type). | 1. Connecting piping loads are high due to large piping sizes and CTR had difficulty to design equipment / piping considering stable support. | 1. CTR changed type of support from lugs type to hanging spring type support. |  | 15253 - Action Taken: During 90% model review, OWNER asked CTR to change the support type from spring to stable / resting type support. 15254 - Recommendation: ITB / project specification shall specify support type selection criteria for Static equipment (ex: hanging / suspended type spring supports are not acceptable). | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5572 | Mechanical Static / Piping: Valve Critical Analysis (VCA) should be completed and reviewed during 60% model review. | 1. VCA was not incorporated in the P&ID and not reviewed during 60% model review. | 1. The correct sequence of conducting the VCA was not followed by SC which resulted in rework in 60% model. 2. Unable to identify and confirm the valve critical classification during the model review in results of disagreement the valve accessibility requirement. |  | 14811 - Action Taken: Given and briefed SC the correct procedure of developing the VCA. 14812 - Action Taken: VCA reviewed by OWNER in a separate session. 14813 - Action Taken: To remind CONTRACTOR to ensure all sessions required to be completed accordingly per schedule. 14814 - Action Taken: To carry out the VCA session for identifying the critical classification and incorporate into 60% 3D Model review. 14815 - Recommendation: CONTRACTOR to follow all the given procedure. 14816 - Recommendation: Conduct internal review first before any official review session. 14817 - Recommendation: Focal person shall identify the sessions which need to be conducted as per schedule. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5576 | Mechanical Static / Piping: Vendor document to be commented with details. | 1. CONTRACTOR commented referring to their internal MOM and not commenting on the requirement (PMI procedure commented referring MOM instead extend PMI in details for Internal MR). | 1. OWNER / CONTRACTOR and other discipline (commented by Contractors inspection and Contractor mechanical do not have copy of their internal MOM) cannot understand the comment or requirement. |  | 14825 - Action Taken: Informed CONTRACTOR to comment the requirement instead referring their internal MOM. 14826 - Recommendation: Vendor document comment to be very specific on the requirement. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5577 | Mechanical Static / Piping: Vendor print submission and approval was delayed. | 1. Delayed vendor print resubmission for vessel I and II (M/s Furui China) due to multiple parties involvement for the documents preparation. 2. Too many layers of checking and approval. | 1. Delayed vendor print submission due design document preparation by sub vendor. |  | 14827 - Action Taken: Informed CONTRACTORs sent engineer to vendor shop for speeding the approval of the documents. 14828 - Recommendation: Multiple party for design document preparation (with different location) shall be avoided. 14829 - Recommendation: Selected vendors shall be capable of preparing document on their own. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5574 | Mechanical Static / Piping: Vendor selected the material to follow the ASTM / ASME for main component for support EN material. | 1. Vendor standard design of non-pressure parts using EN material with mixing of pressure parts of ASME material. 2. VCR should be issued for OWNERs approval. | 1. VCR approval process need to be approved by OWNER. |  | 14820 - Action Taken: VCR issued for approval. 14821 - Recommendation: CONTRACTOR to check with vendor during bid evaluation to avoid VCR issue. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5075 | Mechanical: Equipment clashes with structure members during installation and some part requires permanent modification. | 1. 3D model did not incorporate all small details and late vendor data, such as nozzles smaller than 2 inch and detail on expansion joint. | 1. Equipment clashes with structural members during installation 2. Permanent modification on expansion joint, including cutting of limit rods. |  | 14097 - To include all detail during the 90% model review session. 14098 - To perform detailed constructability review on all critical and complex installation. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5079 | Mechanical: Inaccessibility of big capacity crane after 80% construction progress to lift big equipment | 1. Lack procurement strategy in prioritization of delivery urgency. 2. Lack constructability review to anticipate the issue. | 1. E.g. installation progress impact. Required bigger capacity crane to perform the lifting/installation. |  | 14103 - To understand on equipment installation sequence and properly link to procurement prioritization. 14104 - To understand on equipment installation sequence and properly link to procurement prioritization. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5077 | Mechanical: Incomplete E&I dress-up works on pre dress up columns - cable trays, cable pulling on columns not completed prior to column erection. | 1. Insufficient E&I manpower to complete the dress-up on time. | 1. Incomplete E&I activity on pre-dress up column - thus E&I works shall be finished after the column being erected to vertical position. |  | 14100 - E&I team commitment required to complete column dress-up activity per project schedule to avoid slippage of lifting date. The E&I completion must be on time, together with other Mechanical works dress-up activity. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5076 | Mechanical: Late delivery of Clarifier Tank to site resulted difficulty on transportation to site due to site condition | 1. Late PO placement of Clarifier Tank 2. Little consideration given to site condition (other package condition) when deciding tank delivery condition (delivered in one piece vs several pieces vs site erection) | 1. Difficulty in transporting the tank across 1900-RCK-6120 pipe rack (belongs to P3). 2. Risk of damage on pipe rack OR the tank itself 3. Modification / Disassembly of tank is required to transport the tank to site. |  | 14099 - To perform detailed constructability review on all critical installation / equipment transportation. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5078 | Mechanical: Late execution of TML Baseline Measurement at Site which may impact PICOAT initiative requirement | 1. Only bring minimal weightage of progress upon completion. EPCC normal construction practice to perform at the end of construction phase. EPCC not fully feel the urgency of not carry out the TML Baseline Measurement due to less understanding the work impact to PICOAT. | 1. Impact to the PICOAT initiative |  | 14101 - To well present the PICOAT to EPCC and bring full awareness on how it could impact to regulatory aspect. 14102 - Suggest to perform the TML Baseline Measurement by the equipment vendor/fabricator at the shop prior to delivery to site - it will no further impact to site progress or any quality issue afterwards. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5247 | Metal pads on pump foundation incorrect location (not as per pump baseplate drawing) | 1. Vendor drawing and construction drawing not tally | 1. Base plate leveling cannot be done as per installation manual |  | 14341 - Action Taken: Ensure construction drawing is read in conjuction with the vendor drawing. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5858 | Meter for some utilities (instrument air, plant air, service water, potable water, demin water, HP nitrogen, fuel gas and waste water) from/to BL from/to P7 are not specified in the FEED. | 1. It was understood before that this will be provided by P14. However P14 provided the overall meter to one OPZ (1 common meter for P6A, P7 and P27). Understood billing will be to OPZ instead of individual Package 6A, 7 and 27. | 1. No meter reading for some of the utilities from/to P7. It will be difficult to monitor plant performance and consumption. |  | 15134 - Action Taken: To ensure meters for measuring utilities from/to P7 are provided. 15135 - Recommendation: To establish metering philosophy for the all packages during FEED | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Project Management | 6197 | MIE and YKM are not fully integrated (interdisciplines). | 1. Concept of EPCC team integration is not fully applied | 1. Communication gaps 2. Document discrepancy 3. Redundant Document 4. Engineering & Vendor document are not reviewed by the appropriate personnel. |  | 16240 - Action Taken: Ensure execution as per execution plan. 16241 - Action Taken: Frequent engagement between disciplines 16242 - Action Taken: Established WAR room 16243 - Action Taken: Owner to intervene 16244 - Recommendation: Ensure EPCC is capable of executing full EPCC workscope with full empowerment 16245 - Recommendation: Team building 16246 - Recommendation: Frequent engagement between disciplines 16247 - Recommendation: Establish WAR room | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Project Management | 5109 | Migration from POL to PEDMS system | 1. PEDMS was introduce first time for use and many of core engineering staff didn’t have access and training | 1. Double notifications from POL and PEDMS caused longer times to close |  | 14212 - Action Taken: List down all the documents reviewed and compare between POL and PEDMS 14213 - Recommendation: To implement the similar system at the beginning of the project | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Document Management | 5422 | Migration from POL to P-EDMS. | 1. Introduction of P-EDMS in the middle of execution. 2. Migration is still in progress as of April 2017. | 1. Delay in review of document due to learning curve and migration of docs from POL to P-EDMS. |  | 14504 - Action Taken: Fast-track training to team members on P-EDMS. 14505 - Action Taken: Deployment of extra manpower for migration of docs. 14506 - Recommendation: Avoid to introduce new system in the middle of project. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5476 | Minimum Requirement for Sound Pressure Level (SPL) for PAGA. | 1. Original requirement - In case of failure of one loop, the coverage could be half of the 6 dBA, i.e. 3 dBA above ambiance noise. | 1. Change order resulting in cost impact. |  | 14598 - Action Taken: OWNER is revising the requirement - for each PAGA node, the siren shall interlace, so that in case of failure of one loop, SPL coverage of equivalent to 6dBA over the ambient noise in a dedicated to area of another loop is available. 14599 - Recommendation: SPL shall be defined clearly in the FEED document. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | HSSE | 6267 | Misalign on RAPID HSSE requirement with EPCC | 1. Incomplete document handover to PGB. 2. Late sharing of project requirement (procedure, SI). 3. EPCC awarded earlier than RAPID requirement inception. | 1. Delay on construction activities. |  | 16396 - Action Taken: Engaged with CD HSSE. 16397 - Recommendation: Site requirements to be established at earlier project stage with proper communication medium. 16398 - Recommendation: Centralized instruction on HSSE requirements. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Project Management | 5409 | Misalignment of teams objective and work processes during early stage of the project. | 1. The engineering team was only mobilized after award. 2. Separation between PMC and OWNERs team. | 1. Lack of team integration leading to demotivation. 2. Misalignment between EPCC contractor and iPMT. |  | 14467 - Action Taken: Integrated between OWNER and PMC (iPMT). 14468 - Action Taken: Enhanced team communication. 14469 - Recommendation: The engineering team should be mobilized from FEED and to continue until construction phase. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5468 | Misinterpretation of scope for QRA, RAM & EMC Studies by EPCC | 1. EPCC assumed OWNER to conduct the study | 1. Affecting commencement & completion of engineering deliverables 2. Cost & Schedule dispute with EPCC |  | 14588 - Recommendation: These clauses may give interpretation that it is OWNER responsible to perform the QRA, RAM and EMC (which is not). Recommend to rephrase the clauses. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6019 | Mismatch piping standard and instrument standard (The flange of Level transmitters on the tanks in chemical building to match with the piping flange on the tanks) | 1. The flange of Level transmitters on the tanks in chemical building didn’t match with the piping flange on the tanks | 1. Time lost 2. Rework |  | 15876 - Action Taken: A transition spool piece were ordered and installed between the flanges. 15877 - Recommendation: Inter Discipline Check has to be conducted during engineering stage. Level transmitters are to be procured with the correct specifications and sized as per tanks flanges requirement. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5851 | Miss communication on PMRC training i.e. Contractor assumed initial training received was adequate and efficient Contractor attended the first phase of the training only. | 1. Delay in producing pipe material specification due to extraction of information from PMRC database | 1. Delay in producing PMRC datasheet for project and impact of MTO |  | 15116 - Recommendation: To ensure contractor receive sufficient training and communication between contractor and PMC team 15117 - Recommendation: To ensure mandatory in ITB for contractor to familiarize with the PETRONAS system/software module applications 15118 - Action Taken: Video conference training was conducted for the contractor to ensure the contractor is familiar with the PETRONAS system/software used | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Planning | 5418 | Miss reporting of progress due to incomplete MDR. | 1. Misalignment of progress measurement. | 1. Contractors safety gained very positive progress in beginning due to improper planning (e.g. incorrect document weightage, insufficient deliverables listed as per ITB requirement). |  | 14495 - Recommendation: Suggest to have Interactive session on project logical sequence between Contractor & UPT & Core Team in order to understand and meet project schedule in overall. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5846 | Missing information from FE1 (FEED Documents) documents. | 1. RAPID Project Specification and drawings was not updated accordingly. | 1. Schedule and cost impact since the information required is from FE1 and mostly cost estimates are done based on FE1 documents. |  | 15111 - Recommendation: RAPID project specification and documentation should be updated with regards to query from other contractors regarding the same issue. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5444 | Missing Mechanical Datasheet for 42 tanks (total 44 tanks) | 1. Unable to compile the As-Built documents. | 1. Delay of compile As-Built documents. |  | 14548 - Action Taken: Expedited EPCC to submit the missing Mechanical Datasheet 14549 - Recommendation: Mechanical Datasheet to be check and verify. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5841 | Missing specification in ENMCS | 1. The ENMCS specification requires interfacing details with P14 and instrument. Some of the required info are not incorporated. | 1. ENMCS design and interfacing is not yet finalized. |  | 15099 - Recommendation: To discuss the ENMCS with all interface parties in timely manner 15100 - Recommendation: To conduct PIR on the revised ITB (if any) and include the relevant requirements in ITB | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5973 | Mixed up of power cable and control cable inside RCU. Furthermore, CT for RCU ammeter installed at RCU. | 1. EPCC not understand/following the project requirement/specification. 2. Project team failed to identify during construction/pre-com/FAT | 1. Hazard to human |  | 15803 - Action Taken: SR already raised. Few discussions have been made with LLWT and PMC. Still pending closure | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Construction | 5902 | Modularization Technical Approach Pipe racks, Packages with static equipment (skid-mounted equipment modules), Process Structures Pre-fabrication works carried out in shop minimize the erection activities at site. |  |  |  | 15204 - Applied Solution: Project team has designed all the steel structures as per traditional stick-built approach following the FEED and the Company std. 15205 - Suggestion for Improvement: Interconnecting pipe- racks. Lower part of polymerization process structures. Packages including vessels | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5952 | Most of the Electrical drawings/documents are yet to be approved and obtain CODE 3 before construction, pre-com and commissioning | 1. Lack of commitment from EPCC | 1. No proper reference to OWNER and project team for site verification |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5454 | Motor procured does not follow the Spec. (Heater JB is not separate) | 1. Full Spec was not given to vendor by EPCC | 1. Potential schedule delay |  | 14568 - Action Taken: Raised VCR and TEQ to get approval from TA | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5982 | Motor solo run was not conductor during pre-com as per ITB requirement. | 1. EPCC not understand/following the project requirement/specification. | 1. Verification of motor condition at site and during at FT unable to be done |  | 15812 - Action Taken: Request have be done by Commissioning team to uncouple and do the solo run, but project team proceed to do with couple test run during commissioning stage. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5446 | Multiple specifications and reference editions of Sealing system for centrifugal and rotary pumps | 1. Project specification SHAFT SEALING SYSTEM FOR CENTRIFUGAL AND ROTARY PUMP (RAPID-FE1-TPX-ROT-SPN-0001-0014_0) approved on April 2012 are based on the old revision of PTS 31.29.00.33 (amendment/supplements to ISO 21049:2004) API 682 3rd Edition. 2. New revision of API 682 4th Edition has been published on May 2014. Contractually, based in Para 4.0.3.4 (Applicable codes and standards) Section C, Part II- 4.0 Engineering-General, It is specified that CONTRACTOR shall comply with latest editions at EFFECTIVE DATE, of the Code & standards referenced in documents listed in Section D-Project Documentation. 3. The incomprehensive decision process making in finalization the way forward from UPT/Core team and CONTRACTOR. | 1. Additional man-hours spent for re-clarification / document review process. 2. Renegotiation in term of technical as well commercial issues between Contractor / EPCC and its respective vendor. 3. Fabrication / manufacturing delayed due to revised approved vendor drawing |  | 14551 - Recommendation: A committee can be established by Central Core team to govern the latest edition/revision of Project specification. 14552 - Recommendation: Contractor to be more proactive in term of issuing Technical Query (TQ) to PMC/Owner in addressing any changes in latest edition of project specification. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Procurement | 5526 | MVL (rev.6) for E&I cables is not listed on the latest version of MVL shared in ITB | 1. PRPC procurement team removed the list from the MVL with intention adding E&I cables into category item was not updated. | 1. Bidders free to go to any suppliers. |  | 14689 - Action Taken: Reproposed supplier listed MVL (rev.5) 14690 - Recommendation: To update the category item (E&I cables) | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5443 | NACE requirements and CDBM to be details. | 1. PMC, EPCC and vendor did not aware / overlook of the NACE material requirement in the H2S services. 2. CDBM not established from earlier stage of project | 1. PDR to be raise and testing to be done for the material as proof if the material is sustainability in wet H2S services. 2. Delay of approval documents, late delivery to site. |  | 14546 - Recommendation: All party to be aware the requirements of the NACE requirement and H2S services. 14547 - Recommendation: CDBM to be details on the selection of the materials. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Engineering | 6287 | Navigation and telecommunication works | 1. Appointed specialist parties / contractors were not able to keep up with their individual timelines. | 1. Schedule delay |  | 16436 - Action Taken: UEMB procured some items directly and resources had to be added to complete the works. 16437 - Recommendation: To award the project to the contractor with proven experienced and track record. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Quality | 5279 | NDE backlog and data not accurate | 1. Delayed in key in of drawings/reports. Updated drawing/redline mark-up not updated | 1. Increase no of backlogs due to delay NEWS selection of NDE joints. Delayed to clear test packages |  | 14394 - Action Taken: Requested NEWS personnel from CD to station at site office. Push sub-contractor to expedite key in. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5240 | Never ending quantity freezing | 1. Change in engineering design during construction phase 2. Development of engineering contribute to change in construction | 1. Delay the construction |  | 14332 - Recommendation: To have transparency In terms of design changes | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5675 | NEW CIDB requirement of COA for pipe and steel structure | 1. Although COA is a part of contract, it’s mainly applied to MS while Rapid#6A/#11 contracted with ASTM. 2. But, CIDB announced apply for COA to ASTM in the middle of project execution | 1. CIDB COA requirement for pipe and steel structure is under discussion with CIDB, OWNER and SC. Due to this, it hold the delivery of Cooling Water pipe and subsequently affect the Cooling Water construction work. 2. Stated below is the status of the COA wherein pipes were selected and waiting for sampling and test to be performed by Sirim for three (3) batches of Underground CS Welded Pipes. 3. TPIB for Steel Structure was already approved as shown below. 4. Detail procedure & guideline is still under preparation & discussion with CIDB / OWNER. 5. Detailed stepwise procedure is under development but as per present information, it takes longer than expectation. OWNERs support to resolve is required continuously in terms of RAPID Complex issue. |  | 15073 - Action Taken: COA can be substituted with vendor’s MTC endorsed by Contractor under Contractor’s responsibility. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Interface | 5293 | No access road between the boundaries within P2 area |  | 1. Limitation on transportation and loading area |  | 14413 - Recommendation: To improve the effectiveness of interface coordination meeting | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Project Management | 5994 | No analysis/study was conducted before change to DCS | 1. Management decision | 1. Long review process 2. Stringent engineering process |  | 15831 - Recommendation: To have a gap analysis / study to simplify the requirement. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Procurement | 6366 | No dedicated Procurement personnel to monitor overall procurement activities from RFQ to PO issuance. | 1. No dedicated personnel. | 1. Schedule delay. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Procurement | 5866 | No dedicated SPIR coordinator assigned by EPCC Contractor to prepare, coordinate and submit the SPIR form. | SPIR List: 1. CONTRACTOR shall review and complete its portion of the SPIR form by determining the quantities proposed to OWNER for approval. CONTRACTOR shall use interchangeability lists supplied by VENDORS or SUB- CONTRACTORS to compile a consolidated summary of all SPARE PARTS for the FACILITY to determine maximum interchangeability and to minimize SPARE PARTS inventory List Requirement as per CONTRACT 2. CONTRACTOR shall submit the duly completed SPIR forms to OWNER no later than three (3) months after issuance of the corresponding PURCHASE ORDER or SUB- CONTRACT for the EQUIPMENT and MATERIAL, along with relevant drawings and quantities as calculated by CONTRACTOR for OWNER’s information and action. | 1. Cost and schedule impact. |  | 15149 - Recommendation: SPIR list to be part of Project Milestone Payment and SPIR Coordinator roles and responsibilities to be clarified in PEP and Org Chart. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Precommissioning/Commissioning | 6066 | No dedicated team for Commissioning. | 1. Insufficient manpower. 2. Unclear requirement. | 1. Late in document submission. |  | 15651 - Action Taken: To identify / allocate dedicated team for Commissioning. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5665 | No delegation of authority by CONTRACTOR. | 1. No delegation of authority in the event of PM is travel outside office. 2. CONTRACTOR implemented unannounced new policy without informing OWNER (force 1 month unpaid leave). | 1. Unauthorized person signed for COA / Invoice on behalf of PM without OWNER approval (e.g. cost engineer signed on behalf of PM). 2. Delay in document approval process due to rejection by OWNER. 3. OWNER has to reschedule the critical meeting e.g. finance audit etc. due to unavailability of the focal person. |  | 15048 - Action Taken: The related document has been rejected and CONTRACTOR has to resubmit with authorized signature for owner approval. 15049 - Action Taken: CONTRACTOR to delegate the authority and get OWNER’s approval. 15050 - Recommendation: CONTRACTOR to strictly follow communication procedure. 15051 - Recommendation: CONTRACTOR to inform OWNER any major policy change that may impact project progress. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Planning | 5282 | No detailed schedule up to level 7 for construction work | 1. EPCC Contractor has a slow start during detail engineering causing late changes to the scope of work No requirement specify in ITB | 1. Project baseline schedule submission to iPMT was delayed by 1 year. 2. Some scope of works were not captured during the development of the project schedule. |  | 14397 - Action Taken: Strengthening of EPCC Contractor Engineering team at the early stage of the Detail Engineering to ensure development of the project is not affect. 14398 - Action Taken: To specify requirement in ITB up to level 7 for construction. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Document Management | 6273 | No effective method of sharing documents | 1. No common drive (system barrier). | 1. Prolong review cycle. |  | 16405 - Action Taken: Documents shared and tracked through email. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Document Management | 5289 | No Owners signatory on final revision of approved document | 1. No proper procedure state the signatory requirement | 1. Changes of content without any official review/approval |  | 14409 - Action Taken: To review/revise/prepare procedure and include the requirement | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Procurement | 5914 | No proper material management at site | 1. Contractor not provided comprehensive material management system | 1. No proper material management at site that contribute to the followings issues: a) Unable to provide early warning for shortage of material b) No segregation of Equipment/Material with Spare Parts c) Unable to locate materials due to improper storage and accountability. d) Require more time even more than one week to locate material. e) Had impacted badly the overall Project progress. f) Surplus management g) Missing materials |  | 15670 - Action Taken: Intervention by OWNER/PMC to station one full time Procurement Coordinator to asset and minimize further impact to the Project progress. 15671 - Recommendation: Emphasize on Implementation of Material Management during early stage 15672 - Recommendation: To have inventory software management system and manage by competent person | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Project Management | 6245 | No proper rollout on latest PPMS by GPD | 1. Disattached from project fraternity (Special project - TFDD, Tech Dept GPK / GPS). 2. No proper rollout from GPD. 3. Late awareness on new requirement. | 1. Late incorporation on change into PEP. |  | 16365 - Recommendation: GPD to provide proper rollout on any new requirement in PPMS to project team. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5474 | No Reducer Allowed for Pipe Size at Battery Limit Connection | 1. Silence on the use of reducer at Interface Point. | 1. Not economical 2. Over designed |  | 14596 - Recommendation: Allowing the use of reducer at Interface Point to optimize the design. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5393 | No standard drawing in project specs for Horizontal Vortex breaker. | 1. Horizontal Vortex breaker for vessel is not available in the Standard Drawing. | 1. Delay in vendor drawing finalization. |  | 14439 - Recommendation: Standard Drawing to include horizontal vortex breaker. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5618 | No synchronization in between transporting company and unloading material at laydown area. | 1. Material delivery not assigned to single company including loading, transport and unloading form point A to point B. | 1. No proper planning, where crane to park, no sufficient lifting gear, inexperience riggers and signalman to give instruction to crane operator during unloading. |  | 14919 - Action Taken: Observation and concern were highlighted to CONTRACTOR and improvement by CONTRACTOR was requested. 14920 - Recommendation: Work scope of each SUB-CONTRACTORs working under CONTRACTOR need to access during tendering to avoid so many company involve in single event. 14921 - Recommendation: Contractor to submit CV for critical position for OWNER’s review to verify the capability of CONTRACTOR’s identified personnel / workers. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5254 | No vendor support during construction period. | 1. Vendor support during installation not included in the service agreement. | 1. Late transformer accessories installation due to late vendor arrangement. 2. May damage transformer due to wrong accessories installation. |  | 14354 - Action Taken: Engage CONTRACTOR to come out with detailed action and mitigation plan for installation. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Procurement | 5915 | No visibility of delivery date | 1. Late issuance of procurement update and not uploaded timely in POL/PEDMS. | 1. Information from Contractor main office not share/update with the site team. 2. Project team unable to evaluate the actual status |  | 15673 - Action Taken: OWNER/PMC establish communication with Contractor main office for latest/required information 15674 - Recommendation: Timely updating and issuance of Procurement Update to Project team (Contractor and OWNER/PMC) 15675 - Recommendation: Frequent reporting i.e. weekly, monthly | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | HSSE | 5645 | Non implementation of RAPID Site HSE Instructions. | 1. Low awareness on importance of document management. 2. No evidence of implementation of RAPID Site HSE Instructions were observed. | 1. Increased project risks and potential consequence management by Central Directorate. |  | 14987 - Action Taken: Conducted verification to the implementation of RAPID Site Instructions and requested CONTRACTOR to furnish the evidence. 14988 - Recommendation: Contractor to track, record, and properly keep the evidence. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Procurement | 5218 | Non matching of fittings, pipings, and IFC drawings for piping spool pre-fabrication | 1. IF drawing issuing sequence not matching material delivery plan 2. Fitting delivery plan not matching with piping delivery plan 3. Fabricator not use the latest drawing issued by EPCC. | 1. Delay in schedule and cost overrun |  | 14290 - Procurement team to align construction team for piping / fitting delivery sequence 14291 - Engineering team to align construction and procurement team for IFC drawing issuing sequence. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5540 | Non Readiness of environmental control features prior to commencement of construction works. | 1. Erosion Soil Corrosion Plan (ESCP) was not yet approved before the target start of construction works. 2. ESCP is not fully constructed when construction activity starts. | 1. Delay in submission of ESCP by CONTRACTOR. 2. Inadequate ESCP could cause flooding and water ponding / backflow. |  | 14732 - Action Taken: Discussed with CONTRACTOR and constructed temporary environmental control features (silt traps, check dams, earth bund, temporary drainage) prior to the commencement of works. 14733 - Action Taken: Instructed CONTRACTOR to expedite the construction of ESCP with proper work planning and adequate resources allocations. 14734 - Recommendation: Preparation of ESCP should be done earlier, possibly by PMC prior to EPCC contract award. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6011 | Noncompliance design such as under rating of electrical component installed. | 1. Vendor data incorporation was not done properly | 1. Packaged equipment not functioning as required due under rating of electrical component. |  | 15860 - Action Taken: Site rectification and local purchase 15861 - Recommendation: Early rectification by Engineering to identify the problem and incorporate to design requirement | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5548 | Noncompliance of construction activity. | 1. CONTRACTOR did not properly cascaded the procedure and method statement to their SUB-CONTRACTOR. 2. Miscommunication between CONTRACTOR and SUB-CONTRACTOR due to language barrier. | 1. Construction activity was not carried out as per procedure and method statement. |  | 14754 - Action Taken: OWNER instructed stop work. 14755 - Action Taken: OWNER provided direct guidance to CONTRACTOR and SUB-CONTRACTOR. 14756 - Recommendation: CONTRACTOR shall lead their subcon and regularly update OWNER on daily planning to avoid miscommunication at site, daily coordination meeting is required. 14757 - Recommendation: To request CONTRACTOR to hire skill Supervisors and Foremen with English fluency. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | HSSE | 5644 | Non-compliance to RAPID Site Management requirements with regards to monsoon season readiness (road crossing using cut piles as culvert). | 1. SC used cut pile as culvert for road crossing. | 1. Causing blockage during monsoon season at some road crossing and increased the risk of flood. |  | 14984 - Action Taken: Instructed contractor to change the crossing using proper concrete culvert. 14985 - Action Taken: Ensure contractor maintain the condition of the crossings while the changing of material completed. 14986 - Recommendation: OWNER to ensure Contractor adhere on PETRONAS HSSE requirements. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | HSSE | 5643 | Non-compliance to various PETRONAS Requirements (e.g. Scaffolding, Lifting, Heavy Lifting, Working at Height, Confine Space, etc.). | 1. Lack of awareness, knowledge and skills at sub-contractors level in compliance with PETRONAS requirements. | 1. Increased the hazard of working at height, and increased risk of incident. |  | 14980 - Action Taken: Inspection, stop work, communication, and ensure scaffolding activities met PETRONAS Requirements. 14981 - Action Taken: Stop work, briefing, training, inspection, called for meetings to resolve the issue and supervision to all scaffolding works. 14982 - Action Taken: Repremind EPCC on the requirement and urge EPCC to expedite the scouting & recruitment process and follow up during weekly progress meeting. 14983 - Recommendation: To hire competent scaffolder, properly plan and ensure all scaffolding activities met PETRONAS Requirements. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Procurement | 5917 | Non-performance of MVL supplier | 1. High demand in the same time (overloaded) i.e. cable, HVAC, MAC, TI, FGS 2. Respond time very slow by vendor 3. Competency of MVL to perform the job | 1. Project delay ranging week to month 2. Quality issue (rusty materials) |  | 15678 - Action Taken: EPCC to source from alternative non MVL supplier 15679 - Action Taken: Engage the QAQC to do proper checking 15680 - Recommendation: PETRONAS to review MVL requirement/assessment i.e. stringent in assessing MVL 15681 - Recommendation: PETRONAS to consider during tender on recommended brand i.e. HVAC | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5204 | Non-standardized engineering decision across EPCCs. For e.g. flowmeter unit measurement in DCS (mass versus volume flowrate) | 1. No clear specification provided as part of standardization. 2. Conflict of inter discipline specs (e.g. electrical vs. civil) | 1. Difference in implementation that can lead to confusion during operation. 2. Longer process to align the difference specs. |  | 14262 - Clear and standardized direction to be given by Core Team, and be driven/supported by experiences from Operation. 14263 - ITB to address this such potential issue. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5968 | Not complying to instrument redundancy communication protocol between DCS & Electrical Equipment. | 1. Inter-discipline miscommunication | 1. Major equipment will lost control & will lead to plant stop. Electrical equipment will don’t have redundant communication. |  | 15797 - Recommendation: Coordination & interface with electrical has to be made earlier during engineering stage. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5090 | Not include review of accessibility 3D model review location review of TML ,cathodic protection and corrosion coupon location | 1. PRBI study was done later than the 3D model review 2. Requirements not clearly specified in ITB | 1. Rework on TML location to suite the platform availability |  | 14165 - Action Taken: RC engineering escalated the issue to the CORE engineering team in KL 14166 - Recommendation: 3D model review to include the location review of TML ,cathodic protection and corrosion cupon location to ease in maintenance and controlling cost for accesibility of inaccesibility location by permanent platform. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2100 | Not well verse in oil and gas project documentation requirement | 1st project with PETRONAS | - Delay in submission of project documentation. - Late work commencement. | - PMC to guide and facilitate i.e provide samples/ guidelines to package contractor. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Precommissioning/Commissioning | 5901 | Nuclear sources: Import license, transportation, storage, installation and Commissioning at site Nuclear sources. |  |  |  | 15200 - Applied Solution: The third party in charge to clarify the requirements of Local Authority regulation 15201 - Applied Solution: Clarified with Owner the responsibility to require the import permit 15202 - Applied Solution: The requirements for transportation, temporary storage, installation and commissioning at site 15203 - Suggestion for Improvement: At the start of engineering phase the Country Law requirements have to be investigate in order to have complete picture on import license, transportation, storage, installation and commissioning at site. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5499 | Only creep settlement is considered for the piping stress analysis | 1. Initial settlement after dewatering (Hydro test) is not specified in Project Specification and PTS | 1. Potential Piping overstressed 2. Potential Additional rework 3. Potential Change order and VO |  | 14631 - Recommendation: To evaluate the Hydro test result 14632 - Recommendation: To reanalyze pipe stress with new initial settlement 14633 - Recommendation: To capture initial settlement consideration in project specs and PTS | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5199 | Opportunity loss to adopt more cost effective solution for a licensed unit. | 1. Less stringent specs by Licensor compared to PTS. | 1. Engineering solution can be expensive. |  | 14253 - To allow the use of Licensors specs (those which are cheaper, if any) in place of PTS as part of cost optimization. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2070 | Optimization in elevation of platform to reduce excess in material | -Excess in material (Earth and rock) | -Cost saving by reduction in cutting / excavation in cut area - | -Issue revised IFC drawing -Regular monitoring of balance cut and fill. | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5774 | Optimization of LLI Strategy to meet schedule requirement. | 1. Advanced procurement of Long Lead Items (EO reactors and Cycle Gas Compressor) was essential but insufficient to de-risk the compressed EPCC schedule – also hiccup on vendor design reviews due to unexpected EPCC award delay. | 1. Tight EPCC implementation schedule with little flexibility and float. |  | 15389 - Recommendation: LLIs should be included as part of FEED Contractors SOW and ensure effective handover at the point of EPCC award. 15390 - Recommendation: More consideration should be given to include critical static equipment as LLIs as well. 15391 - Recommendation: Should have also ordered schedule critical SS clad columns. LLI work process under PMT / PRPC supply division was very difficult due to lack of previous experience | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Engineering | 6040 | Overlap of ROW alignment between JKR FT92 NRR (J52) and PAMER pipeline route (Section 3). | 1. Lack of coordination. 2. JKRs NRR Project was still at an early stage and therefore was lacking details / finalization when PAMER was ready to proceed. 3. Several last minute design changes by JKR. 4. Overall coordination agency was not yet set up. | 1. Delay in finalizing PAMER detailed design. 2. Completed construction of slip road crossing (concrete surround) but had to be abandoned later because JKR changed the location. 3. Change order (additional cost to PAMER) due to additional crossings. |  | 15599 - Action Taken: Line of authority of coordination agency. 15600 - Action Taken: Close coordination with the NRR road contractor. 15601 - Action Taken: Close monitoring of the works at site. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5628 | OWNER should be notified by CONTRACTOR in advance prior to any communication and engagement with Authorities regarding inspection / site visit to TCF. | 1. Late notification by CONTRACTOR to OWNER. 2. TCF SUBCONTRACTOR did not inform CONTRACTOR about their communication with the Authorities. | 1. OWNER did not have ample time to assess readiness of site / buildings for inspection. |  | 14944 - Action Taken: Did a round of quick physical check on the readiness of site / buildings with CONTRACTOR. 14945 - Action Taken: CONTRACTOR performed remedial actions immediately. 14946 - Recommendation: Communication protocol is to be established between SUBCONTRACTOR, CONTRACTOR and OWNER in dealing with Authorities. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6075 | Owner supplied the crusher run | 1. Utilisation of internal resources | 1. Cost and time saving |  | 15541 - Action Taken: Owner identified the source of crusher run from other internal project and supplied it for the new requirement of MOLF platform | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5815 | Oxygen Service Requirement for Valve | 1. Cleaning - Valves in oxygen service lines shall be cleaned to remove contaminants such as greases and oil. 2. Valves in high pressure nitrogen line connected to the oxygen service line shall be supplied as cleaned condition to prevent that contaminants flow into the oxygen line. | 1. DEP 31.10.11.31 - Gaseous Oxygen Systems |  | 15477 - Action Taken: Piping lines where the cleaning is required have been checked and shared at the beginning of project. 15478 - Action Taken: Valves in high pressure nitrogen line connected to the oxygen service line are supplied as cleaned condition as well. 15479 - Recommendation: Preventive Action. 15480 - Recommendation: Cleaning shall be considered not only for the oxygen service line, but also for the lines connected to the oxygen service line. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5450 | P14 Fire water system main ring was routed inside P22 battery limit | 1. This was agreed during engineering stage to allow P14 to route inside P22 BL since P14 claim they dont have sufficient area for route the FW header. | 1. Late construction activities due to improper planning and action by P14.Where P22 need to wait P14 to complete each activity. 2. Challenge for P14 in construction stage (work front availability / permit / access) faced by P14 to enter P22 for the FW system installation. 3. Conflict between 2 contractors who will start first 4. Potential damages and rework |  | 14559 - Action Taken: A new schedule required to be agreed in order to have inline construction sequence and activity. 14560 - Recommendation: To ensure each contractor only working in allocated / dedicate battery limit | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5849 | P7 buildings were not included in RAPID Master Building List during FEED. | 1. FEED drawings and information was not reviewed and updated properly. | 1. Cost and schedule impact. 2. Non- compliance to authorities |  | 15114 - Recommendation: FEED drawings to be reviewed and approved properly. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5969 | Package equipment SAT not properly done. (Chlorine, sludge dryer) | 1. Vendor not doing SAT as per procedure. Vendor lack of knowledge. LLWT not leading the SAT. | 1. Cannot complete SAT as per plan. |  | 15798 - Action Taken: Redo the SAT 15799 - Recommendation: SAT procedure should be reviewed and approved by competent personnel | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5907 | Painting Colour Scheme for Package Supplies. Painting Colour Scheme for Packages have not been reviewed on Painting Procedures issued by Vendors. |  |  |  | 15211 - Suggestion for Improvement: Review of Painting Procedure (including Painting Color Scheme) issued by Vendors shall be performed by discipline in charge for issuing of the Project General Painting Specification. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Quality | 5121 | Painting peeling on Vendor vessels was found at site after delivery | 1.Surface preparation before next layer of coating did not finish properly 2.Over painting 3.Painting damaged by hitting from external force | Owner is not satisfy the painting quality and request to repair |  | 14240 - Recommendation: Vendors painting worker shall be well-educated before performing the job. 14241 - Recommendation: Vendors procedure shall be reviewed by engineering team and QC team then give comment to the procedure clearly if any. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Project Management | 6052 | Payment Process. | 1. Speedier payment. | 1. Better cash flow for contractor. |  | 15624 - Action Taken: Payment can be within 15 days | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5620 | PCB team KL had a different understanding on scope of work. The MC, The agenda flow, the presentation compilation had to be done by iPMT. | 1. Misalignment between the PCB master schedules vs. practical implementation at UPT level. | 1. Programme still went on well, but preparation was hectic due to last minute rush to nominate a MC, explain agenda changes, explain flow of event, etc. |  | 14924 - Action Taken: Dry run conducted and all shortcomings were rectified prior to the real event. 14925 - Recommendation: Clear and detailed explanation to each party on their scope of work. 1) Clear and detailed explanation to each party on their scope of work. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5785 | PEDMS could not generate a Document Control / Deliverable Status Report that was effective. | 1. There was no report template available to enable plug and play migration of data from PEDMS. 2. PEDMS Administration Team were short staffed and didn’t have sufficient resources to come up with a proper template. | 1. There was no means of keeping track of project deliverable status by the UPT and effectively report to management. |  | 15416 - Action Taken: We engaged in extensive discussions with PEDMS Team in KL to convey the projects requirements for a workable Document Control Report. 15417 - Action Taken: Samples from other projects were also provided to them for their reference. 15418 - Action Taken: Finally, a workable template was rolled out but this was at the tail end of engineering phase. 15419 - Recommendation: PEDMS Team or other Document Control Teams for future project should put sufficient effort and resources to develop Document Control Report templates from the beginning of the project. 15420 - Recommendation: Templates from other projects that are compatible with different PDDM systems (e.g.) POL or PEDMS should be shared with new projects so that they can readily adopt them. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5750 | PEDMS Reviewer (Core Engineering): Streamlining of review workflows. | 1. Unreview document by assigned core engineering team. | 1. Overdue document submitted / issued to Contractor – thus delayed the issuance of next revision. |  | 15331 - Action Taken: Reminder were given to the Core Engineering team – however the same issue happened every week. 15332 - Recommendation: To ensure the DDM is assigned to the correct parties and position level. 15333 - Recommendation: To have an approved DDM officially cascaded to UPTs and implement accordingly. 15334 - Recommendation: A responsible person should be appointed to manage the Central DDM. 15335 - Recommendation: A consolidated Document Matrix should be established and managed centrally from inception to close out. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5738 | PEDMS: Best Practice: Offline review of documents beforehand to reduce number of revision of PEDMS. |  | 1. Avoid reproducing unnecessary revision of the document and reducing PEDMS input. |  | 15300 - Action Taken: CONTRACTOR practices that most of the time. 15301 - Recommendation: OWNER and CONTRACTOR shall implement such document arrangement from the beginning stage of Engineering. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5747 | PEDMS: Obsolete TEQs not cancelled on PEDMS. | 1. No instruction were given by Contractor DC to OWNER DC regarding the cancelled document – end up those document remained pending in PEDMS. | 1. Inaccurate status of documents on PEDMS. |  | 15325 - Action Taken: Comments were made to Contractor’ Project Engineer for rectification. 15326 - Recommendation: To assign workflow for TEQ and PDR in PEDMS. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5481 | Performance Guarantee (Blending Calculation) | 1. CONTRACTOR is not capable to perform the scope. 2. CONTRACT is not clear about the requirement. | 1. Additional work to OWNER. |  | 14605 - Action Taken: OWNER assisted EPCC for the blending calculation. 14606 - Recommendation: CONTRACTOR capability shall be accessed prior award. 14607 - Recommendation: Requirement in the CONTRACT shall be clearly defined. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Construction | 6297 | Phase 2: late site procession | 1. Late hand over to EPCC contractor due to 3rd part Contractor | 1. Late Start by Contractor/EOT |  | 16458 - Action Taken: OWNER / PMC coordinate, as to provide work front to Contractor 16459 - Recommendation: OWNER / PMC should follow its own schedule | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Construction | 5898 | Pile foundation design and execution. The schedule of these activities starts early and is not in compliance with the definition of the loads to be supported by the structures or single foundations. |  |  |  | 15196 - Applied Solution: It has been decided to consider the loads coming from similar plants added to the site conditions of this plant. The design has been conservative to support additional minor loads coming from the detailed design. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5740 | Pile Head Treatment: Piles head treatment. | 1. No specific requirement in Codes and PTS for pile head treatment for tension spun pile. | 1. Dispute views on pile head treatment for tension pile between Reviewer and Contractor. |  | 15304 - Action Taken: Contractor to design adequate adhesion resistance of pile cap and spun pile to tension force. 15305 - Action Taken: Application of non-shrink grout to the piles that experienced 50% tension. 15306 - Recommendation: To spell out technical requirement for tension pile clearly in PTS / Project spec / Design basis. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Construction | 6293 | Piling: Lack of equipment comparing to the number of pile | 1. Insufficient machine | 1. Schedule delay |  | 16449 - Action Taken: Mobilized more machine 16450 - Recommendation: To ensure subbies have enough machinery 16451 - Recommendation: Value engineering for other methods. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5501 | Pipe crossing bund / dykewall | 1. Insufficient height of pipe crossing dykewall. | 1. Dykewall volume capacity is less than PTS requirement. |  | 14636 - Action Taken: Recalculate the dykewall volume capacity and to exclude tank freeboard volume. 14637 - Recommendation: To ensure 3D model to capture pipe crossing the dykewall at the early stage. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5225 | Pipe crossing underneath pipe rack | 1. Constructed according to engineering drawings | 1. Impacting construction interface issues |  | 14302 - Action Taken: Strategize the construction sequence | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Procurement | 6045 | Pipe supplier unable to meet pipe demand. | 1. Supplier had earlier slowed down the production because of limited staging area, and when the construction activities picked up subsequently, the supplier was unable to cope with the demand. | 1. Short supply of pipe during construction to support increased construction team and construction activities. 2. Schedule delay. |  | 15613 - Action Taken: Go for second supplier. 15614 - Action Taken: Included the issue as one of the critical issues being closely monitored during monthly risk management meeting. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5258 | Pipe support in instrument trench is erected higher than design | 1. Engineering drawings / 3D model don’t show pipe support location. | 1. Pipe supports installed in the middle of the trench. |  | 14359 - Action Taken: Cutting of paving to make way for new route of trench | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5493 | Piping forces are being received from Piping department for the structural design based on the Design condition of pipe for summary of maximum values. | 1. Civil dont have a format for piping load input. 2. Misinterpretation | 1. Piping forces inputs for structural and foundation design. |  | 14623 - Action Taken: Piping normally provides occasional loads-wind and seismic as applicable, hydrostatic loads and operating loads Fxmax,Fymax and Fzmax respectively. 14624 - Recommendation: Standard format must be established | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Construction | 5899 | Piping MTO for Instrument Control Valves Instrument Control Valves purchasing cycle is directly linked to Piping engineering schedule activities. |  |  |  | 15197 - Suggestion for Improvement: It may be standardized to buy 2 or 3 different fittings and flanges sizes for each control valve (or group of them) up to a certain diameter (i.e. 10 or 16) in order to avoid to buy on urgent basis at later stage | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5709 | Piping: Best Practice: TML can only be finalized during RBI. But RBI exercise only happens after vendor print i.e. GA and piping iso are available. However platform and ladder clips design have to be freezed for manufacturing. |  | 1. Delay avoidance on fabrication of major equipment. |  | 15229 - Preliminary TML location was reviewed by PGTSSB only on high rise equipment such as column. In doing so, fabrication can take place based on preliminary platform and ladder clip location. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5710 | Piping: Delay in development of valve modelling in SP3D. | 1. Auto conversion function for DDP not available inside the SP3D. | 1. Delay in vendor print and DDP conversion issue have resulted to inaccurate model review. 2. Inaccurate valve dimension leading to unnecessary access platform. |  | 15230 - Action Taken: Manual conversion of valve dimension into SP3D was done. 15231 - Recommendation: To get contractor fix the DDP conversion issue and speed up and ready much earlier on vendor data. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5011 | Piping: IP point completion | 1. Contractor not binded by IP point completion | 1. Time of IP completion not same. 2. Probable cost impact (back charge) by Other Contractor. 3. Schedule impact to commissioning. |  | 13956 - Development of Integrated schedule control. 13957 - To include milestone for IP3. 13958 - To include responsibility for Interconnecting Contractor. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5712 | Piping: Misinterpretation of project specification on closed drain piping secondary containment. | 1. P11s glycol and carbonate closed drain line was designed with no secondary containment (concrete trench). 2. Typical drawing in project specs for closed drain system was ambiguous led to misinterpretation. | 1. Major rework on UG closed drain network. |  | 15234 - Action Taken: PDR was approved with conditions on certain assurance with regards to alternative solution (HDPE membrane). 15235 - Action Taken: Good collaboration between CONTRACTOR, UPT and Core Eng. in coming up with alternative to minimize impact. 15236 - Recommendation: Correction in project specification | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6341 | Piping: 90% model review bring upfront (1 month) | 1. Management decision to expediate engineering schedule. | 1. Re-work. 2. Model it based on assumption (vendor packages). |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Interface | 6367 | Piping: Interface issue with other packages (e.g. P3, P14). IFC drawing / 3D model provided not reflecting actual site construction | 1. As built drawings are not available at that point of time. 2. Insufficient information for actual underground by 3D model. | 1. Schedule impact. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6344 | Piping: Overall procurement strategy (not using same vendor from P1) | 1. New local vendor for lower cost. 2. Split above and underground piping to different vendor. | 1. Schedule impact. 2. Prolong procurement process. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6348 | Piping: Stringent RAPID specification for NACE compliance piping materials for Wet H2S service. | 1. PTS requirement. | 1. Difficult to source material for small quantity (no mill accept small quantity order). 2. Need to source for ex-stock material which difficult to meet specification. 3. Time consuming to raise VCR. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5243 | Platform beam doesn’t fit to column external attachment | 1. Latest construction drawing not shared with vessel vendor | 1. Site modification at site slightly delay the installation date |  | 14336 - Action Taken: EPCC to update latest fabrication drawing changes promptly to vessel vendor and ensure changes been made accordingly. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5452 | PMRC Code | 1. The requirement to follow PMRC Code only after the award (previously CONTRACTOR used Shells MESC code number for material identification) | 1. This has caused delay in Piping activities MTO and procurement. |  | 14564 - Action Taken: Action already taken and all material incorporated accordingly. 14565 - Action Taken: PMRC code already been reviewed, rectified and checked by CONTRACTOR and CORE team. 14566 - Recommendation: Establish material class and direction what to be used should be firm during beginning of the project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5717 | PMRC: PMRC database. | 1. Unclear instruction on PMRC scope in ITB led to wrong interpretation by CONTRACTOR. | 1. PMRC Piping Classes and datasheets was prepared offline. However the format is accordance with PMRC standard format. |  | 15246 - Action Taken: Core engineering had raised a project memorandum to strengthen the requirement for CONTRACTOR to upload all piping classes and datasheets into PMRC system. 15247 - Recommendation: ITB requirement on PMRC scope need to be amended to make it clearer. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5609 | PMT had to conduct additional pre-Q for the vendors which had been selected / awarded by other packages or currently existing in MVL under different category. | 1. No detail guideline available to address the situation on selection the vendors whom has been pre-qualified by other packages or existing under different category in MVL. | 1. Delay in issuance of PO and potential delay in delivery since both PMT and EPCC Contractor require additional time to conduct Pre-Q and audit for the vendors. |  | 14896 - Action Taken: Proceed with pre-qualification exercise. 14897 - Recommendation: To enhance the guideline in utilization of vendor across RAPID Project. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5795 | PMT organization and manning - assignment of dedicated resource at design office i.e. DHSE, Material Corrosion (MCI), Package, HVAC. | 1. Control of project execution resource cost might have been tight. | 1. Document reviews and turnaround delay. 2. Lack of coordination and inter discipline checking. |  | 15442 - Action Taken: Common resources were deployed on need basis but the delays is still occurred. 15443 - Recommendation: To benchmark suitable deployment of key resources at different phases against project of similar nature. 15444 - Recommendation: More importance should be given to project execution requirement. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5608 | PO is not in accordance to Award Recommendation. | 1. Inconsistency in delivery period between Award Recommendation and PO issued by CONTRACTOR. 2. Some delivery period in CONTRACTORs submitted Unpriced PO not in line with their Award Recommendation. | 1. Some deliveries are expected to be beyond L3 Schedule. |  | 14894 - Action Taken: the concerns to CONTRACTOR and requested CONTRACTOR to ensure contents of PO in accordance to Award Recommendation. 14895 - Recommendation: Notification by CONTRACTOR on any changes instead of OWNER aware about it after reviewing the PO only. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5611 | PO not able to be issued on time with the availability of MVL | 1. Internal dispute on the recommended OEM after evaluation of TBE despite the OEM is MVL vendors. 2. Concerns raised by TA on the recommended OEM since the OEM is new OEM to PETRONAS. | 1. CONTRACTOR not able to proceed with the purchasing according to schedule since waiting approval from OWNER. |  | 14902 - Action Taken: Compiled as much information as possible and came up with mitigation plan on the new OEM. 14903 - Recommendation: MVL to be a control document which to be reviewed by both Procurement and Engineering at Centre before applying to project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5934 | POL / Documents transmit | 1. Documents hold by LLWT and not uploaded to POL. SMHB do not have direct access to upload documents to POL | 1. Reviewer do not receive notification for document review and not able to trace the document in POL, however SMHB emailed to ask to review the documents which they have submitted |  | 15723 - Action Taken: To check with document controller to coordinate with LLWT to trace & upload the documents | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5224 | Poor construction sequence especially related to underground works i.e. foundation, E&I trench, Process Pipe Trench & UG piping | 1. Tight project schedule 2. Changes of engineering drawings | 1. Erosion underneath foundation 2. Settlement of shallow foundation 3. Poor compaction |  | 14301 - Action Taken: Strategize the construction sequence by priotizing the deeper foundation or UG services | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5964 | Poor execution and understanding on the WinPCS and Turnover process i.e. Producing Check sheet C. |  | 1. Delay in project execution as EPCC takes time to understand |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5249 | Poor packing of motor | 1. Poor packing for storage from vendor site 2. Incorrect/poor storage at site | 1. Motor component damage, require repair before installation |  | 14343 - Action Taken: Store motor at correct location (Outdoor with cover) | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Construction | 6260 | Poor performance by E&I subcontractor | 1. Lack of skilled manpower due to commitment on other projects in RAPID. | 1. Schedule impact. |  | 16386 - Action Taken: Daily tracking and progress update. 16387 - Action Taken: Mitigation plan submission by EPCC. 16388 - Recommendation: To evaluate the limit on the current project workload. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6016 | Poor quality of Electrical wiring works by vendors | 1. Poor wiring by Equipment Vendor on the Terminal Block create short circuit on the equipment. 2. Limited participation by operation team (OWNER/PMC) during FAT | 1. Incident happen during commissioning of equipment 2. Rework |  | 15870 - Action Taken: Detail inspection on the equipment motor terminal block and Junction Box ensure no short circuit. 15871 - Recommendation: Early notification to E&I team to inspect to terminal ensure equipment received in perfect condition following the safety checklist | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | HSSE | 5273 | Poor UAUC submission from supervisory level up to management level. | 1. Lack of accountability as there is HSE is HSE Team business mindset. 2. Lack of awareness and incentive program which designed for supervisory and management level. | 1. Inconsistent submission on UAUC submission from iPMT and EPCC supervisory up to management level. |  | 14386 - Action Taken: Increase awareness program which specifically design for supervisory and management level. 14387 - Action Taken: To offer incentive or remuneration for highest contributor or best UAUC. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Procurement | 5406 | Poor Vendors selection for items / services not listed at MVL. | 1. EPCC finding cost saving. 2. The proposed vendor is not similar during bidding. | 1. Potential quality issue. 2. Impact on delivery. 3. Unfamiliarity with project and PTS requirements. |  | 14460 - Action Taken: Advised thru feedbacks on references with company profile, workshop loading and job references with benchmark set on requirements of good vendor selection for future sourcing. 14461 - Action Taken: Continued monitoring and feedback on vendor selection submitted thru PreQs. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Construction | 5885 | Positive: Civil work activities currently having good progress despite rainy season | 1. Early start and mobilization of sufficient manpower for the initial works. 2. Prefabricate the rebars prior to installation inside trench. This shortens the time for the trenches to be exposed. 3. Excavation and preparing the earth ditches to expedite the dewatering of rain water. 4. Method statements and JHA prepared, discussed and approved by EPCC/Owner prior to work commencement | 1. Steel structure erection works can be started in Dec due to the timely completion of the interconnecting pipe racks. |  | 15173 - Recommendation: Contractor shall lead the sub-contractors 15174 - Recommendation: Contractor shall prepare L4 construction plan for effective monitoring of sub-contractors | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Engineering | 6042 | POSITIVE: Designers decision to raise Seluyut Dam FSL from 24 meters to 26 meters msl during the conceptual design stage when there was no clarity then on the intended final dam capacity. | 1. To maximize potential use of dam with minimal incremental cost. | 1. Minimal cost impact, but significant increase of additional storage capacity that had benefited the projects and the States future water supply planning. 2. No impact on schedule. 3. 520mld to 900mld increase made the storage buffer more reliable. |  | 15605 - Action Taken: To conduct cost benefit analysis for major resources to take advantage of similar situation i.e. minimal cost and schedule impact, but significant benefits. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | HSSE | 5880 | Positive: Early mobilization of EPCC HSE Personnel to site | N/A | 1. Able to manage HSE issue at early stage and set right thing at the first place. |  | 15167 - Action taken: Early mobilization of EPCC HSE Personnel to site | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5448 | Positive: Establishment of PMRC Code at earlier stage of project |  | 1. Reference (piping class) for future project 2. Standardization of system throughout PETRONAS |  | 14554 - Recommendation: To implement PMRC Code for future project | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | HSSE | 5877 | Positive: Formal Safety Assessment (FSA) studies e.g. HAZID, Bow-Tie, Fire Safety Adequacy Review (FSAR) and Performance Standard conducted with the attendance of PTA from PMC Team | N/A | 1. Ensure consistency of the studies with Project Specification and others related standard/practice done at PETRONAS. |  | 15163 - Recommendation: The practice shall be implemented at others RAPID Packages | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5491 | Positive: Good collaboration between UPT and EPCC managing the scope changed. |  | 1. Fast decision making 2. Minimize rework |  | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5460 | Positive: Implementation of RAPID P22 Fire Safety Detailed Design Dossier (FSDDD) Report Writing | 1. Lack identification of missing information critically needed in FSDDD presentation for JBPM approval | 1. Challenges in meeting requirements as described in flowchart part of procedures developed by JBPM to facilitate the process of obtaining the Dept. support for CCC issued by Majlis Penbandaran Pengerang. |  | 14578 - Action Taken: Developed different approach with constant guidance from Fire Safety PTA | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Procurement | 5861 | Positive: Increase surveillance level especially at China and critical items | 1. To meet CIDB requirements | 1. Non- compliance to regulatory requirements 2. Increased product quality |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Procurement | 5508 | Positive: Managed to hold subcontractors / vendors to stay working with PETRONAS |  |  |  | 14652 - Action Taken: Early intervention by UPT and management 14653 - Action Taken: Creating an ESCROW account to monitor the fund movement within Malaysia (specific for P22 project) 14654 - Action Taken: Issuance of comfort letter to vendors to convince them to participate in RAPID P22 project. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | HSSE | 5278 | Positive: Perpetual HSE Incentive and Celebration | 1. Small token being given to workers by monthly basis: • Best Safety Award (Worker) • Best Safety Award (Supervisor) 2. HSE Celebration in conjunction of 100,000 and 500,000 man hours without LTI. | 1. Increase workers motivation as they felt that they are well appreciated. 2. Cultivate the sense of accountability as we have they are part of project completion factor regardless their position and level. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Construction | 5884 | Positive: Piling activities completed ahead of schedule | 1. Selection of capable subcontractor who requires minimal supervision. In the work coordination and supervision, site team observes the subcontractor possess smooth work sequencing and safety consideration attributes with proper barricades and signage prior to work 2. Proper planning and tracking of the associated tests until completion. 3. Method statements and JHA prepared, discussed and approved by EPCC/Owner prior to work commencement. | 1. Civil works started earlier. |  | 15171 - Action taken: Good collaboration between OWNER and contractor 15172 - Action taken: Focused on contractors strength | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | HSSE | 5277 | Positive: Positive HSE Awareness level among supervisory and management level. | 1. Daily Tool Box talk (HSE Issue) has been delivered by Construction manager as well as supervisor. Positive • Any issue pertaining HSE matters have received strong support from Supervisors, Construction Managers & Project Manager. | 1. Most of HSE activities are easily implemented as management level is willing to give their support and commitment. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5459 | Positive: RAPID P22 Inter-Discipline Check (IDC) For Vendor Documents | 1. Poor multidisciplinary coordination in reviewing respective Vendor documents | 1. Delayed in finalizing Vendor document (IFC issuance) and subsequent outstanding arrangement for respective Vendor procurement |  | 14576 - Action Taken: Periodic offline review involving relevant multi-disciplinary participation in demonstrating minimization of review cycle through official Document Control issuance. 14577 - Action Taken: Relevant queries clarification with identified Vendor through TEQ, tele-conference, video conference (wherever necessary) to avoid confusion / discrepancy. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Procurement | 6046 | POSITIVE: The PCC contractor was able to maintain its sub-contractor and suppliers until project closure. | 1. Long term relationship or arrangement between main contractor and the subcontractors / suppliers. 2. Timely payment by the main contractor especially during the period of needs (like before the Chinese New Year). | 1. Smooth implementation of the project. 2. Achievement of project milestones as per schedule. |  | 15615 - Recommendation: Proper evaluation during tendering stage on contractors working background and history 15616 - Recommendation: Ensure timely payment to the main contractor 15617 - Recommendation: Involve subcontractors key personnel in key meetings to assess and ensure commitment. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Procurement | 5863 | Positive: TPI appointed by PMC inspector was ineffective | N/A | 1. Delay in manufacturing progress |  | 15140 - Action taken: Deployment of discipline engineer on key package & critical equipment instead of TPI. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5084 | Post award (and late) changes and contradiction in Project Specifications | 1. Several on-going initiatives 2. Clarification to FEED requiremement 3. Misalignment between project spec and PTS 4. Misaligment between multidisiplinary PTS requirement. Eg. control valve hardfacing material (inst vs piping); earthing philosophy (inst vs elec). 5. Lack of interdisciplinary communication to incorporate all specification results in late clarification/incompliance. | 1. Increase in number of rework 2. Delay in completing task/action items |  | 14149 - Early confirmation on the additional requirement 14150 - To establish early communication and clarification on the items involved. 14151 - Review PTS requirements | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5257 | Potential interfacing issue for electrical and instrument cable crossing | 1. As per the ITB requirement, only road crossing require duct bank. Hence any crossing interfaces requires completion of other disciplines works or temporary arrangements | 1. Delay in cable laying. |  | 14357 - Action Taken: Temporary bridge with scaffolding or temporary cross over pipe is provided. 14358 - Action Taken: To propose ITB to clearly mention to have duct bank for electrical/instrument crossing | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5956 | Power and control cable ordered should design with spare and wastage contingency | 1. Actual length longer than design measured length from drawing. | 1. Shortage of cable quantity for work front and cable can be lay as per drum cutting list. |  | 15769 - Action Taken: Additional cable quantity require to be ordered to overcome shortage 15770 - Recommendation: Before material take off, design engineer should check the quantity ordered taking consideration of spare and wastage contingency. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5214 | Precedence on Packaged Equipment: Driven equipment should take precedence whenever there are discrepancies between spec. | 1. Precedence are not specified in the ITB. | 1. Deviations will be raised against the driven equipment. |  | 14280 - To avoid discrepancies between specifications. 14281 - ITB to specify the precedence when deal with discrepancies between specs. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5431 | Preference project requirement is not aligned (e.g. Partial Stroke Requirement for EIV) | 1. OWNER preference / experience and project requirement not aligned | 1. AO cards on the system side had to be removed and remain unused 2. PST facility at valve had to be removed and wasted 3. Cost impact to CONTRACTOR for removal of the facility |  | 14522 - Action Taken: PST facility at both valve and system side were removed 14523 - Recommendation: PST should be clearly specified in ITB not required for Tank Farms. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Quality | 6198 | Presence of QA / QC personnel during FAT. | 1. Unavailability of EPCCs QA / QC personnel during FAT. ie: Online FTNIR | 1. Deviation of ITB. 2. Owner has to take charge on FAT requirement. |  | 16248 - Action Taken: NCR issued and responded by EPCC. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5954 | Pressure Gauges procured are to have correct ranges (to follow operating pressure) specified by Process in the approved line list. | 1. Many pressure gauges installed were under ranged. | 1. Many pressure gauges installed are under ranged. They were all installed as per the old line list. |  | 15765 - Action Taken: New line list was revised and process identified the correct ranges for pressure gauges. New pressure gauges are procured and will be replaced. 15766 - Recommendation: The line list has to be finalized with the correct operating ranges before the procurement of the pressure gauges | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | HSSE | 5796 | Process / HSE: Toxic EO exposure (STEL) in case of emergency release | 1. Operation team expressed concerns about toxic EO exposure (STEL) in case of emergency release. 2. Incomplete specification in PTS on STEL. | 1. PTS requires mitigation for IDLH while Operation insisted on mitigation for STEL and PEL. 2. Potential change order. |  | 15445 - Action Taken: Licensor feedback received on safe handling of emergency EO. 15446 - Action Taken: Mitigation measures (dilution steam and increase of EO vent elevation applied). 15447 - Action Taken: Concerns on Emergency toxic EO release to atmosphere addressed through appropriate mitigation measures. 15448 - Recommendation: Applicable PTS shall be updated clearly specify toxic exposure limit (PEL) to be mitigated. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5496 | Process Datasheets are issued for some of the Instruments but not for all the Instruments. Issued Process Datasheets are not updated. Subsequent revisions of Process datasheets are not issued by Process Dept. | 1. On / Off Shutdown valve, controls and safety valves Process is providing instrument process datasheets. For other field instruments, process providing the instrument process data in prescribed format | 1. Process Data for Field Instruments. 2. Delivery Schedule is also affected due to same. 3. This may lead to wrong selection of Instruments. |  | 14627 - Action Taken: This is typical to current project. Such issues have not been observed in other projects. 14628 - Recommendation: Process Datasheets need to be established | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5921 | Process documents not finalized before DCS Graphics & Software programming and testing. | 1. EPCC Contractor had no experience using DCS previously. 2. Project team (Process) was not included in the FAT schedule planning. This had contributed to the unreadiness of process document for the DCS work and testing. The control system Vendor had executed DCS/ESD/FGS work based on revised Process document (P&IDs, PCN, CEM) that were not reviewed by the Project team. 3. Certain information required from Package Vendor was unavailable causing a lot of punch items created during testing. | 1. While FAT is ongoing for the DCS/ESD/FGS system, EPCC Contractor had continued updating changes on these documents causing rework by the Vendor, delay in testing and lots of punch items created. 2. Design review (HAZOP, SIL studies etc.) were performed on the earlier version of Process documents. Any changes made during FAT might have led to inconsistencies and non-compliance as these changes should have been reassessed and approved prior to the implementation. |  | 15694 - Action Taken: Ensure all markups and changes done from the FAT were carefully picked up by EPCC Contractor and updated into the affected P&IDs, PCN and CEM. 15695 - Recommendation: Ensure all Vendor had submitted all data and information on time so that EPCC could finalize all relevant process document e.g. P&IDs, Control Narrative and CEM prior to DCS/ESD/FGS system FAT. 15696 - Recommendation: To inform and include Process team in Graphics/Software FAT planning. 15697 - Recommendation: Ensure pre-FAT item is checked and EPCC Contractor had performed initial check with the DCS Vendor before the actual FAT begun. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Interface | 5424 | Process interface integration management can be further improved. | 1. Current arrangement involving too many interfacing that depending on other packages. | 1. Utility design condition that can impact other process units pipe rating / schedule (e.g. LP steam condition). 2. Piping connections from one unit to another within the same package will have to go through other package scope in the P&ID. |  | 14509 - Action Taken: Finalized the IP as early as possible to avoid impact to construction. 14510 - Recommendation: Scopes split to be properly done. 14511 - Recommendation: Minimize dependencies on other packages for internal process line. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5399 | Process safety specification not provided in early stage. | 1. Several specification released / updated from Directorate which is very late and beyond Contractors schedule. For example: HEMP specification (consists of Design HSE Case, SCE PS, LOPA, etc.). | 1. Late changes to the finalize design which may result in potential change order. |  | 14447 - Recommendation: The issuance of specification / standardization need to be as early as possible or need to be parallel / before Contractors start work. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5590 | Process: Best Practice: Smooth deliverable for P&ID between CONTRACTORS and OWNER. | 1. Continuous discussion and clarification before official issuance for P&ID deliverables. | 1. Mutual understanding and cooperation. 2. Clear roles and responsibilities for each personnel. |  | 14854 - Action Taken: Continuous and maintained mutual understanding between OWNER and CONTRACTOR. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Engineering | 5588 | Process: FEL Stage: Surge Analysis was not in the EPCC scope. | 1. The requirement was not stipulated in the ITB. | 1. Interfacing issues as it involves total RAPID projects. |  | 14850 - Action Taken: Escalated to Petchem and UIO. 14851 - Recommendation: The requirement to be included in the ITB for future project. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6329 | Process: Late technical requirement imposed by Licensor (e.g. PWHT requirement for unit 1440) | 1. Licensor upgrade material selection due to feedback from other client. | 1. Material cost. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5744 | Process: Licensors Guarantees for front end and backend throughputs not exhaustive. | 1. After the ITB issuance EO Purification unit was deleted completely. 2. Deletion of EO Purification lead to mismatch between capacities of EO reactor and Glycol section. | 1. Additional work order to licensor. 2. Full process guarantee for 100% downstream product could not be achieved (710 KTA instead of 740 KTA MEG). |  | 15315 - Action Taken: Through addendum glycol capacity expansion from 710 KTA --> 740 KTA MEG through simulation exercise and this was made as a condition for contract award. 15316 - Action Taken: Glycol section capacity increased from 710KTA MEG --> 740 KTA MEG through simulation study by the Contractor with Licensor support. 15317 - Recommendation: Proper consideration of plant capacity based on all potential scenarios. 15318 - Recommendation: FEL 2 and FEL 3 exercise should be carried out on staggered basis to define products slate and project scope clearly at the beginning. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5743 | Process: Optimization of nozzle sizes not connected to column internal. | 1. Based on Licensor feedback Contractor optimized some of the columns nozzles not connected to column internals. 2. Contractor optimized some column nozzles not connected to internals. 3. Lacking thorough evaluation on hydraulic by contractor. | 1. Higher than normal velocities concern. Due to advanced stage of column fabrication change of nozzle sizes would have resulted in cost and schedule implications. |  | 15311 - Action Taken: Based on the information available in project specification, modified nozzle were reviewed. 15312 - Action Taken: Engaged PTAs to assess and endorsed all nozzle size changes. 15313 - Recommendation: Proper and clear design criteria shall be included in the applicable PTS for nozzle sizing. 15314 - Recommendation: Any changes to licensor PDP elements should be thoroughly reviewed and implemented after written consent. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6330 | Process: Optimization of the AOC basin in terms of sizing and destination | 1. To optimize project spec during engineering design. | 1. Space limitation. 2. Design difficulty to put all in limited space. 3. Potential project deviation. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6326 | Process: Prolong dynamic simulation study | 1. Contractor not budgeted in the proposal. 2. Outsource to 3rd party | 1. Payment milestone cannot be produced on time. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5748 | Process: SCC informed they can supply methane with acetylene 0.16%. EPC stage change for EOEG to provide PSA unit to clean acetylene from Steam Cracker methane was difficult to solve technically and commercially and disruptive to progress. | 1. SCC informed EOEG about their inability to supply methane with acetylene <10 ppm around middle of Engineering phase. 2. Lack of validation of FEED battery limit supply specification. 3. Fundamental reason for wrong spec being followed on Steam Cracker was acceptance of a cost reduction without checking the consequences fully. Late identification occurred because of interface barriers due to the need to protect intellectual property of SCC Licensor and EOEG Licensor. 4. Discrepancy discovered at advance stage of the project. | 1. SCC methane supply with high acetylene not meeting EOEG Licensor spec requirement as acetylene is catalyst poison. This possibly occurred due to miscommunication during FEED stage and resulted in change order. 2. Change order with large cost impact. 3. Increase in engineering and procurement activities and resources to execute the change. |  | 15327 - Action Taken: PSA unit to be installed for purify of methane from acetylene to less than 10 ppm and the following actions were taken: • Technologies selection.• Change order issuance.• Extend PMT and EPCC resources. 15328 - Recommendation: Proper communication during FEED and core team to monitor raw material specification requirements of all the plants in the complex. 15329 - Recommendation: For future complex projects with such barriers, it’s recommended to appoint a small process interface coordination team under the central process manger to supervise all interconnecting streams for the entire complex. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5745 | Process: Tank truck loading facility to be modified to include Butadiene loading. | 1. Discrepancy in conceptual design was noticed during hazop session. 2. Design basis was developed with only limited information from butadiene customer. 3. OWNER lack of experience in managing butadiene. | 1. Lack of clarity on the conceptual design of butadiene loading prepared during FEED. 2. Delay in design freeze due to lack of crucial design information (tanker and customer plant operation). |  | 15319 - Action Taken: Hazop discontinued and Conceptual design revisited based on the feedback from butadiene handlers / transporters. 15320 - Recommendation: FEED for such loading facilities shall be developed based on clear and authentic information from all the concerned parties. 15321 - Recommendation: Early intervention by UPT, O&M and commercial team in freezing the design for customer requirement. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Procurement | 6194 | Procurement execution not as per schedule. | 1. No dedicated procurement personnel / coordinator at EPCC office | 1. Delay in procurement communication and finalization. 2. Project execution report not hollistic causing difficulty in procurement progress tracking. |  | 16232 - Recommendation: Ensure Procurement team is in the same location and part of the Project team. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2066 | Procurement for adequate numbers and suitable plant/ machinery as per schedule | -not all machinery suppliers keeping sizable stocks -compliance with safety requirement | Delay in schedule and cost overrun | -Detail plan for plant/machinery mobilisation considering the availibility of work front and prioritize activity according to project milestone. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Procurement | 5221 | Procurement for category items through Global Frame Agreement (GFA) or Price Agreement (PA) under management of PPMD and PSI | 1. GFA / PA Terms and Condition are partially shared with CONTRACTOR. 2. No direct communication with OEM and CONTRACTOR, PPMD and PSI are handling queries for all EPCC CONTRACTORS. 3. PSI was removed in the middle of CONTRACT execution. | 1. CONTRACTOR’s procurement cycle is extended to add additional time for clarification of difference CONTRACTORs T&C and GFA & PA T&C. 2. Lack of communication and delay in receiving response between PPMD/PSI and CONTRACTOR in terms of technical and commercial clarification. 3. PO novation from PSI to OEM, extra time added to CONTRACTOR to negotiate T&C with OEM. |  | 14295 - Direct Purchase between OEM and CONTRACTOR for Category items. 14296 - Shared GFA and PA Terms and Conditions with CONTRACTOR. 14297 - Frequent meeting with PSI to expedite the process (conference call). 14298 - To appoint dedicated person to manage one EPCC contractor assisted by sufficient manpower. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Procurement | 5613 | Procurement progress not in accordance to schedule. | 1. Duration between the issuance of TBE and PO was rather too short i.e. 1 month while the review of TBE had taken place more than 1 month. 2. TBE issued later than schedule since Contractor required more time to review the bidders technical proposal and conduct clarification with bidders. | 1. Certain PO cannot be issued according to schedule. 2. OWNER have limited time to review the documents e.g. Award Recommendation, Technical Bid Evaluation. |  | 14906 - Action Taken: Alert / highlight to Contractor and engineering discipline on weekly basis on the upcoming TBE due to be finalized. 14907 - Action Taken: Alert / highlight to Contractor on the upcoming TBE to be issued. 14908 - Recommendation: Issuance of inquiry to take into consideration the duration to review the documents. 14909 - Recommendation: Procurement Status Report to indicate the TBE completion date also instead of issuance date only. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2115 | Project Documentation Procedure does not specify clearly the requirement of Class Z and X documents. | - contractor unfamilliar with the requirement | - Certain issue closure had delayed by the lack of understanding to respond to different class of document. | -Requirement on the Class Z and X specification has been standardize and defined for all SD packages | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5436 | Project Documents Review by PMC -To implement standard flow chart of document distribution to all discipline engineer to review the VDR / TDR by creating document distribution traceability by D.C (Document controller). | 1. Delay in schedule and cost overrun | 1. Delay in schedule and cost overrun |  | 14534 - Action Taken: Detail plan for plant/machinery / Civil Work / Electrical / Instrumentation mobilization considering the availability of work front and prioritize activity according to project milestone. 14535 - Recommendation: To implement standard flow chart of document distribution to all discipline engineer to review the VDR / TDR by creating document distribution traceability by D.C (Document controller). | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5437 | Project Execution (All Discipline)-To implement standard work practice / work sequence in constructing the project to avoid any rework and any repair work at site due to in sequencing of the activity as required. | 1. Create interfacing issues for work front for others discipline. | 1. Delay in schedule 2. Potential cost overrun. |  | 14536 - Action Taken: To follow work schedule and work sequence as per plan develop by the planner assigned. 14537 - Recommendation: To implement standard work practice / work sequence in constructing the project to avoid any rework and any repair work at site due to in sequencing of the activity as required. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Project Management | 6363 | Project execution not as per approved base line schedule | 1. Late PO issuance. 2. Lack of manpower resources. 3. Slow decision making. | 1. Schedule impact. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5847 | Project Grid Line was not established. | 1. FEED drawings was not reviewed properly. | 1. The plot plant is referenced according to local / structural gridline. |  | 15112 - Recommendation: FEED drawings to be reviewed and approved properly i.e. PIR, LDR or audit | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | HSSE | 5881 | Project key personnel (non-Malaysian) are unable to enter project site due to unavailability of VISA and CIDB card | 1. 1. Due to unavailability of working visa and CIDB card. 2. Lack of manpower planning from the contractor | 1. Sufficient supervision of work activity is jeopardized. |  | 15168 - Recommendation: Early planning on application of working permit e.g. after award. HR or Admin Dept. shall play effective role. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Project Management | 6047 | Project management framework based on water industry standard rather than PTS. | 1. Original is a state project and then take over by PETRONAS. 2. Fast track project and framework not to use PTS. | 1. Non-compliance to PTS. 2. Deem interference by management. |  | 15618 - Action Taken: Complied with PTS as much as possible. 15619 - Action Taken: Exemption for PTS. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5438 | Project Materials -To establish / freeze the material project specification / Datasheets for each discipline to avoid repurchasing of materials required and to meet the materials compliance as per project specification. | 1. Delay in schedule | 1. Cost impact to the project & cost overrun. |  | 14538 - Recommendation: During Engineering Stages all the related documents (Project Specification/ Datasheets) to be established before project Execution at site. 14539 - Recommendation: To establish / freeze the material project specification / Datasheets for each discipline to avoid repurchasing of materials required and to meet the materials compliance as per project specification. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Undefined | 6000 | Project progress was not going as planned. | 1. Clear authority/project driver to take charge and ensure work executed as planned especially at site was not effective from Contractors organization. | 1. Lack of commitment on Contractors side to work towards achieving what has been planned. Target kept shifting. |  | 15841 - Action Taken: PMC took charge and dealt directly with sub-contractors and vendor to push for work progress and material deliveries. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Planning | 5284 | Project Schedule did not consider the local weather factor | 1. EPCC Contractor overlooked in including the weather factor during schedule development | 1. Inaccurate project planning and scheduling resulting in unreasonable completion dates and productivity. 2. Causing delay to activities planned. |  | 14402 - Action Taken: To utilize local weather historical data and model it into the schedule during its development. 14403 - Action Taken: Consider lower productivity during monsoon season. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Project Management | 6049 | Project schedule is more of reporting than controls to avoid delays. | 1. Too much focus on reporting on progress rather than on critical activities that affect the project. | 1. Delaying in certain sector of the project, e.g. intake. |  | 15621 - Action Taken: To review critical activities on regular basis. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Project Management | 6305 | Project Schedule is unclear as there is no critical paths | 1. Junior planner unable to provide the baseline scheudle | 1. Difficult to proof the EOT 2. Schedule delay |  | 16472 - Action Taken: Mobilized Senior Planner 16473 - Recommendation: To appoint experienced schedule planner. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Project Management | 5992 | Project schedule was construction bias. | 1. Planners were construction biased. 2. No planner during engineering phase. 3. Commissioning Planner was on part time basis. | 1. Insufficient planning for activities others than construction. |  | 15827 - Action Taken: Incomplete schedule for Engineering 15828 - Action Taken: Ad hoc planning for commissioning stages 15829 - Recommendation: Contractor to have planners who will track all phases of works | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5920 | Project Specification on Management of Change not followed during implementation of HAZOP actions | 1. EPCC Contractor did not agree with the use of TEQ to obtain Owners approval for changes on design for closure of HAZOP action items due to the fact that the alternatives they proposed had been discussed during HAZOP close out session with Owner/Project team. | 1. For closure of HAZOP action items, there were no TEQ submitted to officially record justification and owners approval on design change for alternatives to HAZOP recommendations as proposed by the EPCC Contractor. |  | 15689 - Action Taken: HAZOP Close Out report individual action worksheet was used to document all justification for HAZOP action items which EPCC Contractor had proposed alternatives to the recommendations 15690 - Action Taken: HAZOP close out discussion notes were attached in the Close Out report. 15691 - Action Taken: EPCC Contractor responses for each HAZOP action item was reviewed thoroughly and implementation was verified. Worksheet then signed off by the Project Technical Authority. 15692 - Recommendation: Insist EPCC Contractor to obtain Owners approval for the design change via submission of TEQ. 15693 - Recommendation: Any design change shall be strictly controlled and documented in accordance of Project Specification on Management of Change. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5908 | Project Sub-Vendor List for Package Supplies. Issue for Inquiry Material Requisitions for Packages have been issued without the Project Sub-Vendor List (since missing). |  |  |  | 15212 - Suggestion for Improvement: Project Sub-Vendor List shall be prepared by Procurement and attached to all Issued for Inquiry Material Requisitions for Packages. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Document Management | 5520 | Project team spend unnecessary time to prepare administrative function | 1. No dedicated Document Controller for engineering documentation purposes 2. No administrative personnel for non-critical documents | 1. Poor quality of some project deliverables 2. Late submission of some project documents |  | 14675 - Recommendation: To hire dedicated Engineering Document Controller 14676 - Recommendation: To hire Interns for non-critical administrative function | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5458 | Prolong delayed RAPID P22 Refinery Tank Farm Fire Protection 3D Model | 1. Implementation of the FSDP requirement only after at approximately 80% of P22 engineering progress. 2. Minimum support / shortage of resources e.g. information, key personnel, expert modeler. 3. No HSE Engineer involvement in HSE 3D model review throughout RAPID P22 Residual Engineering | 1. No / less continuity in demonstrating and confirming relevant Risk Assessment, Active and Passive Fire Protection and Emergency Response implemented and associated with the design of RAPID P22 2. Prolong delay in finalizing primary input for RAPID P22 HSE 3D Model Review completion subsequently outstanding issuance of critical EPCC Contractual Deliverables e.g. HSE P&IDs, ISOs, UG / AG Fire Protection & Personnel Protection layout, MTO |  | 14572 - Action Taken: Assignment Fire Safety PTA at PL home office in finalizing Legal & HSE Contractual Obligations 14573 - Action Taken: Focused execution of 3D Model for HSE post FSDP implementation 14574 - Action Taken: Developed 3D Modeler Self-Assessment Checklist to assure each unit of relevant fire protection are assessed against engineering specification 14575 - Action Taken: Buddy concept between UPT-22 Designer (role as Coach) and PL Modeler in addition of relocation of PL Modeler workstation inside IPMT office | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Procurement | 5217 | Prolonged custom clearance process for fabricated steel structure materials | 1. Lack of awareness on CIDB new requirements from Certificate of Approval (COA) 2. Lack of direct communication & clear direction. | 1. Delay in schedule and cost overrun |  | 14286 - Engaged and work closely with PRPC permitting team, CIDB & SIRIM for guidance to resolve the incoming immediate shipments. 14287 - Engaged and learn from PCP teams experience in dealing with CIDB COA matters. 14288 - For shipments already under sailing, application for exemption of Full Type Test Report (FTTR) was submitted and approved by CIDB. 14289 - For materials still undergoing manufacturing process, normal COA approval process via FTTR will be carried out. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | HSSE | 5882 | Proper HSE documentation and tagging e.g. form, inspection tag, sticker and etc. not available in the beginning of project | 1. Unavailability of administrative resources and support to EPCC site personnel during initial stage e.g. IT, printing and etc. | 1. Audit findings and monitoring for compliance is ineffective. |  | 15169 - Recommendation: Effective management on small value of procurement items. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5970 | PSV setting at chemical pump not as per P&ID | 1. LLWT adjusted the value at site to cater with pump stroke | 1. Impact to process since the set pressure was given by process engineer. |  | 15800 - Action Taken: Make-up P&ID as well as got approval from process engineer | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5210 | PTS and project specification different understanding and interpretation | 1. EPCC / Vendor not familiar with PETRONAS standard. | 1. VO 2. Delay in schedule |  | 14271 - EPCC / PMC Owner to bring forward any queries and to be resolved quickly. 14272 - Any deviation to PTS & Project specs is properly recorded. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5475 | Public Address / General Alarm (PAGA) Zoning Definition | 1. There is no PAGA Zoning Definition. | 1. Change order resulting in cost impact. |  | 14597 - Recommendation: PAGA Zoning shall be defined clearly in the FEED document. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5213 | Pump Seals Refilling: Refilling for Plan 53B - The preferred refilling method was centralized top-up. However, different Contractors have provided different options. | 1. PTS is open to interpretation regarding the refilling. 2. Contractors may take different approach based on interpretation | 1. Inconsistent refill methods across the refinery. 2. Possible change order or VO if we were to impose |  | 14278 - Recommendation: To clearly specify which top-up method is preferred 14279 - Action Taken: Core team implemented the preferred method after getting input from all packages. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5984 | Punch list category changed/closed without the consent of initiator. There are few findings where PL closed without corrective action at site | 1. Schedule driven 2. Initiator not available to verify | 1. Defect raised not properly closed |  | 15814 - Action Taken: Reminder to LLWT and PMC were done by LKC. Improved | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Procurement | 5527 | Purchase of Engineering Software i.e. PHAST Risk was rejected by PRPC Project Services | 1. Contract issue between PMC and PRPC | 1. Delay in purchased of the software 2. Possible delay in finalisation of P30 layout. |  | 14691 - Action Taken: Spoke to the software vendor to get temporary license 14692 - Action Taken: Approval from PMC to purchase the software though not chargeable to PRPC | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Quality | 5415 | QA / QC program at fabrication shop for vendor equipment not properly managed. | 1. Focal point for quality not available. 2. Earlier arrangement of Third Party Inspection (TPI) being managed by directorate team without the proper notification to the UPT. 3. Over reliance on TPI. | 1. Quality Performance Indicators not establish for fabrication shop. |  | 14486 - Action Taken: PMC established SQS (under quality central directorate) as the centralized body to govern quality. 14487 - Action Taken: UPT direct involvement via focal point to ensure compliance to project specifications and proper review are being done. 14488 - Recommendation: Standardize a minimum ITP for overall RAPID. Any additional EPCC requirements will supplement the minimum ITP. 14489 - Recommendation: Early appointment of quality focal point in UPT. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Quality | 6275 | QAQC KPI target by CD shall be established at early stage of project | 1. Late establishment of QAQC SC. 2. Additional requirement by RAPID QAQC mgmt. | 1. Rework on the QAQC KPI measurements. 2. Additional monitoring scope. |  | 16407 - Action Taken: Realignment of KPI requirement between CD and EPCC. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Quality | 6009 | QAQC process during construction not properly done. For example construction has punch list which has been carried over into commissioning phase, RFSU | 1. Schedule driven | 1. Rework |  | 15857 - Action Taken: Closed all punch list prior to commissioning | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5057 | QAQC: Confusion during instrument underground cable inspection at duct bank and trenches. | 1. Last minutes engineering changes to cable schedule. | 1. Nearly 90% of underground instrument cable drawing need red line mark-up. |  | 14059 - Action Taken: To include red line mark up and as built drawing at punch list. 14060 - Recommendation: Strengthen engineering design change management | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5033 | QAQC: Field welds not identified in ISO drawings | 1. Engineering constructability study not included during design stage | 1. Massive site rework to compensate the changes and out of dimensions |  | 13999 - Action Taken: Rework 14000 - Recommendation: To consider constructability identify field welds during design stage. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5062 | QAQC: Gap in document issuance with correct class.eg. Class Z assigned for Class O document | 1. Lack of understanding on the document management process 2. Lack of document control enforcement | 1. Poor document control 2. Use of wrong document revision |  | 14070 - Action Taken: Conducted clarification and training on document control 14071 - Recommendation: To have continuous quality document assurance at early stage of the project | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5063 | QAQC: Gap in document status with correct revision number e.g. Revision 0A marked as issued for execution e.g. Revision 0A not up rev to rev 1 | 1. Lack of understanding on the document management process 2. Lack of document control enforcement | 1. Poor document control 2. Use of wrong document revision |  | 14072 - Action Taken: Conducted clarification and training on document control 14073 - Recommendation: To have continuous quality document assurance at early stage of the project | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5027 | QAQC: Incomprehensive analysis of input, identification of root causes and execution of output/corrective action/mitigation | 1. Lack of technical analysis competency | 1. Poor mitigation of root cause |  | 13988 - Action Taken: Guidance and training 13989 - Recommendation: To consider noncompliance link to payment process. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5036 | QAQC: Incomprehensive pre-inspection meeting (PIM). PTS and project specifications not discussed and addressed, evident in PIM MOM | 1. Pre-Inspection Meeting (PIM) conducted in accordance to template MOM which is not project specific, not incorporating PTS, Project Specification requirements | 1. Significant numbers of non-compliances in PTS, project specifications and procedures |  | 14004 - Action Taken: To revise PIM MOM template to be project specific inclusive of section for project requirements 14005 - Recommendation: Have minimum PIM i.e. PTS as requirement. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5065 | QAQC: Inconsistent submission of Comment Response Sheet (CRS) | 1. Lack of understanding on the document management process 2. Lack of document control enforcement | 1. Poor document control 2. Use of wrong document revision |  | 14076 - Action Taken: Conducted clarification and training on document control 14077 - Recommendation: To have continuous quality document assurance at early stage of the project | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5051 | QAQC: Insufficient inspection point coverage in the inspection test plan (ITP). | 1. Lack of intervention point | 1. Poor quality control |  | 14047 - Revise ITP | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5048 | QAQC: Insufficient knowledge on project specification, PTS, and procedure requirements to carry our WORK resulting in repetitive findings non compliance | 1. Lack of knowledge, understanding of PTS, Project Specification | 1. Repetitive findings and non-compliances to PTS, Project Specification & Procedure |  | 14041 - Training with dual languages 14042 - Translation key points | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5068 | QAQC: Insufficient manpower as specified in the ITB & improper construction planning | 1. Work permit limitation for foreign worker 2. Minimum salary for local | 1. Delay in work execution progress |  | 14084 - Reschedule work patent based on existing manpower availability and prioritize work based on criticality | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5046 | QAQC: Insufficient resources during to performing inspection Documents such as unpriced PO, PTS, Project Spec not made available. Inspection tools not made available. E.g. Gauges etc | 1. Poor source inspection coordination | 1. Substandard inspection practice |  | 14038 - To provide sufficient resources required to carry out task | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5028 | QAQC: Insufficient, inconsistent and conflicting roles and responsibilities defined in separate documents | 1. Lack of coordination in document preparation, review and approval | 1. Conflicting job scope and poor limits of authority practice |  | 13990 - Action Taken: Identify and define correct roles and responsibility, streamline across separate documents 13991 - Recommendation: Early identification and define correct roles and responsibility, streamline across separate documents. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5050 | QAQC: Isometric does not identify the weld joint number for pipe to pipe support connection | 1. Not identified during design | 1. Welded joints to pressure parts could not be identified & recorded |  | 14045 - Action Taken: Enforce site identification to include support 14046 - Recommendation: To have number of piping support weld in ISO during bidding stage. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5038 | QAQC: Lack of link between procurement quality and commercial procurement strategy causing lack of vendor commitment in repair | 1. Gap in procurement commercial and quality strategy | 1. Long delay in repair and rectifications for rejected material/equipment |  | 14008 - Action Taken: Continuous and frequent reminders, weekly meetings 14009 - Recommendation: To strengthen procurement commercial strategy. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5067 | QAQC: Lack of manpower to carry out inspection & specific tasks i.e. ITR completion and improper handover by EPCC contractor. | 1. EPCC not hiring sufficient manpower to execute specific task. 2. EPCC late mobilize handover team to produce & implemented handover system according to ITB | 1. Delay in work progress 2. No clear boundary between construction & pre-commissioning stage and contributed to delay on system energization. |  | 14080 - Action Taken: EPCC hired specific manpower. 14081 - Action Taken: Mobilize handover team early. 14082 - Action Taken: Populate the system completion data during engineering stage. 14083 - Recommendation: To populate the system completion data during engineering stage. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5055 | QAQC: Late closure of Surveillance Report (SR), Nonconformance Report (NCR), Overage Shortage & Damage (OS&D), Damage Notification Disposition (DND), Audit Findings | 1. Lack of commitment and pro-activeness | 1. Delay in construction 2. Further damage due to idling material/equipment |  | 14054 - Action Taken: Continuous monitoring and motivation 14055 - Recommendation: Construction to support QA to expedite the closure of the findings 14056 - Recommendation: Strict consequence management to nonperformance vendor | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5044 | QAQC: Late issuance and short notice for Notice of Inspection (NOI), Inspection Application Notice (IAN) & Request for Inspection (RFI) | 1. Poor coordination with vendors | 1. Difficulty in coordinating attendance |  | 14034 - Action Taken: To avoid last minute request and follow look ahead plan 14035 - Recommendation: To comply with ITB requirement | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5032 | QAQC: Massive number of site modifications - piping | 1. Early shop fabrication work prior design completion | 1. 11,400 DB of rework |  | 13998 - Rework | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5035 | QAQC: Mismatch datasheet (surge protection device (SPD)) for instrument valve from actual valve during material receiving inspection. | 1. Improper reviewer during engineering stage | 1. Confusion during material receiving and installation |  | 14003 - Inform engineering team & vendor to update the datasheet | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5066 | QAQC: No process control to ensure document adequacy and approval completions | 1. Documents overdue for approval for up to 2 years | 1. Poor document control |  | 14078 - Action Taken: Consolidate and follow up approval 14079 - Recommendation: To have continuous quality document assurance at early stage of the project | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5059 | QAQC: No request for deviation of completions management system (CMS) from contractual WINPCS to SPF-PCC | 1. Late mobilization of responsible parties 2. Poor Management of change (MOC) for deviation 3. Late action of required compliance to ITB | 1. Late pre-comm & comm readiness |  | 14063 - Action Taken: Immediate decision on CMS system for use and setup 14064 - Recommendation: Strengthen project change management | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5047 | QAQC: Poor acceptance criteria for workmanship at source | 1. Inadequate inspection coverage for level 2 & 3 tag item | 1. Major rework at site |  | 14039 - Action Taken: Revise ITP 14040 - Recommendation: Comprehensive QAQC requirements for each criticality level. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5053 | QAQC: Poor control, coordination and proactive measures for material receiving inspection resulting in significance equipment installation without material receiving. | 1. Lack of interdepartmental coordination | 1. Late material receiving 2. Conflict in liability |  | 14050 - Action Taken: Continuous tracking and monitoring 14051 - Recommendation: To enhance receiving process especially for critical items affecting the critical path. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5043 | QAQC: Poor execution and coordination of site repairs and rejected materials/equipment with vendors, resulting long lead time for rectification | 1. Poor coordination between site quality and procurement quality. 2. No site procurement quality representative | 1. Long delay in repair and rectifications for rejected material/equipment |  | 14033 - Continuous and frequent reminders, weekly meetings | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5037 | QAQC: Poor practice of change management. Several vendor not advice and unaware of the change process required - Technical Queries (TEQ), Vendor Concession Request (VCR) | 1. Absence of change management procedure. 2. Change management not discussed in Pre-Inspection Meeting (PIM) | 1. Significant numbers of non-compliances in PTS, project specifications and procedures |  | 14006 - Action Taken: To revise PIM MOM template to be project specific inclusive of section for project requirements 14007 - Recommendation: Have minimum PIM i.e. PTS as requirement. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5031 | QAQC: Poor practice of the change management - Field Design Change Notification. FDCN issued upon OWNER request | 1. Noncompliance to procedure | 1. Unrecorded changes 2. Poor site coordination |  | 13996 - Action Taken: Request for FDCN issuance 13997 - Recommendation: Periodic review. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5060 | QAQC: Population of required database in Completions Management System (CMS) incomplete with little progress within after 2 years | 1. Late mobilization of responsible parties 2. Late action of required compliance to ITB | 1. Late pre-comm & comm readiness |  | 14065 - Action Taken: Immediate population of required CMS database 14066 - Recommendation: Periodic review on manpower requirement based on current backlog/forecast activity. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5030 | QAQC: Qualified quality resources as per requirements, however with lack of competency and experience | 1. Manpower selection | 1. Challenging execution of QMS |  | 13994 - Action Taken: Requires OWNER in depth involvement, continuous training and guidance 13995 - Recommendation: Pre-com and commissioning required VOC for specific skill workers. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5029 | QAQC: Quality personnel man power planning not available. Poor increase of resources for inspection activities versus project progress | 1. Manpower and resources planning specific to quality not available | 1. Poor inspection coverage |  | 13992 - Action Taken: Continuous analysis and request on man power resources required against site activities 13993 - Recommendation: Periodic review on manpower requirement based on current backlog/forecast activity. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5061 | QAQC: Requirement of duration for motor solo run. | 1. Conflict between PTS Mech (4 hours) & PTS Elec (1 hour) | 1. Cost for fuel diesel generator & schedule |  | 14067 - Action Taken: Refer to PTA for advise 14068 - Recommendation: Strengthen project change management 14069 - Recommendation: Core engineering to decide upfront project requirement | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5056 | QAQC: Rework on motor RCU cable termination | 1. Incorrect drawing for motor RCU cable termination during engineering | 1. Motor cannot be started during pre-com |  | 14057 - Action Taken: Re-wiring cable termination based on latest drawing 14058 - Recommendation: Interconnection diagram between RCU and MCC to be specified during engineering stage. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5064 | QAQC: Several approved alphabetical & alphanumerical revision not returned with numerical revision | 1. Lack of understanding on the document management process 2. Lack of document control enforcement | 1. Poor document control 2. Use of wrong document revision |  | 14074 - Action Taken: Conducted clarification and training on document control 14075 - Recommendation: To have continuous quality document assurance at early stage of the project | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5026 | QAQC: Several key document revision history outdated for up to two (2) years not incorporating latest project requirements, lessons learned and continuous improvement, indicating incomprehensive quality management review, evident in quality review MOM. | 1. Incomprehensive periodic management review | 1. Poor quality management system |  | 13987 - Revision, guidance and training | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5025 | QAQC: Several key requirements as per ISO 9001:2008ITB P1 Sec C Part II 14.0 Quality Management Requirements not established in the Project Quality Management Plan | 1. Incomprehensive ITB incorporation, periodic management review | 1. Poor quality management system |  | 13986 - Document revision, guidance and training | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5054 | QAQC: Significant gap across disciplines in information transfer, planning and execution resulting in conflict, misunderstanding and poor coordination | 1. Lack of communication 2. Poor understanding of departmental roles | 1. Poor information transfer 2. Redundancies 3. Conflicting coordination |  | 14052 - Action Taken: Ensure interdepartmental communication 14053 - Recommendation: To develop RACI at early stage for contractor. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5049 | QAQC: Substandard site Non Destructive Testing (NDT) planning and strategy. Mitigations taken are corrective, not preventive and proactive. | 1. Poor NDT forecast and look ahead | 1. High NDT backlog |  | 14043 - Action Taken: Proactive and consistent planning, forecast. 14044 - Recommendation: Process simplication for alternative method. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5052 | QAQC: System breakdown in warehouse management.- Poor incoming material control, storage, inventory and issuance/distribution - Insufficient warehouse area - Poor preservation, housekeeping - Poor space management, storage plotting and retrieval system | 1. Poor management. 2. Lack of resources | 1. Poor warehousing |  | 14048 - Action Taken: Mobilization of a warehouse manager. Increase in resources 14049 - Recommendation: To consider dedicated warehouse manager as a key person based on volume of the project. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5034 | QAQC: Unavailability of lighting loop diagram | 1. Not develop during engineering stage | 1. Difficult to perform inspection & to troubleshoot during maintenance. |  | 14001 - Action Taken: Manual trace at site and mark-up drawing 14002 - Recommendation: Propose to have lighting loop diagram | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5058 | QAQC: Untimely adequacy of key documents and process for Pre Comm & Comm execution | 1. Late mobilization of EPCC responsible parties | 1. Late pre-comm & comm readiness |  | 14061 - Action Take: Audit and identify gaps for closure 14062 - Recommendation: Periodic review on manpower requirement based on current backlog/forecast activity | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Construction | 5045 | QAQC: Vendor in house testing not performed causing failure during issued RFI for joint witness | 1. Substandard practice 2. Schedule driven | 1. High failure frequency 2. Continuous delay |  | 14036 - Action Taken: Request for in house testing performed prior issuance of RFI 14037 - Recommendation: To include in-house testing requirement in ITP prior RFI issuance including in PIM. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5854 | QRA Consultant ERM produced QRA report on 28th June 2016 with the assumption register based on information available during early EPCC from document QRA Specification RAPID-P0024-PMC-HSE-DES-0001-0002 Rev 0 dated December 2015 | 1. There was some changes in QRA assumption register e.g. there is latest wind data available and also some of ERM understanding of QRA specification was not in line with our PTA. | 1. ERM has to revise/reproduc e QRA report. They have to rerun the QRA simulation. Some delay and QRA rev 0 was only produced on 3rd September 2016 with estimated delay of 1 month. |  | 15123 - Recommendation: VC meeting need to be conducted between QRA consultant and our PTA prior to preparation of QRA report and all the assumption register is agreed by PTA 15124 - Recommendation: Proposed to establish standard assumptions for all packages in PRPC 15125 - Recommendation: To conduct Assumption Register based on the input from each discipline SMEs (to be prepared by CORE) 15126 - Recommendation: To conduct studies by single consultant for consistency and standardized assumption basis | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Engineering | 6237 | QRA shall be included as part of EPCC / expert scope | 1. Not included as part of EPCC scope. | 1. Additional scope / cost to EPCC. |  | 16352 - Action Taken: Reinclude the QRA in the EPCC scope. 16353 - Recommendation: To include QRA part of ITB. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5661 | Quality and submissions of relevant project progress reports not as per OWNER expectation. | 1. CONTRACTOR submitted their weekly report and daily report not as per agreed timeline. 2. CONTRACTOR are using lack of internet connection at site as reasons for late submission of daily report. 3. CONTRACTOR did not using OWNER’s approved reporting template. | 1. OWNER unable to analyze project performance within time. 2. Unable to identify and resolve risk / issues arise in timely manner. |  | 15039 - Action Taken: Issues and concerns has been highlighted to CONTRACTOR during weekly meeting and through emails for further improvement. 15040 - Recommendation: CONTRACTOR’s Discipline head to submit each discipline input as per agreed timeline / forecast 1 day ahead achievement to allow their project control team prepare the report and submit on time. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Procurement | 6364 | Quality issues for LLI vendor | 1. Shortage of manpower. 2. Incompetent welders. | 1. Schedule impact. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Procurement | 5117 | Quality of 3rd party vendor inspection | 1. Incompetent inspector 2. EPCC inspector too rely on OWNERs 3rd party inspectors | 1. Rework at site 2. Potential schedule delay 3. Potential cost impact 4. Potential NCR to construction |  | 14230 - Action Taken: Mandated material arrival inspection for all equipment to identify issue 14231 - Action Taken: Intervention by the OWNERs in-house quality inspector 14232 - Action Taken: Re-assessment of the 3rd party inspectors 14233 - Recommendation: To ensure competency of the 3rd party inspector at early stage | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Undefined | 5998 | Quality of progress reporting was not to expectation. | 1. Lack of input from other department/disciplines. 2. Reporting task was handled by the same person who was also doing other tasks. | 1. Project status was not reported completely. 2. Issues and concerns were not escalated to higher management. |  | 15837 - Action Taken: Highlighted during PC meetings. 15838 - Recommendation: PMC provided templates for reference. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5485 | Radiation / Dispersion Studies. | 1. Sub-Contractor is not providing study radiation / dispersion contour because it is not in their scope. | 1. Unnecessary delay in finalizing flare package, associated drawings and layout. |  | 14614 - Recommendation: To ensure the requirement is specified in Sub Contractor ITB prior issuance. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5739 | Raised Floor Height: Raised floor height discrepancy for FAR and LCR. | 1. Discrepancy on the minimum raised floor height between: • Civil standard drawing • Instrument standard drawing | 1. Late engineering changes. |  | 15302 - Action Taken: Verifying the actual height provision with the cables laid and equipment underneath, with consideration of future / spare space. 15303 - Recommendation: Specification to be updated. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Interface | 6072 | RAPID not inform PAMER on the final level of their platform level (keep changing). | 1. Final level is not finalized. 2. Lack of coordination (interface) meeting. | 1. PAMER changed the engineering design to suite RAPID. 2. Schedule delay. |  | 15660 - Action Taken: Gave provision to contractor from beginning. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5707 | RCM details is only up to main equipment. | 1. As per ITB, there was nowhere mention on level 7 or sub-equipment up to individual tag number. Therefore, only main equipment such HEX, column, compressor and pump are classified under ECA study. 2. ITB was not specific enough that leaves gap in interpretation. | 1. Specified tag numbered equipment e.g. instrument was not covered under the scope of RCM by EPCC. 2. Reworked on RCM to cover from 234 equipment to more than 7000 equipment. |  | 15227 - Action Taken: Close discussion with CONTRACTOR to persuade them to absorb the additional scope based on spirit of good relationship. 15228 - Recommendation: To be specific in ITB write up. Adding the specific requirement of equipment up to individual tag number. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5087 | RCM study output not as per PETRONAS Maintenance Management System (PMMS) requirement. Some of the scope of M-Plan establishment not cover as per ITB. | 1. Lack of understanding on PMMS requirement 2. ITB is not fully aligned with OWNERs maintenance system | 1. Additional works is required to align the RCM study outcome to M-Plan development |  | 14159 - Action Taken: Revisit of the RCM study and rectify the gap 14160 - Recommendation: To standardize the PMMS requirement accordingly in ITB | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6092 | Recovery work due to unforeseen sea bed conditions i.e. hard layer | 1. No time float allowed for any unforeseen situation i.e. discovery of hard layer | 1. Work Progress and cost |  | 15571 - Recommendation: To engage experienced Project Manager or Construction Manager or Planner 15572 - Recommendation: To appoint competent subcontractor 15573 - Recommendation: To have close monitoring and coordination work | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5261 | Re-design work on the 3D model with effected the isometric drawing up revision | 1. Late information received from vendor regards to the dimension of piping, instrument and mechanical data. 2. Overlook on the PID, instrument and project specification requirement and also lack of checker to check the drawing and document | 1. Additional Contractor man-hours and double work |  | 14362 - Action Taken: Required more designer and checker to mitigate the issue. 14363 - Action Taken: EPCC shall mobilize and expert/ experience in order to advice the technical issue without impacting the construction progress | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5269 | Re-engineering works due to several technical clarification/memo sent at later stage by Central Core Team | 1. Late clarification by Central Core Team related to several technical issues (example IMCS-CMMS link, local remote etc.) 2. Different interpretation of requirement between CONTRACTOR and Central Core Team | 1. Additional CONTRACTORs man-hours and hardware required which lead to possible Change Order from CONTRACTOR |  | 14377 - Action Taken: Engage CONTRACTOR to come out with detailed action and mitigation plan in order to meet the stated requirement (if they agreed) 14378 - Action Taken: Central Core Engineering must define this scope at earlier stage to all packages to avoid re-engineering works | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5831 | Relay Online Calibration | 1. Protection relay do not support online calibration without shutdown. | 1. RAPID-FE1-TPX-ELE-DES-0001-002. 2. Non Spared equipment shall have protective devices with online calibration technology or redundant relays to allow its test and calibration be carried out without isolation of the feeder to meet local regulatories requirements of two-year testing interval. |  | 15499 - Action Taken: As per CONTRACTOR’s process team references, non-spared equipment have been defined. 15500 - Action Taken: There is only one non-spared equipment. In case of the other single service equipment, they are allowing short time stopping for calibration or maintenance and it will not result shutdown which may affect the production. 15501 - Recommendation: Preventive Action. 15502 - Recommendation: CONTRACTOR provide fully configured withdrawable type spare relay for HV, fully equipped spare MCC for LV | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6085 | Repetitive noncompliance in dredging work i.e. Short Dumping | 1. Contractor was unable to control the subcontractors 2. Contractor worked without installing tracking equipment i.e. DDMS | 1. Warning by local authority i.e. DOE |  | 15556 - Action Taken: Make sure DDMS was available 15557 - Action Taken: Make sure control room is functioning 15558 - Action Taken: Owner forced Contractor to stand down until all rectification was done 15559 - Action Taken: Owner enforced control procedure | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Project Management | 6360 | Requirement to incorporate site lessons learnt from other packages. | 1. Lessons learnt captured from site audit etc. | 1. Schedule impact. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5433 | Requirements discrepancies between RAPID project specs and PTS (e.g. Instrument Air Filter Regulator material requirement) | 1. Requirements discrepancies between RAPID project specs and PTS 2. In PTS 32.37.20.10 states SS body, in RAPID-FE1-TPX-INC-DES-0001-0006 calls for metallic alloy | 1. Items was identified as CA during Engineering Technical Assurance Audit for using metallic alloy 2. Inspection for Control Valve was delayed |  | 14526 - Action Taken: Discussion still on-going 14527 - Recommendation: Technical Bid Tabulation should be reviewed together with PTA before PO is being issued. 14528 - Recommendation: To ensure any discrepancies between reference documents are clarified and EPCC should obtain OWNER approval | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5434 | Requirements discrepancies between RAPID project specs, PTS and auditor (e.g. Instrument Impulse line thickness requirement) | 1. Requirements discrepancies between RAPID project specs, PTS and auditor 2. PTS 32.37.20.1 and RAPID RAPID-FE1-TPX-INC-STD-0001-9001 specify 1.5 mm wall thickness | 1. Item was identified as PA during Engineering Technical Assurance Audit for having 1.5 mm wall thickness vs 2.0 mm requirement |  | 14529 - Action Taken: All affected drawings are going to be updated for correct site installation 14530 - Recommendation: To ensure any discrepancies between reference documents are clarified and EPCC should obtain OWNER approval | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Award/Contract | 6063 | Requirements or conditions for issuing IA not specified in contract. | 1. COC not really specified. 2. PMT did not focus on the requirement of IA. |  |  | 15645 - Recommendation: To specify and list out conditions of IA PMT to priorities at early stage. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5678 | Re-sequencing PAYMENT MILESTONE | 1. Payments are proceeded sequentially as per contract, but the sequence of payment milestone is not practical to project. 2. Payment milestone schedule was updated based on the approved baseline schedule by OWNER. In order to maintain the schedule, updated payment milestone shall be agreed. | 1. SC Issued Change Notice #15 for Re-sequencing PAYMENT MILESTONE and OWNER confirmed it. |  | 15076 - Action Taken: If change has been occurred, have to analyze impacts for the change and share / discuss with OWNER. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5909 | Review Sessions for Main Packages with attendance of in charge Vendor. |  |  |  | 15213 - Applied Solution: HAZOP, IPF and 3D Model Review Close- out Reports have not been included in the Vendor Documentation Requirement Table of the Material Requisitions for Main Packages; 15214 - Applied Solution: P&ID review and functional analysis meeting have not been scheduled and performed with Vendors; 15215 - Applied Solution: Vendors did not attend Package 3D Model review and Alarm Rationalization with OWNER (since not in Package Vendor scope of supply). 15216 - Suggestion for Improvement: Review Sessions requirements (procedures/specificati ons, Vendor attendance, close-out reports, etc.) to be included in the Issued for Inquiry Material Requisitions for Main Packages shall be defined at the early proeject stage 15217 - Applied Solution: Delay in the closure of both Contractor and Package Vendor deliverables. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Construction | 6296 | Rework due to incorrect construction method | 1. CONTRACTOR Young Engineer Programme (Fresh Engineer) | 1. Schedule delay |  | 16456 - Action Taken: Senior Supervisor / Engineer should take the lead 16457 - Recommendation: To employ experience staff | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5246 | Rework/ repair work require at site after installation | 1. Foundation setting survey is not accurate | 1. Equipment require modification at site due to steel structure/foundation no proper handover ( anchor bolt lack protrusion, steel structure foundation rusted after install Air Fin Cooler) |  | 14340 - Action Taken: To enforce proper document and RFI on foundation by Civil and Mechanical prior to installation of equipment | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Project Management | 6053 | Risk Management Committee. | 1. Identify risks appropriately. | 1. Reduction of risks. |  | 15625 - Action Taken: Commitment of members to resolve issue. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5755 | Risk matrix and ALARP application for IPF study. | 1. Risk matric and ALARP application as referred in ITB document is obsolete, superseded by 2 revisions of PTS at Group level. 2. Risk matrix and ALARP application is not aligned, with PGTSSB facilitator proposed to use new matrix and ALARP application in line with newly issued PTS. | 1. Dispute with contractor causing delay in IPF study. |  | 15345 - Action Taken: Hybrid risk matrix and ALARP application is identified for RAPID duly accepted by EPCC contractor. 15346 - Recommendation: Risk matrix and ALARP application to be updated and included as part of ITB document or Job Bulletin for EPCC execution. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5633 | Risk mitigation actions closure are not properly closed based on the real project status. | 1. CONTRACTOR update the status without confirmation. 2. CONTRACTOR missed the action due date. 3. Lack of experience of CONTRACTOR focal person to manage their Risk Register. | 1. Wrong reporting on the information update to OWNER. |  | 14955 - Action Taken: Regular discussion and meeting with CONTRACTOR. 14956 - Recommendation: CONTRACTOR shall assigned an experienced focal person to coordinate the Risk Management. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Interface | 5111 | ROAD: RFCC-2 working area access is limited by outside battery limit roads | 1. Outside battery limit roads (i.e North, East & South roads) belong to OTHER PACKAGE | 1. Delay in RFCC-2 progress |  | 14215 - Action Taken: Continuous engagement with Package 3 14216 - Recommendation: Suggest the roads between packages should be done by outside refinery packages, and shall be completed first for every package to use. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Quality | 6006 | Roof slab not waterproofed at filter & storm water gallery | 1. The provision of waterproofing not indicated on IFC | 1. Water leaks through the slab |  | 15851 - Action Taken: The roof slab to be waterproofed 15852 - Recommendation: Proper design review by EPCC | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5905 | Safety Valves Installation, Flare headers and Sub headers In standard Basell design, continuous slope on discharge lines of safety valves is not required. |  |  |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Engineering | 5528 | Same FEED team were used to work on other FEED package (e.g. P31) which was put on hold after 2 months | 1. No clear management direction | 1. Impact on common utilities shared by both P30 & P31. 2. Sharing of FEED resources. |  | 14693 - Action Taken: Decision was made to hold P31 by management. 14694 - Action Taken: P30 deliverables and ITB revised to capture the exclusion P31. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5758 | Schedule disparity / mismatch between different packages for common integrated contract (i.e. MAC and TI). | 1. SD-4 schedule is well ahead of Petchem due to late EPCC award for Petchem packages. | 1. Schedule mismatch between the two Sub-Directorates. 2. Schedule amendment and extension on SD-4, and expedited deliverable schedule on Petchem EPCCs. |  | 15351 - Action Taken: Schedule alignment between SD-4 with Petchem EPCCs conducted, with Petchem EPCCs requiring to submit engineering input earlier as to match SD-4 engineering freeze dates. 15352 - Recommendation: Interfacing EPCM contracts to include schedule amendment provision to match interfacing EPCC award contract dates as to allow more flexible and reasonable target date for both parties. 15353 - Recommendation: Proper assessment to align design interface schedule. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Project Management | 5516 | Scope is not defined clearly by FEED contractor | 1. Lack of details in FEED deliverables | 1. Bidder is not clear or may get confuse on the scope which will impact cost estimation |  | 14668 - Action taken: Clarification with bidders 14669 - Recommendation: PMT to review and verify FEED deliverable list prior to start FEED. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Undefined | 5679 | Scope Split of Sleepers for pipings / trays from LLDPE to OSB | 1. Since the location of OSB is outside of process ISBL as per the contract, the work scope is OUI between SC process area and OSB area. 2. SC requested to OUI JV for sleepers between LLDPE and OSB (OSBL of SC’s scope) during the meeting and via IMT to finalize. However OUI mentioned Owners decision is required. | 1. OWNER informed to SC that the responsible for sleeper is SC because all piping/cable to OSB is SCS. So, SC tried to find the way to OSB within ISBL and provided. |  | 15077 - Action Taken: The work scope and interface with other contractor has to be discuss and finalize in the bid stage or early stage of engineering to avoid late design change. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Interface | 5523 | Seamless communication and integration between other EPCCs via implementation of Interface Management Tool (IMT) throughout project cycle | 1. Lack of communication between EPCCs with regards to interfaces 2. Poor interfaces integration between EPCCs 3. Tendency of packages to work in silo | 1. IMT helps the project team and they used it when appropriate, in both directions, for answering queries as well as for raising questions. 2. Early identificatiuon of the ties-ins with existing units/areas in all disciplines (piping, civil, structure, instrument, electrical. |  | 14681 - Action taken: Utilization of IMT (Interface Management Tool) which is a very developed & synthetic tool that allowed the IPS contractor to have seamless communication with the other EPCC’s. 14682 - Action taken: Participation of LICENSOR in the discussion of interface with EPCC contractors and definition of strategies for next phase of the project. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6015 | Selection of instrumentation equipment on the pipes was not supported properly. | 1. Poor support on the instrument installed on PVC pipe | 1. Punch list required to add support |  | 15868 - Action Taken: Additional support require in order strengthen the SS PG on PVC pipe. 15869 - Recommendation: To include support during design | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5449 | Selection of test Vent and Drain for piping system. | 1. Contractor has followed RAPID-FE1-TPX-PIP-STD-0001-0002 Project Specification - Piping Construction Standard for the test vent and drain. As there is a conflicting requirement stipulated in two project specifications in the ITB. | 1. Contractor has followed RAPID-FE1-TPX-PIP-STD-0001-0002 Project Specification - Piping Construction Standard for the test vent and drain. As there is a conflicting requirement stipulated in two project specifications in the ITB. |  | 14555 - Action Taken: All pipes with drain and vent already revised accordingly to suit this requirement.(Isometric drawings and MTO) 14556 - Recommendation: Threaded cap should only be used for Non-hazardous Utility system. 14557 - Recommendation: For Process and any Hazardous lines, flange with blind flange or butt welded cap is to be used. 14558 - Recommendation: Design engineer shall raise up TEQ to OWNER during design stage to avoid confusion on vent / drain selection. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Undefined | 6001 | Setting-up of Project WBS and progress measurement can be further improved. | 1. Contractor was not familiar with the industry project control standards. | 1. Rework on execution Schedule required during construction. |  | 15842 - Action Taken: PMC provided templates for reference. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Engineering | 6043 | Several engineering or design improvements were required or noted during the construction stage | 1. standard design approach was taken during design stage, 2. Inadequate review including cross-discipline (including operation team), site verification, and incorporation of previous lesson-learnt. | 1. Change orders (additional cost), 2. Delay to timely closure of the project because most of the improvements were noted / undertaken late in the project stage, 3. Some difficulties to operation team. |  | 15606 - Action Taken: To conduct proper design review at the beginning of the project, with the involvement of operation, safety and security teams 15607 - Action Taken: To conduct proper site verification. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5095 | Several VCR raised from equipment package due to not meeting project specification (I&C requirements) i.e. thermowell, pressure gage specification, level indicator glass type | 1. Lack of communication 2. Late submission of specification by package vendor | 1. Most changes cant be make because the fabrication works / orders have been completed 2. Potential schedule delay and cost impact |  | 14177 - Action Taken: Continuous follow up between equipment and I&C team from Contractor side on reviewing vendor documentation 14178 - Recommendation: To clearly clarify / inform vendors project engineer of I&C deliverables as per project specifications. 14179 - Recommendation: Early identification of PDR can be reviewed and approved. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5222 | Sharing of manpower with other discipline | 1. Sub-Contractor tend to share the steel structure, piping and fireproofing manpower for other disciplines | 1. Not enough manpower for steel structure and fireproofing as need to wait for other discipline to complete their job first. 2. Not having skilled worker for that particular job |  | 14299 - Action Taken: Highlight to management to have specific manpower for each discipline. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Procurement | 6231 | Short notice given to Owner for some equipment delivery to site | 1. Change in procurement delivery plan. 2. Lack of communication between Procurement team and site construction team. 3. Logistic coordinator based location away from site. | 1. Late RCP approval. 2. Late Custom clearance. |  | 16343 - Action Taken: Closely monitor on equipment delivery via weekly meeting. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5262 | Shortage of material required at site | 1. Late information of MTO provided to procurement and material control 2. Changes on PID and vendor data 3. Re-design of the piping routing due to not as per PID and other requirement | 1. Will affect the construction progress and construction sequent activities |  | 14364 - Action Taken: Margin of the material purchase shall be increases 14365 - Action Taken: All the basis information such as PID and vendor shall be confirm at earlier stage 14366 - Action Taken: Borrow or purchase from other EPCC | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Procurement | 6235 | Shortage of materials for Fire Water line by subcontractor | 1. Late received of confirmation for interface point by EPCC. | 1. Schedule impact. |  | 16349 - Action Taken: Expedited closely the suppliers. 16350 - Action Taken: Interface point confirmation / coordination by EPCC. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5238 | Site readiness | 1. Pipe rack handover 2. Scaffolding progress 3. Access issues 4. Pipe erection issues 5. Equipment handover | 1. Delay the construction |  | 14325 - Action Taken: Introduce partial handover 14326 - Action Taken: Increase scaffolding material and manpower 14327 - Action Taken: Designated temporary access 14328 - Action Taken: Work out of sequence for pipe erection | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Procurement | 5525 | Slow decision making during finance evaluation period | 1. Limited bidders 2. No clear guideline to disqualify the bidder 3. Language barrier 4. Bidders not clear on language requirement in the RFP | 1. Delay in finalising LLI procurement items. 2. Impact schedule delivery |  | 14686 - To leverage on the EPC business / secure online bidding portal. 14687 - To utilise online bidding tool. 14688 - To brief FEED contractor on OWNER requirements at the early stage of project | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Construction | 6294 | Slow in piling material delivery | 1. Lack of material 2. Delayed order 3. Never take into account the casting and cooling period | 1. Schedule delay |  | 16452 - Action Taken: Prepared material list for monitoring purposes 16453 - Recommendation: Material delivery should follow schedule | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Quality | 6318 | Slow Material Submission | 1. CONTRACTOR may misunderstood the EPC requirement, as Contractor is pending OWNER approval | 1. Delay in material delivery |  | 16498 - Action Taken: Arranged a workshop explaining the EPCC concept 16499 - Recommendation: OWNER need to ensure Contractor understand the EPCC concept during tendering process. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6078 | Slow mobilization of critical equipment i.e. dredger and hopper barge | 1. Contractor does not own any equipment, 2. Back up plan was fully dependent on third party equipment supply. | 1. Delay in work progress |  | 15545 - Recommendation: To prequalify the suitable and experienced contractor | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Construction | 6259 | Slow piping progress | 1. Poor coordination between EPCC & subcontractor. 2. Subcontractor not familiar with EPCC CMS database. | 1. Schedule impact. |  | 16383 - Action Taken: Close monitoring and tracking on daily basis. 16384 - Action Taken: Additional manpower by EPCC. 16385 - Action Taken: Additional upfront planning as per construction sequence. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Construction | 6261 | Slow progress of E&I work | 1. Late finalization of detail engineering Late mob of E&I subcon New set of manpower | 1. Schedule impact. |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5974 | Sludge building not having lightning protection. As per IEC 62305, lightning protection shall be installed if metal thickness is less than 4mm | 1. EPCC not understand/following the project requirement/specification. | 1. No lightning protection |  | 15804 - Action Taken: Few discussions have been made with LLWT and PMC. Still pending closure | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5966 | Sludge Recirculation Pump failed because of foreign material (debris, rubbish etc.) from suction (upstream). | 1. Clarifier did not properly clean and no commissioning strainer install for first time plants running | 1. Equipment failed to running and have possibility of equipments damaged |  | 15794 - Action Taken: Fabricated commissioning strainer and install at pump suction before running the pump for first run 15795 - Recommendation: To ensure rotating equipment commissioning strainer in the part of ITB requirement | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5630 | Smooth communication and execution with OUI-JV and SD-4 regarding the area between ISBL and Geographical Limit with both parties. | 1. Demarcation of the area is already specific. The truck loading area, OSBL and waste area are located at geographical area. | 1. Demarcation of the area and SOW are clear enough to carried out by contractor (grey area). |  | 14949 - Action Taken: Face to Face meeting with SD-4 and OUI-JV to do job segregation and agreed by them. 14950 - Recommendation: To have a clear demarcation for the area of the project that ensure that only one contractor will handle the execution. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6010 | Smooth management of site inspection record and punch list record for completion management. | 1. Late setup of completion management system WINPCS | 1. Late closure of critical punch due to no proper record establish at the early stage. |  | 15858 - Action Taken: Generate WINPCS report to identify critical punch in accordance to system completion criticality 15859 - Recommendation: Early development of punch list management so that critical punch to be address and resolve at the earlier the right time. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5209 | Some engineering issue is being settle for less due to meet project schedule | 1. Technical issue found late in stage | 1. Maintenance issue during operation |  | 14270 - Alignment and understanding between SEG and PMC / Owner team (technically and working method) need to be periodically gauge to align back with target, between project management and working level. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5203 | Some issues, which were already clarified, raised again during detailed execution by EPCC. | 1. Some UPT members not aware of the same issues that were clarified during bidding. 2. Generic resolution during the clarification between EPCC bidder and evaluation team. | 1. Some scope were challenged and took time to resolve. 2. Prolong decision making. 3. Unnecessary argument. |  | 14260 - All UPT members need to be familiarized and aware of issues clarified during bidding to avoid delay in execution. 14261 - All the ITB clarification to be made available for UPT members to access. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Award/Contract | 5416 | Some ITB requirements not clear (Misunderstanding of ITB requirements). | 1. Contractors proceed with their own understanding, without raised any TEQ. Example: Overall QRA by OWNER addressed in Section C Part II 4.2. Versus Facility QRA in Section C, Part II – 1.0 SUMMARY SCOPE OF WORK Clause 1.7.2. | 1. Potential quality issue. 2. Non Acceptance of handover. |  | 14490 - Recommendation: Contract personnel to be early person present in the team to guide team on contract issues. 14491 - Recommendation: The ITB must be prepared by experienced and technical person. 14492 - Recommendation: To introduce PIR during pre-ITB. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Engineering | 5511 | Some of the deliverables issued to the FEED bidder are not required in this package | 1. Lack of validation of deliverables prior issuance to the bidder due to fast track project 2. Lack of experience | 1. Unnecessary time spend for the bidder |  | 14660 - Recommendation: To ensure validation process is in placed prior to issuance to the bidder | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5478 | Sparring Philosophy for Inert Gas System | 1. Same supplier used for inert gas, i.e. Inergen for all plants in RAPID. 2. Initially, Sparring is not required based on cost saving initiative 3. BOMBA insisted to have spare | 1. Potential schedule impact 2. Rework |  | 14601 - Recommendation: Sparring Philosophy shall be considered for Inert Gas System 14602 - Recommendation: To adhere fully with Authority / Regulatory (BOMBA) requirements | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5922 | Specific Process studies not completed at right project phase as per ITB | 1. During basic design, the contract requires EPCC Contractor to perform sludge disposal cost optimization study to evaluate and justify their selection of the final sludge treatment and disposal options. EPCC Contractor had mistakenly assumed that the sludge drying unit has to be included as part of the final sludge treatment process. | 1. The implementation of sludge dryer as part of the sludge treatment process had not been supported by any cost or economics evaluation study. |  | 15698 - Action Taken: Assist EPCC Contractor to submit the study to comply with ITB requirement. Based on the economic feasibility study and cost comparison, sludge drying was found justifiable. 15699 - Recommendation: To confirm understanding of EPCC Contractor on contents and requirement of the contract especially with regards to their deliverables. Contractor may not be familiar and misunderstood the requirements. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5236 | Spool segregation and sequence | 1. Lack of manpower 2. Insufficient crane | 1. Late spool issuance to site and cause delays in construction |  | 14323 - Action Taken: Increase manpower and crane | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Project Management | 5513 | Staff lack of focus due to overloaded works caused by multifunction tasks | 1. No dedicated SME personnel in charge for some disciplines 2. Poor assignment of manpower in Organizational Structure 3. Shortage of manpower | 1. Delay in submission of some project deliverables 2. Lack of validation/verification process in engineering documents. Only for minimum requirement. |  | 14663 - Recommendation: Proper planning in staff allocation according to project phases 14664 - Recommendation: Staff need to be onboard prior to the project initiation. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5850 | Staircase width: Minimum requirement vs. safety escape. | 1. No clear criteria on what governs the width of the staircase requirement. 2. Vague specifications subject to interpretation | 1. Cost and schedule impact. |  | 15115 - Recommendation: To update relevant PTS and project documentation to include the requirement for minimum width, escape width and rescue width. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5875 | Standardization of progress measurement used in RAPID | 1. Different approach by each EPCC Contractor 2. Magnitude of the RAPID project | 1. Under/over reporting the actual physical progress giving misinterpretation of measurement |  | 15160 - Recommendation: Standardization of progress measurement and identify gaps on various progress measurement system | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6353 | Static: Colour code in PTS is not clear for platform component | 1. PTS coating spec 30480031. | 1. Longer time to repaint. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6337 | Static: Datasheet from one of equipment late issuance by process discipline | 1. Schedule driven project concurrent process decision finlization spec. 2. Detail data pending finalization on certain process (e.g safety valve is still pending when vessil data sheet issued). | 1. Late issuance of mechanical datasheet. 2. Late issuance of technical requisition. 3. Late start for techical bid evaluation. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6355 | Static: Different description used for insulated equipment | 1. Design temperature to be used for carbon steel and low alloy steel. 2. Operating temperature to be used for stainless steel. | 1. Schedule impact. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6354 | Static: Manholes location should be near the bottom of vessel for all vertical vessels | 1. Based on licensors datasheet is different with PTS spec. | 1. Schedule impact. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Engineering | 6338 | Static: Prolong technical bid evaluation by certain equipment vendor | 1. Sub-vendor cannot meet certain technical requirement (e.g. specific model for API 610 centrifugal pump). 2. Limited number of vendor list. | 1. Schedule impact on the engineering. 2. Longer time for evaluation to be finalised. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2075 | Stringent safety requirements on machinery and equipment (oil and gas vs general construction standard) | -Unfamiliar with safety requirements | -Delay in mobilization | -PMC to provide comprehensive guidelines and checklist to Package Contractor during tender | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2085 | Strong Support from JPDC, UPENJ, PRPC and JKR to expedite Road Gazettement process by the state. | Tight schedule to allow for J52 road closure. | - Road opening to the public on time. | - Meeting with State Exco responsible for public work in the present of State Legal advisor team, State PWD team, JPDC to expedite the process of Road Gazetment. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6014 | Study for platforms and accessibility requirement for operability and maintainability use not done properly | 1. Additional Platform request by Operation and Maintenance towards the end of Project | 1. Limited access to Human and additional Platform require at the end of the project. |  | 15866 - Action Taken: Create Punch list in order to revisit the actual requirement from O&M perspective. 15867 - Recommendation: Early involvement of O&M during Model review very critical to address any design discrepancy. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | HSSE | 6055 | Subcontractor using illegal workers to work at site. | 1. No proper control / monitoring by main contractor. | 1. Potential reputation penalty / stop work. |  | 15628 - Action Taken: To have continuous monitoring on manpower at site. 15629 - Action Taken: Impose penalty to subcon. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5933 | Submission of complete Final Engineering Dossier and Manufacturer Data Book should be submitted around 1 month after delivery | 1. Lack of commitment from vendor side to compile the document as per required index. Also lack of expediting from contractor side. | 1. Final Engineering Dossier and Manufacturer Data Book has not completed for review and submission after few months of delivery of the equipment at site (happened to all rotating equipment) |  | 15721 - Action Taken: Few meeting were conducted with non-performance vendor to highlight delay of the document. Target date is given for vendor to commit. 15722 - Recommendation: Contractor should send their rep to office of all non-performance vendor to monitor and expedite the submission of the document. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Planning | 5285 | Submitted EPCC Contractor Level 4 schedule contains schedule error and bad planning (i.e.. Out of sequence activities, Long lag durations, activities without successor and etc.) | 1. EPCC Contractor lack experience in utilizing Primavera P6 for planning and scheduling for projects this size | 1. Legitimacy of the submitted schedule becomes questionable and may portray incorrect schedule dates for execution. |  | 14404 - Action Taken: iPMT set-up weekly schedule review meeting to train EPCC Contractor on the good practices and also to rectify the schedule error prior to official submission. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5215 | Substandard quality of engineering document (i.e. P&ID, Civil & Piping Drawings) | 1. Lack of quality checker from contractor prior submission to iPMT. 2. Different competency level of contractor’s engineers. 3. Frequent turnover of manpower. | 1. Many cycle of revisions and time consuming. 2. Unfamiliarity of EPCC working procedures. |  | 14282 - Put milestone payment on hold. 14283 - Continuous reminder during monthly meeting. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Project Management | 5533 | Successful focused execution for completion of FEED | 1. Full support from PMC core and OWNER. 2. Closed follow up by PMT team 3. Proactive meetings initiated with other packages. | 1. Timely submission of project deliverables 2. ITB issuance to bidders according to plan |  | 14702 - Recommendation: Proper planning in staff allocation according to project phases 14703 - Recommendation: Staff need to be onboard prior to the project initiation. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2098 | Sufficient resources for recovery plan | Good coordination between PMC and contractors i.e realistic recovery and good management support. | -Schedule recovery of progress slipages. -Project completed on time. | - PMC and Contractor had relook at their resources planning. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Construction | 6037 | Survey error by appointed licensed surveyor - error in rim survey of Seluyut impounding area, and error in profiling pipeline alignment near Bukit Pelali area. | 1. Error when setting up the Temporary benchmarks (TBM). 2. Inadequate coverage of LIDAR survey data. 3. Involve interface up to state level. | 1. Recall surveyor to plot again. 2. Additional lands had to be acquired (Plot D, Plot E, and Felda lots) when construction already started. 3. Impact construction activities and overall schedule 4. Additional project cost due to VOs (land clearing and additional earthwork) and additional land acquisition. 5. Cannot perform pump performance test and etc. 6. Seluyut reservoir could not be fully impounded in a timely manner. |  | 15591 - Action Taken: Maintain water level 18meters until problem is resolved. 15592 - Action Taken: Crisis management approach - Surveyor was directed to undertake and complete the survey quickly, and top State official (Dato SS) was approached directly for assistance. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5500 | Survey Monument | 1. Movement of bench marking points from its original coordinate/ elevation. 2. Survey monument has to be moved due to construction development. | 1. Misalignment at battery limit interface point between 2 interface contractors. |  | 14634 - Action Taken: Joint survey among all parties at site to minimize mismatching / discrepancies. 14635 - Recommendation: Location and design of survey monument shall be captured during engineering stage. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | HSSE | 5879 | TBE for portable firefighting equipment (e.g. fire extinguisher for 50 kg and 9 kg) issued for OWNER’s review not comply with the Project Specification. | 1. Contractor unable to source for vendors which can meet the Project Specification. Vendor just proposed the deviation 2. Not complying to the PDR requirement | 1. This may lead to inconsistent practice amongst RAPID Packages on the Fire Fighting equipment |  | 15165 - Recommendation: To ensure Contractor comply with the PDR and Project Specification 15166 - Recommendation: OWNER to thoroughly check the TBE and consult PMC if deviation required | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5893 | Technical resolution record for Vendors |  |  |  | 15188 - Suggestion for Improvement: Its recommended that TCMHQC prepare a uniform template used to record the technical resolution between vendor and Contractor | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Award/Contract | 5417 | Tedious subcontract requirement and approval process for 3rd Party engineering related study. | 1. Several cycle / documentation required to get approval for the subcontract of 3rd party studies, which give rooms for Contractor to claim delay from PMC / OWNER side. Example: Some confusion happen to engineering disciplines on the involvement in the prequalification activity, i.e. need to give feedback to the prequalification (which is prepared by subcontract department). | 1. Delay in awarding of contract and finalization of 3rd party. |  | 14493 - Action Taken: Expedited the approval process. 14494 - Recommendation: Requirements / work flow to be simplified if possible. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6020 | Telecom speakers are supposed to be installed according to approved telecom equipment layout as per PAGA mapping study report. | 1. The PAGA study reports were released late from the telecom integrators. Due to that, the speakers were installed as per the older revision of the equipment layouts. | 1. The telecom speakers in sludge building were installed at wrong location, as per the old revision of the layouts. |  | 15878 - Action Taken: The speakers were relocated as per the latest revision of equipment layouts. 15879 - Recommendation: The telecom equipment layout has to be finalised to jive with the PAGA study report before installation of speakers at site. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6017 | Temporary labelled for cable wrongly mark | 1. Due to that, wrong termination of cables in the wrong junction boxes occurred. | 1. Cable pulled wasn’t labeled properly with the correct cable tags. 2. Lost of time |  | 15872 - Action Taken: The cables had to be tracked back by performing continuity test for tracing 15873 - Recommendation: The cables has to be labeled accordingly while pulling is ongoing. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5771 | Tender review process is very time-consuming and inefficient. Too many technical reviewers but limited commercial reviewers. | 1. Tedious bid communication system. 2. Lengthy authorization / approval process. | 1. Time consuming in issuing responses to bidders. |  | 15383 - Recommendation: Recommend a further review of the entire process and potentially replace with a secure software / comms solution. 15384 - Recommendation: This should be done with sufficient oversight by GSCM / governance. 15385 - Recommendation: To have small but highly experienced review team. Sealed room and communication using pieces of paper is outdated and should be replaced by a secure software / comms solution. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5487 | Termination of HDPE Liners inside dyke/ bund wall | 1. No edge jointing for HDPE liner to the tank foundation | 1. Infiltration of spillage into the ground. |  | 14616 - Recommendation: Edge termination for HDPE Liners inside dyke / bund wall to be specified. 14617 - Recommendation: No gap is allowed to avoid infiltration of spillage into the ground. Normally will use E-lock, nails, etc. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5874 | The absence of Level 4 detailing for Construction activities: Level IV detailed schedules and control documents shall be prepared by CONTRACTOR and issued to OWNER within C.D + 85 days and 3 months prior start of related activities | 1. Since the start of Site activities, CONTRACTOR has not provide the number of personnel to sufficiently undertake the management of Procurement, Logistic and Construction activities. This has directly affected coordination of the activities among these various departments, which is not performed at the highest level. Due to the shortage of manpower at Site, there are anticipation on the tendencies from the CONTRACTOR to over multi-task personnel, which is a risk to the Project due to incompetence, and overloading. | 1. Cost and schedule impact. |  | 15158 - Recommendation: L4 schedule to be part of project Milestone Payment 15159 - Recommendation: To classify MDR as Class Z document | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Award/Contract | 5657 | The approval for SUBCONTRACTING was delayed. For subcontract work related to specific technical jobs such as HVAC, Insulation and E & I, technical bid evaluation assessment proposal by CONTRACTOR. | 1. Insufficient technical input provided by both CONTRACTOR and proposed bidders (Subcontractors). 2. There wasnt any planning for detailed technical submission by CONTRACTOR. | 1. For more technical works such as HVAC and E & I, the proposed technical information for the bids are insufficient that led to queries by OWNERs technical team. 2. As a result, OWNERs technical reviewer posed technical queries that were not included as part of Subcontractors submission or CONTRACTORs evaluation. These inquiries actually lengthen the evaluation process. |  | 15026 - Action Taken: Expediting both parties, CONTRACTOR/ Subcontractor for response for additional technical queries and OWNER for earlier assessment. 15027 - Recommendation: Subcontract Plan to include detailed technical query for Subcontractor to submit. 15028 - Recommendation: OWNER to advise plan to review detailed technical assessment during Pre-qualification phase of bidding. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Procurement | 5912 | The awarded Contractor is not familiar with PETRONAS Project Procurement requirements. | 1. First time with PETRONAS project 2. Issue of MVL (Master Vendor List) 3. Restriction using nominated RAPID vendor i.e. MAC, TI, etc. | 1. Contractor Procurement progress was slow due to Procurement process compliance |  | 15665 - Action Taken: OWNER/PMC granted waiver to certain Procurement process in order for Contractor to progress the work 15666 - Recommendation: Implementation of PETRONAS requirement shall be reviewed to suit the General Industry practice | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Undefined | 6310 | The baseline is not properly prepared. Many of the activities are unable to link between one and another. | 1. Junior planner unable to provide the baseline scheudle | 1. Baseline unable to be approved |  | 16483 - Action Taken: Mobilized Senior Planner 16484 - Recommendation: Seniority of planner to commensurate with the size of the project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5890 | The communication between Beijing Office Centre (BOC) and Milan Office Centre (MOC) should be strengthened. |  |  |  | 15185 - Applied Solution: Hold the monthly meeting between BOC and MOC at least. The documents related PDR/TQ/MDRshould be shared with BOC. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5494 | The design conditions provided by licensor in bid line list was retained in detailed engineering stage. Later it was identified the design conditions specified in the line list is higher than the piping material specification PMS. | 1. Point has been taken care in line. | 1. Checking of Licensor Line List during Detailed Engineering. |  | 14625 - Action Taken: While preparing the line list design conditions needs to be checked in-line with PMS. Process Check list for line list already issued. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Precommissioning/Commissioning | 5670 | The document was submitted in week lapse for review. | 1. CONTRACTOR submitted the document based on the milestone target rather waiting for completion review by the Licensor. | 1. The review of document was done in within the period, for more than 200 documents. 2. Results to shortage of time to review all document within 10 working days. |  | 15064 - Action Taken: The team planned and scheduled the review by assigned specific area for each team member. 15065 - Recommendation: Staggered submission of the document will allow the time to be reviewed in details and proper manners. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5895 | The DOSH application is mandatory to allow the delivery and the installation of the equipment. |  |  |  | 15190 - Applied Solution: It has been settled a log on the status of the DOSH application managed through also the local consultant MIE for all the supplies. 15191 - Suggestion for Improvement: It has to be assessed (if applicable) two step of the DOSH application. | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6024 | The MCB (main circuit breakers) rating for some downstream Panels are supposed to be lower than the MCB rating at PDB (power distribution board) and MCC (motor control centre) | 1. By specifications and standards, the MCB rating of the electrical power DB and MCC correspondingly has to be higher rating at upstream panel. | 1. The MCB (main circuit breakers) rating for the downstream Panels are higher than the MCB rating at PDB (power distribution board) and MCC (motor control center) |  | 15886 - Action Taken: New MCBs with the correct ratings are procured for the power distribution boards and recalibrate MCCB setting at MCC take place 15887 - Recommendation: Inter Discipline Check has to be conducted during engineering stage for MCB rating sized accordingly for between upstream and downstream panel | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5953 | The MCB (main circuit breakers) rating for the Yokogawa Panels are supposed to be lower than the MCB rating at PDB (power distribution board) | 1. Miscommunication inter discipline 2. By specifications and standards, the MCB rating of the electrical power DB has to be higher than the Instrument panels. | 1. The MCB (main circuit breakers) rating for the Yokogawa Panels are higher than the MCB rating at PDB (power distribution board) |  | 15762 - Action Taken: New MCBs with the correct ratings are procured for the power distribution boards. 15763 - Action Taken: Punch list item 15764 - Recommendation: Inter Discipline Check has to be conducted during engineering stage. The MCB rating has to be sized accordingly for the Yokogawa panels compared to the power distribution boards | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5927 | The motor Local/Remote switch shall not be provided at the switchgear. | 1. For safety reason the Local/Remote switch shall be removed to avoid confusion for local operation. | 1. Every motor is provided with Local/Remote switch at the switchgear/MCC. |  | 15710 - Action Taken: To omit the Local/Remote switch from switchgear. 15711 - Recommendation: All the RCUs at field are equipped with spring return switch for local and remote control. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5631 | The reporting by CONTRACTOR are not in good quality. | 1. CONTRACTOR submitted the report not meeting OWNER expectation. 2. Late submission of reports and missing few contents as required per ITB. | 1. Late approval by OWNER. |  | 14951 - Action Taken: Several reminder given to CONTRACTOR in the weekly meeting. 14952 - Recommendation: CONTRACTOR shall aware the reporting requirements by OWNER. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5889 | The review of vendor documents have been taken too long time during the initial stage and in some case also in the followed period. |  |  |  | 15183 - Applied Solution: To speed up the review activities and Strengthen the manpower. 15184 - Suggestion for Improvement: Suggested to update the relevant WI/PR and improving the DCG group to reduce the time to upload the Vendor deliverables | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5955 | The rotameter and needle valve to be installed at the inlet of analyser in the lab, to ensure the pressure doesn’t exceed 2 bar as specified in the specification | 1. It wasn’t captured in the GA Drawing and P&ID, but the specifications states that its required. The rotameter and needle valve is not mandatory but its recommended. | 1. The rotameter and needle valve were not installed at site. |  | 15767 - Action Taken: Rotameter and needle valves are to be procured and to be installed at the inlet of the analyzer. 15768 - Recommendation: The GA Drawing and P&ID has to reflect the requirements of the specifications. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5105 | The standard specified in PTS is not suitable for the required test. | 1. It mentions in PTS32360117, section 11.1, valve low temperature test and vacuum test shall follow ISO 15848. | 1. Potential cost impact |  | 14204 - Action Taken: ISO 15848 is the standard for valve fugitive emission. Thus, vendor finally proposed their own testing method to PMC for approval. 14205 - Recommendation: Proper standard / method shall be referred for the specific test in PTS | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5790 | There is delays to set up office and communication system such as internet system, office supplies from Contractor. | 1. Possibly due to firewall restriction at contractor office. 2. Too many steps for OWNER to establish basic work necessities (Safety system- Visitor, laptop registration, ID card and not using USB etc.) (Samsung ID card- Owner should pay deposit). 3. Samsungs procedure are not OWNER friendly. | 1. Slower internet speed. 2. Too many IT related restriction. 3. Lack of VC system (Not working for presentation)-difficult to make schedule. |  | 15434 - Action Taken: Communicated with contractor, and try to solve and explain the matter well. 15435 - Recommendation: Prepare ITB detail for the next project to save time for setting. 15436 - Recommendation: To consider to use independent hardware and network. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Award/Contract | 5886 | There were a lot of short comings in CONTRACTOR’s Engineering deliverables. This includes CONTRACTOR’s responsibility to coordinate and obtain information from OTHER CONTRACTORS within RAPID for purpose of finalizing the design. | 1. Both CONTRACTOR’s Engineering and Contract teams did not read the Contract. They assumed PETRONAS’ Contract is the same with any other contract. They therefore executed the deliverables based on their previous experiences which were mostly with Clients from the Middle East; where these Clients usually do not examine the CONTRACTOR’s work against their contracts. The CONTRACTOR’s Contract team’s ignorance about the deliverable obligations renders their Engineering team unguided in terms of compliance | 1. It impacts both schedule and cost because if the short comings were realized untimely it would affect VENDORS related deliverables; from procuring of POs to equipment manufacturing and delivery. The worse scenario is if the short comings are discovered during construction or commissioning. |  | 15175 - Recommendation: It needs CONTRACTOR management (at Project level) action to ensure compliance awareness. 15176 - Recommendation: In ITB, contractors Contract Manager shall be as a key personnel 15177 - Recommendation: Kick-off meeting | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Construction | 5248 | Thickness for grout (TOC-TOG) is more than 50 mm | 1. Excessive removal of concrete during chipping activity | 1. To achieve required TOG level, more grout and/or superior grout material is required, more cost incurred for grouting material |  | 14342 - Action Taken: Use proper concrete chipping tools to avoid excessive removal of concrete | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5837 | Time & Cost impact due to COA | 1. Additional verification is required for pipe & steel structure & plate by Sampling & lab test at country of origin for COA although vendor’s MTC is available and endorsed by Contractor. 2. For pipes, additional 52 days is spent for COA (yellow) which impacts project Cost and Schedule. | 1. Although COA is a part of contract, it’s mainly applied to MS while Rapid#6A/#11 contracted with ASTM. 2. But, CIDB announced apply for COA to ASTM in the middle of project execution. |  | 15508 - Recommendation: Preventive Action. 15509 - Recommendation: COA can be substituted with vendor’s MTC endorsed by Contractor under Contractor’s responsibility. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5216 | Time consuming to prepare CRS | No automated CRS generate (manually). | 1. Delay in return document to contractor. |  | 14284 - Contractor to prepare CRS. 14285 - To implement automatic CRS. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Engineering | 5530 | Timely issuance of ITB despite of short FEED duration | 1. Good coordination and communication with the Owner 2. Strong FEED team from similar type of project. 3. Clear definition of impact to other packages. 4. Lessons learnt from other project | 1. Timely issuance of ITB |  | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 20C2-EPCC | Package 20C2-EPCC | Undefined | 2084 | Timely resolution of underground water problem. | water seepage found at certain location within the road alignment | - Possible future potholes and road settlement. | - subsoil drain install at the identified area as a result of site coordination and visit with the engineering team. | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5780 | Timing of Electrical Safety And Operability Review (ELSOR) workshop. | 1. ELSOR workshop held too late. 2. Latest requirements not clear in specification. | 1. Impacted procurement and subsequent vendor data for electrical design. |  | 15403 - Recommendation: To be held earlier (1 month after major electrical equipment PO). | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Project Management | 6050 | To have a dedicated land expert for project. | 1. Timely resolution of land matters. 2. Factor payment to land owners. | 1. Transfer delivery of land and quicker access to site. 2. Minimal interruption to construction activity. |  | 15622 - Action Taken: To continue with such practice. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5931 | To have minimum no of punch list to be done at site. | 1. A lot of punch list has be rectified at site due to contractor approach not to delay delivery. | 1. A lot of punch list has be rectified at site. |  | 15717 - Action Taken: To minimize confusion when the equipment is delivered at site, the Inspection Release Note has to attach with all the pending punch list. 15718 - Recommendation: Contractor should identify criticality of equipment required at site and for those equipment is not critical, contractor should just rectify all the punch list at vendor workshop. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Procurement | 5219 | Too dependent on certain vendor (i.e. KNM). | 1. Limited option of Master Vendor List. 2. Vendor is overloaded. | 1. Delay in equipment delivery. |  | 14292 - Master Vendor List to be extended with more option. 14293 - To relook on the award strategy for critical equipment. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5099 | Too dependent on EPCC and Core Engineering on quality related deliverables | 1. Limited resources 2. Unclear scope and demarcation for quality review process | 1. Schedule Impact due to late feedback on quality review process. e.g. welding requirements |  | 14190 - Action Taken: PMC Mechanical has been communicating with Inspection for managing issues related to welding in terms of vendor/contractor deviation 14191 - Recommendation: Project to provide direction on this matter and ensure quality related deliverables are completed ontime e.g. responsibilities to approve welding related documents. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5401 | Too many code 4 documents pending to be revised to upgrade to code 3. | 1. Contractor doesn’t have resource to upgrade the drawing to code 3. | 1. Delay in subsequence revision of engineering drawing. |  | 14450 - Recommendation: Contractor to properly discuss with OWNER on the code 4 comments so that it can be immediately upgrade to code 3. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5295 | Too many discrepancies in process design deliverables (supported by Audit points). | 1. Engineering done by third party Mumbai office instead of KL Home Office hence poor quality / detailed technical check. 2. PEPI does not share documents such as calculations, engineering simulation tools and hydraulic at the right time. Upon specific request and very late in the project, some of the calculation was shared and most of the time issues were discovered. | 1. Engineering re-work (PSV, caustic line), SRU mass balance / nameplate capacity deficiency, amine system vs tank volume, caustic hydraulic line deficiency. 2. Potential safety and operability issue. |  | 14415 - Action Taken: PEPI should acquire all calculation sheet from MEC to ensure traceability of all calculation records for integrity check / future reference. 14416 - Action Taken: Engineering calculation should be shared to OWNER as part of the deliverable per ITB. 14417 - Action Taken: To conduct detailed technical self-checking of all documents and operability review in view of the numerous errors identified based on sample -checks. 14418 - Recommendation: The proposal of different location for Engineering between OWNER and contractor should not be agreed. 14419 - Recommendation: Alternatively OWNER should ensure contractor to provide adequate manpower. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Project Management | 5988 | Too many parties involvement in same issue | 1. Involvement of multiple parties commenting on same case at different stage of projects. 2. Relevant parties comes at different stages to discuss on the same issues. | 1. EPCC to spare additional time to resolve issues from the feedback or audits findings |  | 15817 - Action Taken: Intervention by project team on case to case basis 15818 - Recommendation: Stakeholders to discuss and strategies the common approach rather than all parties involvement at their own time. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Construction | 6038 | Too many sub-contractor in pipe laying work. | 1. Fast track project. 2. Need to recover on the initial delay. | 1. Effect quality of work. 2. Owner have to monitor closely / directly with the sub-contractors. 3. Insufficient supply of line pipe 1300mm to site. |  | 15593 - Action Taken: PMT monitor closely up to sub-contractor level. 15594 - Action Taken: All parties monitored closely via the Risk Management Committee. 15595 - Recommendation: PMT to have provision to have additional senior inspector of work and inspector of work. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Award/Contract | 5655 | Too much correspondence by CONTRACTOR. | 1. Excessive correspondence by both OWNER and CONTRACTOR. | 1. CONTRACTOR issued many formal correspondence though related to technical matters. |  | 15022 - Action Taken: CONTRACTOR is advised to refrain using formal correspondence and encourage use of meetings. 15023 - Recommendation: Regular meetings to resolve standing issues instead of letters. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5383 | Too slow progress, too many deviations at last minute, not focused (engineering done in parallel with construction / while commissioning work is also in progress). | 1. Procurement is done without considering engineering (example safeguarding valves with PST). 2. Engineering done by third party Mumbai office instead of KL Home Office. 3. Should all engineering calculation is performed in same office, immediate decision and closures of issues can be made swiftly without the need to wait for many parties from different offices. | 1. Ultimately will pressure owner to waive certain requirements and impose a schedule impact. 2. Current slow progress of commissioning phase (progress has been very slow, will be 11 month to MC but PetroPCS still not up yet, schedule and utility requirement not available etc.). 3. Potential operability and safety issue. |  | 14420 - Recommendation: To acquire sufficient resources to enable focus of all detailed deliverables. 14421 - Recommendation: Early enforcement of the PDR submission. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5784 | Took far too long from ITB Issue to LOA. | 1. Lengthy processes for bid review and obtaining management approvals. 2. Difficulty of Contractor absorbing Case 5 and Drumming Warehouse - resulted in 4 weeks extension to bid closing. | 1. Resulted in the sacrifice of project schedule for a better bargain on the EPCC Cost (shortened EPCC project schedule by 2 months). |  | 15414 - Action Taken: EPCC schedule had to be compressed. 15415 - Recommendation: Due consideration should be given to risk / potential losses if schedule is compromised or compressed too far in the course decision making. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Engineering | 6238 | Toxic Release Shelter (TRS) not included in contract | 1. Was decided to exclude during VE phase as there was no requirement based on previous QRA from RAPID. TRS is only required after QRA done by Petchem EPCC. 2. Limited information when the scope being developed. | 1. Additional scope / cost. |  | 16354 - Action Taken: Reincluded the TRS in the EPCC scope. 16355 - Recommendation: Provision / optional scope in the contract for TRS. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5853 | Two (2) sessions of HSE Design Review conducted between TCM and PETRONAS with the Licensor (LYB) | N/A | 1. Ensure the HSE design related items complied (minimum) with Licensor HSE Design criteria and also meeting the RAPID Project Specification |  | - | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Engineering | 5842 | Typical Loop discrepancies between Licensor & PETRONAS / Project Standards. | 1. EPCC Contractor fails to migrate/incorpo rate PETRONAS standards into Licensor design. 2. EPCC claimed status quo for Licensor design. Upon various checks & technical reviews, several changes are made with the consent of both party; OWNER and LICENSOR. 3. Copy & Paste habit of EPCC Contractor. | 1. Late finalization of Typical Loop design. 2. Late finalization of Project P&IDs. 3. Major man hours lost to align Licensor Design with PETRONAS standards. 4. Impact on INC progress. |  | 15101 - Recommendation: PMT to emphasize EPCC Contractor to respect and abide on OWNER requirement (those fund the project). 15102 - Recommendation: PMT to deploy complete team during FEED and ensure to meet PETRONAS/Project standards. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6088 | Unable to agree the Extension of Time (EOT) at the earlier stage of construction | 1. Unsure of the impact on late site possession 2. Focusing on project completion and not on EOT discussion | 1. Lack of commitment by contractor due to unclear and late finalization of contractual completion date |  | 15566 - Recommendation: Recommend to discuss any EOT element at the early finding | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Planning | 6271 | Unable to measure engineering completion progress | 1. No MDR for project. | 1. Actual progress not known / unverified. 2. EPCC may claim higher progress. |  | 16403 - Action Taken: Engineering progress monitored by completion of design review stages. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Project Management | 6306 | Unable to troubleshoot ICT issues | 1. Lack of experience, as the re is no dedicated ICT engineer from OWNER/PMC and CONTRACTOR | 1. Schedule delay |  | 16474 - Action Taken: Have to seek support from vendor. 16475 - Recommendation: This is a specialist work, a specialist should be assigned to the project. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | HSSE | 6315 | Unable to understand oil and gas safety terminology | 1. Misunderstanding i.e. JHA | 1. Hinder construction work |  | 16492 - Action Taken: Training provided 16493 - Recommendation: To have an experience HSE Manager | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5550 | Unavailability of details and plan drawing reference number for the earth plug in the foundation layout drawing. | 1. CONTRACTOR did not include reference drawing number for earth plug in foundation layout. | 1. Construction team was not aware of the locations for earth plug locations. |  | 14761 - Action Taken: Requested CONTRACTOR to include reference drawing number for earth plug in foundation layout. 14762 - Recommendation: To ensure all electrical requirement to be spell out in Civil drawing and foundation layout should be reviewed by Civil and Electrical team. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Precommissioning/Commissioning | 5967 | Unavailability of EPCC Instrument & Process Engineer during Commissioning activity. | 1. Delay in commissioning activity. | 1. Delay in start-up activity. |  | 15796 - Recommendation: Project team have to aggressively emphasize EPCC to follow & comply project execution procedures & requirements. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Undefined | 5997 | Unavailability of key Project Control personnel at site on fulltime basis, i.e. PC Manager | 1. Contractors PCM was also involved on other projects. | 1. PCM not available fulltime at site to drive project control tasks, coordinate between all disciplines and be accountable for any shortfall. PCM was only attending to monthly meetings. |  | 15835 - Action Taken: Highlighted deficiency in Sponsors meeting. 15836 - Recommendation: PMC took charge and dealt directly with sub-contractors and vendor to push for work progress and material deliveries. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Procurement | 5116 | Unavailability of the As-built drawing of Tjg Setapa berthing facilities | 1. Integration amongst OSM team and the projects | 1. Delay in unloading of the material (i.e. CO Boiler) |  | 14227 - Action Taken: Intervention by the Project Director of PRPC 14228 - Recommendation: To strengthen the communication and integration between OSM team (in charge with the MOLF) and project team 14229 - Recommendation: To do site visit and validate the drawing prior to any finalization of the ship and unloading activities | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Project Management | 6244 | Uncertain project cost (DEIA, SIA, EMP, Shared facilities, MOLF rate, accommodation rate etc) during early stage of project | 1. Cost assignment, cost distribution not timely available by RAPID. | 1. Additional cost. |  | 16363 - Action Taken: Operational cost will be pass through to customer. 16364 - Action Taken: Project cost will be absorbed in existing tariff. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Quality | 6279 | Unclear construction transition to commissioning phase. | 1. No turn over system by EPCC. | 1. Delay on PSSR. |  | 16412 - Action Taken: Realignment with commissioning team and track the completion of pre-comm activities. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5471 | Unclear definition of AOC Basin Size. | 1. Relevant drawing is not available. | 1. Potential overflow when heavy rain. |  | 14592 - Recommendation: Underground pipe volume, which is water filled system shall be considered. Basin size needs to be designed to accommodate first flush water from the paved area + the volume in the pipe. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | HSSE | 6054 | Unclear HSSE requirements in the contract. | 1. Lack of experience and knowledge preparing the HSSE contract requirements. | 1. Delay and potential cost impact. 2. HSE incidents. |  | 15626 - Action Taken: To appoint expertise to prepare the contract document. 15627 - Action Taken: To crosscheck with the requirements in relevant Acts, Regulations and Authority. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5200 | Unclear ITB scope for Contractor. | 1. Some scope of works in ITB are too generic for Contractor: for e.g. Contractor shall conduct maintainability and operability review, and submit report to Owner; Contractor to update FEED QRA etc; Late sharing of procedure for Transient Analysis to be done by Contractor. | 1. Difficulty to impose specific and standardized deliverables across different EPCCs. |  | 14254 - To provide specific deliverables for all scope of works. 14255 - To have early engagement with contractors to address on the generic scope. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5435 | Unclear material requirement for fireproofing of On-Off Valve | 1. PTS 80.47.10.30 specifies the requirement for equipment to remain operable in 15 mins. It does not specify the type of material to be used | 1. Item was identified as CA during Engineering Technical Assurance Audit for using Fire Resistant jacket |  | 14531 - Action Taken: Discussion still on-going 14532 - Recommendation: Project Spec should clearly state the material requirement 14533 - Recommendation: Technical Bid Tabulation should be reviewed together with PTA before PO is being issued | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Project Management | 5636 | Unclear scope in some section in ITB. | 1. Changes due to cost optimization for RAPID project. | 1. Potential change order. 2. Unnecessary argument and confrontation with CONTRACTOR. |  | 14961 - Action Taken: Took effort to explain CONTRACTOR on the scope. 14962 - Recommendation: Scope should be clearly define in the ITB. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Project Management | 5789 | Unclear Scope of Work definition for additional / changed Work. | 1. No FEED level information available to solicit change proposal e.g.: Additional TTLR and PSA work were introduced as part of P11s scope of work in the middle of the project. However, the SOW for both were not clearly defined when change proposals were solicited from contractor. | 1. As a result, the change proposals had to be recycled numerous times due to technical clarifications and this caused delays in approving and implementing the changes in a timely manner and obtaining the optimum price with minimum / reasonable contingency. 2. Schedule re-adjustment resultant of this changes could only incorporated into the baseline schedule at a later stage hence, distorting the interim progress measurement namely for engineering and procurement. 3. Delay approving. |  | 15431 - Action Taken: Technical clarifications were issued for better definition in the course of evaluating change proposals submitted by contractor. 15432 - Action Taken: Several technical clarification meetings were held with various stakeholders (i.e. core engineering, UPT Team, etc.) prior to submission of final change proposals. 15433 - Recommendation: Owners Team should prepare a clearly define SOW of additional / changed scopes for timely approval of change orders and to obtain competitive change order costs. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Construction | 6299 | Uncontrolled sub- contractor, start work after 9AM | 1. Site coverage is too big | 1. Loss of productivity |  | 16463 - Action Taken: To station one engineer at site 16464 - Recommendation: To have area based organization for certain work. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Engineering | 6283 | Unexpected settlement due to HYDEC Method at specific area | 1. Underlying 4 meters suitable soil cover is insufficient above the peat soil. | 1. Settlement occur for the non piling buildings |  | 16427 - Action Taken: Design review and providing the mitigation plan. 16428 - Recommendation: The system is not recommended for areas where the underlying 4 meters suitable fill is insufficient above the the peat soil area. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28B-EURO 5 | RC-P28B-EURO 5 | Project Management | 6362 | Unexpected site condition in term of rock formation | 1. SI coverages not comprehensive. | 1. Impact schedule to contractors. 2. Impact cost to contractors. |  | - | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Project Management | 6243 | Unfamiliar with regulatory requirement | 1. Late appointment of RLO personnel. 2. Detailed regulatory requirement not available during early stage. | 1. Late establishment of regulatory register. 2. Potential schedule impact / Notice. |  | 16360 - Action Taken: Expedited appointment of local RLO during execution phase. 16361 - Action Taken: Expedited EPCC to establish equipment list and regulatory register. 16362 - Action Taken: Engaged with RAPID regulatory and permitting team. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6184 | Unfamiliarity of RAPID requirements | 1. Few assessment/workshop was held initiated from PRPC which EPCC caught off- handed i.e. issuing template for P14 (DCS- LIMS, DCS-PIMS, P-TASK (previously AMADAS- DCS)), CMMS, etc | 1. Causing higher MH expenditure to satisfy the requirement |  | 16215 - Action Taken: Multiple meeting conducted with other interface point (P14) 16216 - Action Taken: Followed as per directive request from PRPC + Core Team 16217 - Recommendation: ITB to specify more clearly on such acquisition w/ template to be provided so that EPCC may at least knew of what kind of data to be handover to PRPC in proper manner. EPPC also need to place this kind of queries earlier during the bidding 16218 - Recommendation: To have interface coordination at early stage (pre-award) | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Engineering | 6185 | Unfamiliarity of RAPID requirements especially SPI requirements | 1. Communication Gap leading to revision of Instrument / Equipment tag numbers during the final stages of engineering 2. Lack of understanding of SPI requirement. | 1. Additional work or rework of executed work 2. Reordering of hardware , e.g. New tag number templates to be ordered to subvendors 3. Potential Variation Order 4. P&ID and other related deliverables need to be revised due to new tag number |  | 16219 - Recommendation: Information should be shared with the PMC Core team in a joint review session in order to avoid any communication gaps leading to rework during later stages of the project 16220 - Recommendation: To implement standard flow chart of document distribution to all respective discipline engineers to review EPCC documents by creating document distribution traceability by Document Controller | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Project Management | 5867 | Unfamiliarised with IPMT procedures and requirements. A lot of Job Bulletin, site instruction and new procedures on the IPMT procedure update during project execution which required project procedure to keep revise and update. | 1. Lack of control in IPMT procedure & no proper database to keep track these procedures | 1. Project Specification Procedure to be frequently revised and update |  | 15150 - Recommendation: Roll out session on IPMT procedures by IPMT home office to PMT prior mobilization to Engineering office | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Project Management | 6250 | Unfired pressure vessel (UPV) delivered without design approval and HT exemption | 1. Vendor / Fabricator obtained the approval individually. 2. DOSH unable to verify with vendors from overseas. | 1. Late DOSH approval. |  | 16369 - Action Taken: Urged EPCC to update the approval status. 16370 - Action Taken: Owner & EPCC engaged with DOSH to expedite the approval. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | HSSE | 5518 | Unhealthy work life balance of the staff in executing a fast track project | 1. Excessively working overtime 2. Stress due to overloading of works (multitask) 3. Work aggresively to meeting deadline | 1. Poor quality of some of the project deliverables 2. Decrease work performance |  | 14672 - Recommendation: Management to recognize and acknowledge if the team completed some of the milestones 14673 - Recommendation: Reward basis | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | HSSE | 5538 | Unhealthy work life balance of the staff in executing a fast track project | 1. Excessively working overtime 2. Stress due to overloading of works (multitask) 3. Work aggresively to meeting deadline | 1. Poor quality of some of the project deliverables 2. Decrease work performance |  | 14709 - Recommendation: Management to recognize and acknowledge if the team completed some of the milestones 14710 - Recommendation: Reward basis | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Award/Contract | 5888 | Unit rates in the contract ridiculously higher than normal standard practice | 1. Ineffective price rationalization 2. Rates used in USD 3. Heavy reliance to PMC in coming up with price estimation |  |  | 15181 - Recommendation: To ensure cost rationalization against PETRONAS internal price database 15182 - Recommendation: Alternatively, project can hire external consultant to conduct cost rationalization | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5480 | Unnecessary requirement of Independent Professional Civil Engineer in the ITB | 1. Full time independent professional civil engineer registered with the Board of Engineers Malaysia with dedicated responsibility for all QA/QC aspect, having minimum of 5 years’ experience in concrete quality control and testing. | 1. Unnecessary project cost |  | 14604 - Recommendation: This requirement is overzealous and it is not regulatory requirement. Suggest to remove from any future project. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Procurement | 5114 | Unpaid Detention and Demurrage (D&D) Charges are a potential threat to RC logistics/Constructions progress. Several incidents of unpaid D&D almost blocked custom clearance and forwarding of cargo from ports to site. | 1. Outstanding D&D charges due to containers belonging to Ship Liners are being held back by EPCC for extended stay exceeding allowable free detention period of between 14-21 days. | 1. Any shipment with the same name of consignee “PRPC” will be blocked from custom clearance and forwarding of cargo from ports to site if there is outstanding D&D charges. |  | 14222 - Recommendation: If any : EPCC & Forwarder must devise a scheme that allows sufficient invoice processing whilst allowing cargo to be cleared pending settlement of D&D charges. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Precommissioning/Commissioning | 6067 | Unreadiness of RWTP for PAMER full commissioning. | 1. Delay of RWTP from December 2016 to February 2017. | 1. Unable to perform full commissioning. 2. Affect closure of PCC contract. |  | 15652 - Action Taken: Coordination between different work packages. 15653 - Action Taken: Regular engagement with RWTP team. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P6A-LLDPE | PC-P6A-LLDPE | Construction | 5543 | Unsafe and limited access provided at wide excavation area. | 1. Steep slope for access ramp with no proper hand rail and limited access provided for large area of excavation. | 1. Potential HSSE incidents. |  | 14741 - Action Taken: Discussed with CONTRACTOR to provide gentle slope protection, hand rail and adequate numbers of temporary access. 14742 - Recommendation: To spell out technical requirement for temporary access during construction & to include proper sketch for temporary access. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6076 | Unsuitable equipment | 1. Wrong selection of equipment as compare to site conditions i.e. type of dredger | 1. Slow work progress |  | 15542 - Recommendation: Selection of equipment should be done after detailed study of the latest constraint at site and the dredging programme | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5101 | Unsynchronised engineering progress amongst discipline | 1.Untimely precast concrete pipe rack 2. Piping need a large number embedded plates caused by the use of chemical anchor to solve the problem of embedded plate. For precast pipe rack shop drawings are required earlier, according Departments can not provide information opportunely. | 1. The pipe rack shop drawings cannot reflect the increasing embedded plates 2. construction progress delay for increasing work load and difficulty. |  | 14196 - Action Taken: Embedded plates are added by chemical anchor bolts 14197 - Recommendation: Contractor would propose to set long embedded plate on both sides of the pipe rack beam for other Departments if any requirement to set support here. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Project Management | 5410 | Untimely approval for any decision making. | 1. No Project Manager, only programme manager. 2. Too many layer / level for management decision making. | 1. Issues takes longer time to be resolved, i.e. to n fro between UPT, RC and Core Contractor & PMC / OWNER Example: SSU PDR Hydrant configuration. |  | 14470 - Action Taken: Streamline the organization; UPT Project Manager report directly to RC Project Director. 14471 - Action Taken: Revised the LOA to empower the UPT Project Manager. 14472 - Recommendation: Streamline the organization; UPT Project Manager report directly to RC Project Director. 14473 - Recommendation: Revised the LOA to empower the UPT Project Manager. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5091 | Untimely document submission by vendor | 1. Contractor has a tendency to release documents to meet the milestones even when many gaps and issues are still pending. This not only increases the work for PMC in terms of number of documents to be reviewed but also affects the quality of work. It also helps contractor in passing on the his pressure to PMC as contractor claims the document/s are pending for PMC review/comments. | 1. Re-work causing resource constraints 2. Too many documents to be reviewed by the EPCC and OWNER 3. Untimely migration from POL to PEDMS |  | 14167 - Action Taken: Frequent meeting/follow-up conducted between EPCC, PMC and OWNER 14168 - Action Taken: Prioritize the documents submission for the OWNER approval 14169 - Recommendation: Limit the number of revisions 14170 - Recommendation: To set a milestones for the documents submission by vendors (holding power) | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Project Management | 5108 | Untimely mobilization of sufficient workforce | 1. Unfamiliarity of oil&gas project standard compared to General construction standard | 1. Delay in manpower and machineries mobilization 2. Delay in start date |  | 14210 - Recommendation: Plan ahead the schedule 14211 - Recommendation: Review and finalized project procedure at the early stage of project. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B1-MOLF SETAPA | IO-P20B1-MOLF SETAPA | Engineering | 6082 | Untimely mobilization of sufficient workforce | 1. Unfamiliarity of oil & gas project standard compared to General construction standard | 1. Delay in manpower and machineries mobilization 2. Delay in start date |  | 15550 - Recommendation: Plan ahead the schedule 15551 - Recommendation: Review and finalized project procedure at the early stage of project. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20B2-MOLF RAMUNIA | IO-P20B2-MOLF RAMUNIA | Project Management | 6097 | Untimely mobilization of sufficient workforce | 1. Unfamiliarity of oil & gas project standard compared to General construction standard | 1. Delay in manpower and machineries mobilization 2. Delay in start date |  | 15522 - Action Taken: Plan ahead the schedule 15523 - Action Taken: Review and finalized project procedure at the early stage of project. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > Package 18A&B-EPCC | Package 18A&B-EPCC | Undefined | 2071 | Untimely mobilization of sufficient workforce | -Unfamiliarity of oil&gas project standard compared to General construction standard | -Delay in manpower and machineries mobilization -Delay in start date | -Plan ahead the schedule -Review and finalized project procedure at the early stage of project. | - | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5198 | Untimely Technical Decision Making. | 1. Lengthy decision process from Core Team. 2. Conflict between PTS and Project RAPID requirement 3. Last minute changes by contractors. | 1. Schedule impact on subsequent activities. 2. May impact cost due to additional man hours required. |  | 14250 - Respective Project Mgmt. Team at EPCC office to be given certain authority to immediately decide within certain guideline without the need to go through Core Team. 14251 - To develop work process to support timely decision making. 14252 - EPCC to follow PTS requirement subject to contract. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Engineering | 5205 | Use of Copper Alloy for cooling water heat exchangers. | 1. Use of copper alloy technically acceptable as per several PTS. 2. Use of copper alloy not allowed only as per Utilities requirement. | 1. Confusion between UPT and Core Team leading to late decision making. |  | 14264 - If copper alloy not allowed, all the affected PTS needs to be updated. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Engineering | 5392 | Using Old PTS (34.24.26.31 - August 2012) which is totally different compared to current PTS (12.42.01 - April 2015): i.e. Stack design. | 1. Awarded contract is referring to previous version of PTS. 2. New PTS is only issued post-award. | 1. Delay in finalization of stack design. |  | 14437 - Recommendation: Derrick design is preferable than self-supporting double wall design due to accessibility during inspection and maintenance. 14438 - Recommendation: Latest PTS 12.42.01 (April 2015) to be included in future ITB. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Engineering | 5951 | Utilized old/IFR revision of PID during DCS FAT. | 1. Major changes on the IO assignment. | 1. FAT have been extended due to major modification on the DCS cabinet construction. |  | 15761 - Recommendation: All relevance engineering drawings has to be freeze prior to start FAT. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5762 | Vague ITB requirement on Key personnel. | 1. One example is Key personnel requirement is not fully specified. 2. ITB only specified years of experience without stressing on the specific technology / similar experience. | 1. Bidder nominated personnel that only meeting the years of experience even though have no specific / similar experience. |  | 15359 - Action Taken: Request resubmission of suitable candidates. 15360 - Recommendation: To improve ITB requirement, to specify similar experience as one of the key factor. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Procurement | 5864 | VDR Process and Interface with Procurement- Engineering- Project Control to be monitored at micro level. High volume of VDR for complicated static equipment and rotating package (especially for E&I) drawing. | 1. Lack of coordination between contractors procurement , engineering and project control to effectively monitor and close Vendor documents | 1. Delay in engineering and procurement progress 2. Delay in delivery of the equipment |  | 15141 - Action taken: Frequent meeting 15142 - Recommendation: Include payment milestone for vendor document | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5096 | Vendor Deviation Management Procedure (Pre-order Stage) | 1. There was no proper procedure within RAPID or in the ITB for the CONTRACTORs to follow. 2. PMC had difficulty in managing the vendor deviation review process without proper guideline. | 1. Schedule impact. The first submission was delayed due to un-developed procedure. |  | 14180 - Action Taken: Project has to develop a procedure/guideline and propose to Directorate PMT for implementation after receiving the first vendors deviation list from Contractor. 14181 - Recommendation: Project to ensure complete Deviation Management Procedure is in place / available prior to project execution. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P7-POLYPROPYLENE | PC-P7-POLYPROPYLENE | Undefined | 5892 | Vendor document management |  |  |  | 15187 - Suggestion for Improvement: It’s recommended that the vendor documents upload can be more efficient. The original documents/commented documents can be sent and accepted by both parts (vendor can contractor) by mail as another path besides the official TR | 0
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P1-RFCC, LTU, PRU | RC-P1-RFCC, LTU, PRU | Engineering | 5097 | Vendor Equipment PO and Engineering Deliverables submission shall meet / synchronise with overall project planned schedule for Engineering Review and Studies (e.g. 3D Model Review, IPF etc) | 1. Unreadiness / unavailability of vendor data / information. | 1. Schedule Impact. 2. Impact on 60% and 90% Model Review |  | 14182 - Action taken: A separate Model Review conducted for the late packages 14183 - Action taken: Use common or typical model/dimension in the 3D for initial assessment 14184 - Recommendation: Project to close monitor / ensure Equiment PO and Vendor Engineering Deliverables proposal and submission shall meet / synchronise with overall project planned schedule. | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > ASU-AIR SEPARATION UNIT | ASU-AIR SEPARATION UNIT | Procurement | 6234 | Vendor not provide extra allowance on field packing item (e.g. CW component, consumable item) | 1. Lack of monitoring on the packing list vs actual site requirement. | 1. Insufficient items from vendor. |  | 16348 - Recommendation: To consider extra allowance +10%. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P4-ARU, SRU, SWS, LSSU & SSU | RC-P4-ARU, SRU, SWS, LSSU & SSU | Procurement | 5403 | Vendor package engineering resulting in late design changes; i) Amine reclaimer process effluent, utilities. ii) Caustic scrubber effluent, utilities. | 1. P.O was issued late. 2. Late confirmation on the finalized design. | 1. P.O was issued late. 2. Late confirmation on the finalized design. |  | 14452 - Action Taken: Expedited vendor. 14453 - Recommendation: To minimize design ambiguities / unknowns related to vendor package items prior detailed engineering. 14454 - Recommendation: More weightage can be included in the project schedule / project management / risk for vendor package units (e.g. caustic scrubber, reclaimer). | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P22-Tank Farm | RC-P22-Tank Farm | Engineering | 5497 | Vendors are good as a fabricator and provide process guarantee. But when it comes to skid design and 3D model / GAD / Isometric development - vendor is found not educated enough to understand the space requirements operability and accessible issues. | 1. Already included in Model Construction Methodology | 1. Scope of Vendor Equipment on Skid. 2. This causes several revisions of the document to be reviewed also affects the schedule of Civil foundation design and underground design. |  | 14629 - Recommendation: Recommend to clarify from the Proposal stage that we will only model package as a box showing interface details which are necessary for our work. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P32-QMI | RC-P32-QMI | Procurement | 6192 | Very few selection of competitive, technically sound and reliable suppliers listed in RAPID Approved Vendor List for HVAC Unit for analyser house hazardous area application. | 1. Difficulty of sourcing out for the most appropriate with competitive price product for this HVAC Unit application. | 1. Paying a higher fee for the HVAC Unit with unsatisfied performance. |  | 16228 - Action Taken: Registered a new HVAC Unit manufacturer (Stolway) in RAPID AVL. This Stolway has a wide range of experience when it comes to HVAC unit application for Analyser Houses. Few units were also supplied in Petronas Project such as: SAMUR Project. 16229 - Recommendation: To extend approved vendor list specific for HVAC analyzer house hazardous area | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Undefined | 5812 | Wind & Seismic Load | 1. There was discrepancy between Civil Design Criteria and Design of Pressure Vessels regarding Wind and Seismic Load. | 1. Deferent codes are applied. - Vessel : ASCE - Civil : Bsi |  | 15470 - Action Taken: APPLY Bigger Value for Seismic and Wind Load. 15471 - Action Taken: Eurocode 8 vs ASCE 7-10 (Seismic) MS 1553 vs ASCE 7-10 (Wind). 15472 - Recommendation: Preventive Action. 15473 - Recommendation: Modification of Specifications to Match Each Other is Required | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P30-ADDITIONAL OLEFINS STORAGE | RC-P30-ADDITIONAL OLEFINS STORAGE | Award/Contract | 5539 | Withdrawal of SI letter award | 1. Contractor did not agreed with T&C | 1. Delayed in SI award 2. Rework on SI award to different contractor. |  | 14711 - Action Taken: Meeting with the contractor to convince to accept the offer prior to award. 14712 - Action Taken: Award to another contractor. 14713 - Recommendation: Standard T&C to be applied | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > RC-P28-EURO 5 MOGAS | RC-P28-EURO 5 MOGAS | Project Management | 5514 | Work within unrealized target schedule (fast track, industrial practice 27 months). Challenges in doing project in fast track environment | 1. New (late) direction by management to pursue on this project (after RAPID FID) | 1. Poor quality of some project deliverables 2. Late submission of some project documents 3. Impact other existing Refinery project interfaces |  | 14665 - Action taken: Appointed reliable and competent EPCC contractors to execute the project by competitive bidding process 14666 - Recommendation: Management to verify the target schedule with the targeted allocation of resources (manpower, system) | 3
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Construction | 6035 | Workers camp not 100% comply to IFC requirements. | 1. Project taken from state government where IFCs specifications were not part of the requirements. 2. IFC requirements were not specified upfront as part of the ITB document and therefore Owners team, Consultant and Contractor were not aware of the requirements. | 1. Not meeting IFC requirement - noncompliance during audit by GHSE. 2. Delay in ensuring compliance. 3. Disagreement among the parties - Owner and Contractor. |  | 15585 - Action Taken: Negotiated with contractor to comply the IFC requirement without cost impact. 15586 - Recommendation: To clearly include the IFC requirement in ITB, and to clearly highlight the requirements during ITB briefing to all bidders. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | HSSE | 6314 | Working without work permit, or violating safety rules. | 1. Contractor do not understand PETRONAS requirment. (First Time) | 1. Stop Work |  | 16490 - Action Taken: Training provided 16491 - Recommendation: To have an experience HSE Manager | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > CLOSE OUT > IO-P20A1-TCCF & INFRA | IO-P20A1-TCCF & INFRA | Project Management | 6308 | Works split between OWNER and authority for 33kv incoming supply substation. | 1. Risk of the authority delay not assessed in details. 2. Late appointment of subcontractor by TNB (super structural work and equipment) | 1. Schedule delay |  | 16478 - Action Taken: Escalated to higher level and followed up at Putrajaya (PEMANDU & JPDC) 16479 - Action Taken: Managed to ensure TNB to provide temporary portable switch gears. 16480 - Recommendation: To anticipate early any possible delay by authority and mitigate accordingly. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | P25-RAW WATER SUPPPLY PROJECT (PAMER) TO RAPID | Construction | 6039 | Wrong application of construction method by main contractor for the construction of Intake Works. | 1. Missed judge by main contractor on the complexity of the earthwork, causing wrong construction method / equipment / resources. | 1. Schedule delay at Intake. 2. Late start of M&E works, and therefore late commencement of Intake pumping. |  | 15596 - Action Taken: Contractor had to install 2 tower cranes in the middle of project stage. 15597 - Action Taken: Contractor proposal on method selection must be reviewed and agreed by PMT. 15598 - Action Taken: Close monitoring by PMT (on weekly basis) and through Risk Management Committee. | 1
RAPID PMT > Knowledge Base > Project Lesson Learned > ENGINEERING & PROCUREMENT > PC-P11-EO & EG | PC-P11-EO & EG | Engineering | 5706 | Wrong risk matrix used for ECA | 1. As per ITB, Sec C Part II Att. 4B – ECA Guideline, the risk matrix attached was the old one 4x5. 2. ITB was not specific enough that leaves gap in interpretation. | 1. ECA rework. 2. ITP for critical equipment had to be readjusted. 3. Procurement strategy changed during middle stage of execution and led to potential claim. |  | 15225 - Action Taken: Close discussion with CONTRACTOR to persuade them to absorb the additional scope based on spirit of good relationship. 15226 - Recommendation: To correct the ITB on utilizing the new 5x5 risk matrix. | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > RC-P2-CDU, ARDS, HCDU | RC-P2-CDU, ARDS, HCDU | Quality | 5280 | Wrong use of gasket type. Unable to identify gasket type after installation | 1. Not aware or wrong selection of gasket type prior install | 1. Damage of gasket or leaking at flange connection Rework |  | 14395 - Action Taken: To make color coding (rating) for each type of gasket | 2
RAPID PMT > Knowledge Base > Project Lesson Learned > CONSTRUCTION > IO-P16B-RWTP | IO-P16B-RWTP | Construction | 6021 | Y 10 earthling rebar has to be laid as per drawing and welded for continues conductivity throughout concrete slab | 1. Earthling cable unavailable and improper earthling connection observe in some point or area | 1. Y 10 earthling rebar not laid or welded at some point or area before structural concrete casting. |  | 15880 - Action Taken: Separate earthling cable need to lay from the earthling grid to effected equipment’s via cable or earth copper bar. 15881 - Recommendation: Proper inspection and supervision has to be carry out before concrete casting of the floor. | 1